## Cover
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
FINANCIAL MODEL AND MONTHLY REPORTING PACK
Construction and renovation demonstration: deep retrofit (SEAI One Stop Shop), renovation, commercial fit-out and council retrofit
FICTIONAL DEMONSTRATION. Tarnlea Build & Retrofit Ltd does not exist. Every name, client, subcontractor, contract, invoice and balance in this workbook was generated for demonstration purposes and does not describe any real company, client or person. Tax rates and filing rules reflect published Irish rules as at September 2026. Prepared by BriQs Group to show the structure, depth and controls of a monthly finance pack.
Reporting month (last actual) | 2026-08-31
Forecast horizon | Sep-26 to Dec-27 (Base scenario selected)
Currency | EUR
Model status (all integrity checks) | OK
FY2026 revenue, outlook | 9197434.2432
FY2026 EBITDA, outlook | 424278.3155
Secured work in hand at the last actual month | 5341427.57
Cash at the last actual month | 634504.3727
13-week cash low point | 230046.3917
Prepared by | BriQs Group, outsourced finance department and fractional CFO (ACCA-qualified accountant, ex Big Four accounting firms, Xero and QuickBooks Partner)
CONTENTS | What the sheet holds | Type
Cover | This page | Report
Guide | Model map, contract accounting method, conventions, month-end procedure, scenario refresh, information still needed | Report
Checks | Every integrity check with live status; overall status and business warnings | Control
CFO_Report | Quantified findings, scored risks, actions with owners and dates | Report
KPIs | Margin, order book, utilisation, working capital, cash and bond KPIs by month | Report
PL | Monthly P&L by segment, actual and forecast | Statement
BS | Monthly balance sheet with zero check | Statement
CF | Cash flow, indirect and direct, reconciled monthly | Statement
BvA | Budget vs actual YTD and full-year outlook, gross profit bridge by segment | Analysis
Scenarios | Base, downside and upside with live selected column | Analysis
Cash_13W | 13-week direct cash forecast: tax weeks, payment runs, buffer control, reconciliation | Analysis
Project_Profitability | Contract and programme margins with full allocation of labour variance, fleet and overheads; margin movement vs tender | Analysis
WIP | Percentage of completion engine per contract: cost to complete, revenue, provisions, valuations, retentions, cash | Schedule
Residential | Retrofit and renovation programmes: starts, revenue, billing stages, SEAI grant claims | Schedule
Pipeline | Secured work in hand, weighted pipeline, cover, order intake and book-to-bill | Schedule
Variations | Variations register with policy constraint and scenario outcome | Schedule
Commitments | Orders placed vs cost to complete; uncommitted exposure by contract | Schedule
Retentions | Retentions held by clients and from subcontractors; legacy and disputed balances | Schedule
Receivables | Receivables by customer group and days | Schedule
AR_Aging | Aged receivables at the last actual month, tied to the ledger | Schedule
AP_Aging | Aged payables with RCT rates, tied to the Payables schedule | Schedule
Payables | Subcontractors (reverse charge, RCT), materials, plant, overheads | Schedule
VAT_RCT | Bi-monthly VAT and monthly RCT rolls | Schedule
Resources | Site headcount, utilisation, labour recovery, agency and fleet | Schedule
Overheads | Office staff, overhead lines, payroll taxes | Schedule
Fixed_Assets | Vans, plant and tools, IT | Schedule
Debt | Hire purchase, overdraft facility, performance bonds | Schedule
Project_Register | Contract master data, effective dates, forecast cost at completion | Inputs
Assumptions | Scalars, timeline and scenario drivers with the selector | Inputs
Inputs_Actuals | Actual months and opening balances; the only place actual data is typed | Inputs
Budget_FY26 | The original FY2026 budget, never overwritten | Inputs
COLOUR LEGEND
Input (typed value)
Formula (calculated)
Link from another sheet
Actual month (column header)
Forecast month (row 5 flag F)

## Guide
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
MODEL GUIDE
PURPOSE
An integrated monthly finance pack for a founder-led Irish contractor with four lines of business: deep home retrofit as an SEAI One Stop Shop, private renovation and extensions, commercial fit-out, and council retrofit under a framework. It closes the month into a three-statement pack, values every contract on the cost-to-cost method, controls cost to complete against commitments, tracks variations and retentions, forecasts under three scenarios, projects cash week by week for 13 weeks and reports to the owners with quantified findings.
Every number traces back: statement line to schedule, schedule to register or input, input to the document that evidences it in a real close (cost ledger, cost report, payment certificate, bank statement, RCT deduction summary, SEAI claim).
HOW THE MODEL FLOWS
1. Inputs_Actuals holds the actual months and the opening balance sheet. Project_Register holds the contract terms and FY2025 closing positions of each named contract; Variations and Commitments hold the registers. Assumptions holds the timeline, rates and scenario drivers (selector in C11).
2. WIP values each named contract every month: cost incurred (actuals, then the remaining cost to complete spread on an S-curve to the effective completion date), estimated cost at completion, % complete, contract revenue including variations, revenue recognised, onerous contract provisions, gross value certified, retention, invoicing, VAT, cash and contract assets or liabilities.
3. Residential runs the two programmes: jobs started x average value, earned over the job duration; homeowner stage invoices; SEAI grant claims lodged after completion and the post-works BER; snag retentions.
4. Resources compares own labour charged to jobs at the standard rate with site payroll and agency cost (recovery variance) and carries the fleet. Overheads holds office payroll, overhead lines and payroll taxes.
5. Retentions, Receivables, Payables and VAT_RCT roll every working capital balance; Fixed_Assets and Debt hold capex, hire purchase, the overdraft facility and performance bonds.
6. PL, BS and CF link only to schedules; CF is built indirectly and reconciled every month to a direct build of the schedule cash lines.
7. BvA, Pipeline, Project_Profitability, KPIs, Scenarios, Cash_13W, the agings and CFO_Report are reporting layers; Checks proves the structure holds.
CONTRACT ACCOUNTING METHOD
Revenue over time on the input method: % complete = cost to date / estimated cost at completion (IFRS 15.B18; the same stage-of-completion principle as FRS 102 Section 23). Revenue to date = % complete x contract revenue.
Contract revenue = original contract + approved variations + undecided variations at the policy constraint (50%, the amount judged highly probable not to reverse, IFRS 15.56) + pending variations at the scenario agreed share once their expected decision date passes.
Where estimated cost at completion exceeds contract revenue, the expected loss not yet recognised is provided in full (onerous contract provision, IAS 37). Provisions reverse as the contract completes.
Contract position per contract = revenue to date less gross value certified: a contract asset when positive, a contract liability when negative. Retention is a receivable, not part of the contract position.
Actual months: revenue is the ledger figure and the Checks sheet proves it equals % complete x contract revenue using the cost report of that month.
IRISH TAX MECHANICS MODELLED
VAT: 13.5% on construction services to homeowners and commercial clients; council contracts reverse charged (the council is a principal contractor and accounts for the VAT); subcontractor services to the company reverse charged (output and input VAT net to zero); materials, plant hire, agency labour and most overheads at 23%. Bi-monthly returns paid by the 23rd of the following month (ROS).
RCT: deducted from subcontractor payments at the rate Revenue authorises (0%, 20% or 35%, blended on the current mix) and paid over by the 23rd of the following month. Council payments to the company carry RCT at 0%.
Payroll: employer PRSI at 11.25% to 30-Sep-26 and 11.40% from 1-Oct-26; PAYE, USC, PRSI and pension remitted by the 23rd of the following month.
Corporation tax: 12.5% on trading profits; small company preliminary tax on 23 November at 100% of the prior year; balance on 23 September after year end.
SEAI One Stop Shop: the grant is deducted from the homeowner price and paid to the company after completion and the post-works BER; the model treats the grant as part of the VAT-inclusive consideration (confirm with the VAT adviser).
CONVENTIONS
Revenue and receipts positive; costs, payments and deductions negative on the P&L and cash flow. Schedules show movements with their natural sign and a closing line.
Blue on yellow = input; black = formula; green = link from another sheet. Columns C and D on monthly sheets are FY2026 and FY2027 totals (sum, average or closing balance as labelled).
Row 5 of every monthly sheet flags A (actual) or F (forecast); formulas switch on it, so nothing is overwritten when a month becomes actual.
Pipeline contracts are weighted by the win probability of the selected scenario; every flow of a pipeline contract (revenue, cost, cash, bonds) is scaled by it.
MONTH-END PROCEDURE (adding September as an actual month)
1. Enter the September cost ledger by contract and cost type, the cost report cost to complete, revenue recognised, payment certificates and receipts for each named contract; the residential job data; payroll, agency, fleet, overheads, capex and supplier payments.
2. Change the last actual month on Assumptions to Sep-26. Flags, run-rates, cost-to-complete positions, agings and the 13-week opening follow from that cell.
3. Update the Variations register (new, approved, rejected, expected decision dates) and the Commitments register (new orders, invoiced to date).
4. Refresh the AR and AP agings from the ledger listings; the tie-out rows must return zero. Roll the 13-week window forward one month.
5. Refresh the scenario snapshots, reread Checks until the overall status is OK, then rewrite the CFO report findings against the new numbers.
SCENARIO REFRESH
Set Assumptions!C11 to 1 (Base), 2 (Downside) and 3 (Upside) in turn. After each recalculation copy Scenarios column F and paste values into C, D or E. The check column confirms the snapshot for the selected scenario matches the live model.
KNOWN SIMPLIFICATIONS
Forecast receipts and payments are sized by payment days on the invoiced amounts; actual months use bank figures.
Residential contract assets and liabilities are netted at programme level; job-level netting would move a small amount between the two.
Named contract cost types in forecast months follow the mix on Project_Register; the commitments register shows what is already bought.
Own labour is charged to jobs as a share of direct cost; utilisation above 100% is bought from an agency. The standard rate is set to recover payroll at 85% utilisation.
Corporation tax accrues on cumulative profit of each year with no loss carry-forward; capital allowances are assumed equal to depreciation.
Performance bonds run from award to practical completion at the contract bond percentage; release to a reduced bond during the defects period is not modelled.
INFORMATION NEEDED TO CONVERT THIS INTO A CLIENT BUILD
Monthly cost reports per contract with cost to complete by cost code, signed off by the project manager and quantity surveyor.
Payment certificates, payment notices and pay less notices per contract, to replace the one-month certification lag assumption.
The variations register with client correspondence and the quantity surveyor view of recoverability, to support the policy constraint.
RCT deduction summaries (ROS) and each subcontractor deduction authorisation, to replace the blended rate.
SEAI claim listing with BER publication dates and inspection outcomes, to replace the grant payment days assumption.
Timesheets by job and operative, to replace the labour-share allocation with hours actually booked.
The FY2026 corporation tax computation (capital allowances, disallowables) and confirmation of any later PRSI changes.

## Checks
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
MODEL INTEGRITY CHECKS
Every check is a live formula. A value of zero (or at least zero where a minimum is tested) returns OK. The overall status shows on the Cover.
Check | What it proves | Value | Tolerance | Status
STATEMENT INTEGRITY
Balance sheet balances in every month | Total assets less liabilities and equity, all 24 months | 0.24 | 0.5 | OK
Cash flow: indirect method equals direct method every month | P&L and balance sheet movements equal the sum of the schedule cash lines | 0 | 0.5 | OK
Closing cash on the cash flow equals balance sheet cash | Link integrity | 0 | 0.5 | OK
Retained earnings roll: closing = opening + profit - dividends | Equity roll-forward to Dec-27 | 0 | 0.5 | OK
EBITDA on the cash flow equals EBITDA on the P&L | Add-backs complete | 0 | 0.5 | OK
Opening balance sheet at 31-Dec-25 balances | FY2025 closing balances on Inputs_Actuals and Project_Register | 0.0065 | 0.5 | OK
CONTRACT ACCOUNTING
Revenue recognised in actual months equals % complete x contract revenue | Ledger revenue agrees with the cost-to-cost method, every contract, every actual month | 0 | 0.5 | OK
Forecast cost spread equals cost to complete, contracts finishing within the horizon | S-curve phasing neither loses nor adds cost | 0 | 0.5 | OK
Variations in contract value at the last actual month agree with the register | WIP engine and Variations register apply the same policy | 0 | 0.5 | OK
Percentage complete stays between 0% and 100% | No over-recognition | 0 | 0.0001 | OK
Retrofit revenue shares sum to 100% | Every job is fully earned | 0 | 1e-06 | OK
Renovation revenue shares sum to 100% |  | 0 | 1e-06 | OK
Retrofit homeowner stage invoices sum to 100% | Homeowner portion fully invoiced | 0 | 1e-06 | OK
Renovation billing (deposit + progress + snag) sums to 100% | Contract value fully invoiced | 0 | 1e-06 | OK
Programme cost mixes sum to 100% |  | 0 | 1e-06 | OK
Named contract cost mixes: preliminaries share not negative (minimum) | Mix shares on Project_Register are complete | 0.05 | 0 | OK
Cost to complete covers every remaining commitment (minimum uncommitted balance) | No contract has more on order than its cost to complete | 94307.6 | 0 | OK
Project profitability: allocated net contributions equal EBITDA | Labour variance, fleet and overheads are fully allocated | 0 | 0.5 | OK
WORKING CAPITAL TIE-OUTS
AR aging: commercial ties to the ledger | Item listing agrees with the balance at the last actual month | 0 | 0.5 | OK
AR aging: council ties to the ledger | Item listing agrees with the balance at the last actual month | 0 | 0.5 | OK
AR aging: homeowners ties to the ledger | Item listing agrees with the balance at the last actual month | 0 | 0.5 | OK
AR aging: seai grants ties to the ledger | Item listing agrees with the balance at the last actual month | 0 | 0.5 | OK
AR aging: other ties to the ledger | Item listing agrees with the balance at the last actual month | 0 | 0.5 | OK
AP aging: subcontractors ties to the Payables schedule |  | 0 | 0.5 | OK
AP aging: materials ties to the Payables schedule |  | 0 | 0.5 | OK
AP aging: plant and site services ties to the Payables schedule |  | 0 | 0.5 | OK
AP aging: overheads ties to the Payables schedule |  | 0 | 0.5 | OK
FORECAST CONTROLS
13-week cash forecast reconciles to the monthly balance sheet at 31-Dec-26 | Weekly phasing distributes exactly the monthly cash lines | 0 | 0.5 | OK
Scenario snapshots are current for the selected scenario | Live column equals the stored snapshot | 0 | 0.5 | OK
Budget vs actual gross profit bridge reconciles to the P&L variance | Volume plus margin effects equal the gross profit variance | 0 | 0.5 | OK
SIGN AND RANGE CHECKS (minimum values, must not be negative)
Trade receivables never negative |  | 277981.8962 | 0 | OK
SEAI grant receivable never negative |  | 108387.05 | 0 | OK
Retentions receivable never negative |  | 116889.7435 | 0 | OK
Trade payables never negative |  | 430174.3928 | 0 | OK
Fixed asset net book value never negative |  | 168589.9167 | 0 | OK
Hire purchase balance never negative |  | 112831.25 | 0 | OK
Timeline: months flagged actual equal the last actual month number |  | 0 | 0.5 | OK
OVERALL MODEL STATUS |  |  |  | OK
BUSINESS WARNINGS (not model errors: flags for the CFO report)
Lowest month-end cash in the forecast (selected scenario) | Below the buffer means a facility draw or action | 418470.3684
Lowest 13-week closing cash |  | 230046.3917
Peak bond facility utilisation | Above 100% means new contracts cannot be bonded | 88.27%
Lowest forecast site utilisation | Below 75% signals idle labour | 61.62%
Largest onerous contract provision in the forecast | A loss-making contract | 0
Variations raised and undecided at the last actual month (claimed) | Revenue at risk if not agreed | 168400

## CFO_Report
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
CFO MANAGEMENT REPORT
Reporting month: Aug-26 actuals, Base scenario for the outlook. Amounts in EUR. Every figure is a live link to the model; the narrative recalculates with the inputs.
FICTIONAL DEMONSTRATION: Tarnlea Build & Retrofit Ltd and every figure in this report were generated for demonstration purposes.
1. HEADLINE
Year to date revenue is EUR 5,127k, 19.5% below budget, and EBITDA is EUR 45k against EUR 333k budgeted. Three causes account for it: volume (three contracts started two months later than budgeted and retrofit starts ran 22% behind), margin fade on the CF-2601 office fit-out, and idle site labour in the first half (EUR 77k of site payroll not recovered on jobs).
Full-year outlook (Base): revenue EUR 9,197k (-8.4% vs budget), gross margin 18.3%, EBITDA EUR 424k (4.6%). It needs EUR 4,070k of revenue in the last four months, EUR 1,018k a month against EUR 641k a month so far: the four live contracts peak together and the site team runs at full utilisation with agency support.
Cash is EUR 635k at Aug-26. The 13-week low is EUR 230k in the week ending 27-Nov, when PAYE, RCT, VAT and the FY2026 preliminary tax fall due in the same week as the subcontractor payment run: EUR 30k above the EUR 200k buffer, with the overdraft undrawn. In the Downside case cash goes EUR 27k overdrawn in Nov-26, a EUR 227k shortfall against the buffer that the EUR 250k overdraft only just covers.
FY2027 Base: revenue EUR 9,703k and EBITDA EUR 264k (2.7%), down from FY2026 because overheads rise EUR 194k (two office hires and inflation) and the planned site hires land in a first-quarter trough, with utilisation at 62%. Hiring should follow secured work, not precede it.
2. WHAT HAPPENED YEAR TO DATE (BvA, Residential, Resources)
The gross profit shortfall of EUR 267k splits into EUR 214k of volume and EUR 53k of margin. Retrofit is the largest volume gap: 22 homes started against 28 budgeted (the retrofit coordinator post was vacant from March to May, so surveys and grant applications backed up), worth EUR 98k of gross profit. Commercial fit-out and council revenue are behind because CF-2602, CF-2603 and PS-2601 started later than the budget assumed.
Margins: commercial fit-out earned 12.0% against 14.8% budgeted (EUR 44k of margin, almost all CF-2601); council retrofit earned 15.4% against 13.0% (PS-2502 closed out below budget cost); retrofit 21.9% against 24.5%, where the vacancy months also carried lower margins; renovation held its budget margin.
Site labour: own labour charged to jobs fell short of site payroll by EUR 77k year to date. Utilisation was 61% to 65% from February to April while named work ran down, then 100% from July with agency operatives. Overheads are EUR 40k better than budget, mostly the coordinator vacancy, after a EUR 9,500 specific provision against the disputed CF-2311 retention.
3. CONTRACTS: MARGINS, VARIATIONS AND COST TO COMPLETE (WIP, Variations, Commitments, Project_Profitability)
CF-2601 (office fit-out, Dublin 4) is the contract to manage. Tender margin 13.7%; estimated cost at completion is now EUR 1,190k, EUR 172k above the tender budget, after the mechanical and electrical subcontractor was replaced in May and the client changed the design twice. EUR 118k of variations are claimed and undecided; policy recognises half. Forecast final margin is 7.7% in the Base case, and EUR 385k of the cost incurred has not yet come back in cash (work not yet certified, unpaid certificates and retention).
Across all contracts EUR 168k of variations are undecided. The policy constraint recognises EUR 84k; the Base case expects EUR 109k to be agreed, a EUR 25k upside to revenue when the decisions land. The scenario range is EUR 84k of revenue between Upside and Downside, almost all of it profit.
Cost to complete is under control on paper: EUR 4,118k remains on live and signed contracts, of which EUR 1,531k is already committed on orders (37%; 67% on CF-2601). No contract has more on order than its cost to complete, so the forecasts carry every known commitment. The uncommitted EUR 112k on CF-2601 is where further fade would come from: it should be bought before October.
Allocated profitability (FY2026 outlook, after labour variance, fleet and overhead absorption): CF-2601 contributes EUR -73k, the retrofit programme EUR 173k and the renovation programme EUR 216k. The residential programmes earn 92% of EBITDA on 45% of revenue.
4. CASH, WORKING CAPITAL AND THE 13 WEEKS (BS, Receivables, Retentions, Cash_13W)
Working capital tied up in contracts is EUR 580k at Aug-26: contract assets EUR 722k (work done, not yet certified: CF-2601 EUR 202k and PS-2601 EUR 177k), trade receivables EUR 639k (28 days), retentions EUR 154k and SEAI grant claims EUR 108k (60 days). It is funded by EUR 967k of payables, with materials suppliers carried at about 46 days.
The 13 weeks from 12-Sep: opening cash EUR 704k, receipts EUR 2,976k, payments EUR 3,174k, closing EUR 507k on 11-Dec. EUR 320k of tax leaves in the three weeks containing the 23rd (PAYE, RCT, VAT, corporation tax), which is why the 23-Sep and 23-Nov weeks are the pinch points. The forecast reconciles to the December balance sheet to the euro.
Retentions: EUR 107k is held by current clients and releases on practical completion and after the defects periods; the legacy CF-2311 retention of EUR 38k has been overdue since the defects period ended in March 2025. A EUR 9,500 provision is held; the Base case settles it in Nov-26 at 75% recovery.
5. ORDER BOOK, CAPACITY AND BONDS (Pipeline, Resources, Debt)
Secured work in hand is EUR 5,341k at Aug-26, 6.5 months of revenue, falling to EUR 2,860k by December as the live contracts finish. FY2027 revenue therefore leans on the pipeline: EUR 2,286k (24%) of the Base FY2027 revenue comes from contracts not yet won, probability-weighted.
Capacity: own labour demand exceeds the site team from July to November, costing EUR 98k of agency labour in FY2026, then falls away in the first quarter of 2027 while five hires join, taking utilisation to 62% and the FY2027 labour recovery variance to EUR -81k. Performance bonds use 83% of the EUR 750k surety facility now and peak at 88%: the facility, not the pipeline, becomes the constraint on new commercial awards.
6. SCENARIOS (Scenarios sheet; snapshot values from three full model runs)
Base: FY2027 revenue EUR 9,703k, EBITDA EUR 264k, lowest cash EUR 418k. Downside (fewer retrofit starts, two-month delays, 5% overrun on cost to complete, variations agreed at 35%, slower payment): FY2027 revenue EUR 7,972k, EBITDA EUR -181k, lowest cash EUR -27k. Upside: FY2027 revenue EUR 10,898k, EBITDA EUR 735k, lowest cash EUR 543k.
The Downside is survivable only with the overdraft in place and the hiring plan frozen: it turns FY2027 EBITDA negative and takes cash below zero in Nov-26. The triggers to act on are monthly: retrofit starts below 2.8 a month for two months, any contract margin fade above 2 points in a cost review, or SEAI days above 75.
7. RISK REGISTER (scored 1 to 5; score = likelihood x impact)
| Risk | Likelihood | Impact | Score | Mitigation and owner
| Cash pinch points: tax payments cluster on the 23rd and the subcontractor run on the 25th; the Downside breaches the buffer by EUR 227k | 3 | 4 | 12 | Confirm the EUR 250k overdraft is committed and draw it for the tax weeks if needed; weekly 13-week review; Finance Manager
| CF-2601 margin: cost at completion EUR 172k over tender; EUR 118k of variations undecided | 4 | 3 | 12 | Weekly commercial review; submit fully substantiated variation claims; buy the uncommitted packages before October; Commercial Manager
| Order book cliff: secured work falls to EUR 2,860k by Dec-26; FY2027 depends on pipeline conversion | 3 | 4 | 12 | Bid pipeline review every two weeks with win-probability discipline; target two commercial awards by Q1-27; Managing Director
| Site capacity: 100% utilisation Jul to Nov then 62% in Q1-27 as hires join | 4 | 3 | 12 | Tie each site hire to a secured contract start; use agency for peaks; Contracts Manager
| Bond capacity: surety facility peaks at 88% utilised; new awards need 10% bonds | 3 | 3 | 9 | Open talks with the surety for a EUR 1m facility before the CF-P01 award; seek bond reduction at practical completion; Finance Manager
| SEAI grant claims: EUR 108k outstanding at 60 days; inspection queries delay payment | 3 | 3 | 9 | Claim the week the post-works BER publishes; pre-inspection checklist on airtightness and ventilation; Retrofit Coordinator
| Subcontractor tax compliance: one decorator is at the 35% RCT rate; paying without a deduction authorisation carries penalties and exposure to 35% tax | 2 | 3 | 6 | No payment released without a deduction authorisation; quarterly review of subcontractor rates; Finance Manager
| Disputed legacy retention CF-2311: EUR 38k overdue since March 2025 | 3 | 2 | 6 | Mediation with the client; release against a defects inspection; write off the provided share if not settled by year end; Managing Director
| Council concentration: one council framework is the only public sector client and the largest single customer | 2 | 4 | 8 | Qualify for a second local authority framework and an approved housing body panel in FY2027; Managing Director
| Supplier credit: materials suppliers carried at about 46 days; a tightening of credit limits would absorb cash quickly | 3 | 3 | 9 | Agree account limits with the two main merchants; keep materials terms at 30 days end of month; Finance Manager
8. ACTIONS (owner, due date, status)
| Action | Owner | Due | Status | Measure of done
| Submit substantiated claims for V-CF2601-02, -03 and -04 and agree them at the October valuation meeting; buy the uncommitted CF-2601 packages | Commercial Manager | 2026-10-09 | Open | Variations agreed in writing; CF-2601 cost to complete fully committed
| Confirm the EUR 250k overdraft is committed through Q1-27 and pre-agree drawings for the weeks of 23-Sep and 23-Nov | Finance Manager | 2026-09-18 | Open | Facility letter on file; 13-week headroom never below the buffer
| Re-phase the site hiring plan: retrofit installers to start with the second coordinator and the Q1-27 craft and general operative hires to follow CF-P01 and CF-P02 awards | Managing Director | 2026-10-15 | Open | Q1-27 utilisation forecast above 80%
| Bid plan for FY2027: two commercial awards by Q1-27, framework call-off for PS-P01 confirmed, win-probability review every two weeks | Managing Director | 2026-10-31 | Open | Secured work in hand of at least six months of revenue at every month end
| Increase the surety facility to EUR 1m and request bond reduction to 5% at practical completion on CF-2601 and PS-2601 | Finance Manager | 2026-11-30 | Open | Bond utilisation below 70% with the pipeline awarded
| SEAI claims lodged within five working days of BER publication; resolve the queried July claim | Retrofit Coordinator | 2026-09-30 | In progress | SEAI days below 60
| Collect the CF-2601 July short payment and the Rathgar snag retention; settle CF-2311 through mediation | Commercial Manager | 2026-10-31 | Open | Items off the aging; CF-2311 settled
| Monthly cost-to-complete review signed by the project manager and quantity surveyor for every live contract, with margin movement explained | Commercial Manager | 2026-09-30 | In progress | Signed cost reports on file before each close
| Downside contingency plan with triggers (retrofit starts, margin fade, SEAI days, cash headroom) and the levers on Cash_13W in order | BriQs CFO | 2026-10-15 | Open | Plan approved by the Managing Director and attached to the October pack
9. INFORMATION NEEDED BEFORE THE SEPTEMBER CLOSE
Signed September cost reports for CF-2601, CF-2602, CF-2603 and PS-2601, with cost to complete by package.
The client quantity surveyor position on V-CF2601-02 to -04 and on the July short payment, in writing.
The ROS deduction summary for September and the current deduction authorisation for every subcontractor paid in the month.
SEAI claim listing with BER publication and inspection dates, including the outcome of the queried July claim.
The overdraft facility letter and the surety facility terms, to confirm limits and renewal dates.
The FY2026 corporation tax computation from the tax adviser, to confirm the preliminary tax payment due on 23 November.
Prepared by BriQs Group for the directors of Tarnlea Build & Retrofit Ltd (fictional demonstration company). Model status at the time of preparation: OK.

## KPIs
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
KPI DASHBOARD
Live links into the statements and schedules. C = FY2026 (actual + forecast), D = FY2027. Monthly columns follow the Timeline.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
GROWTH AND MARGIN
Revenue | PL | 9197434.2432 | 9703425.5229 | 664034.2 | 566098.91 | 490939.1 | 453372.76 | 476711.55 | 646422.85 | 880782.99 | 949041.64 | 1074285.2096 | 1074569.1442 | 1008230.9892 | 912944.9002 | 822468.0859 | 673862.1744 | 581675.8012 | 676204.412 | 851315.566 | 969743.5884 | 1010443.7122 | 972765.6925 | 878268.8397 | 803854.7397 | 756126.7258 | 706696.1853
Growth vs same month prior year |  |  | 5.501% | 13: 23.86%; 14: 19.04%; 15: 18.48%; 16: 49.15%; 17: 78.58%; 18: 50.02%; 19: 14.72%; 20: 2.5%; 21: -18.25%; 22: -25.19%; 23: -25%; 24: -22.59%
Gross margin % | PL | 18.27% | 18.62% | 19.16% | 22.73% | 22.85% | 23.61% | 13.25% | 14.07% | 17.27% | 17.2% | 17.06% | 18.02% | 18.54% | 18.86% | 18.27% | 18.76% | 19.43% | 18.92% | 18.21% | 17.94% | 17.91% | 18.09% | 18.63% | 19.18% | 19.48% | 19.5%
Contribution % after site resources | PL | 16.42% | 15.92% | 15.72% | 15.59% | 12.89% | 13.44% | 7.149% | 10.96% | 17.24% | 19.2% | 17.29% | 18.31% | 19.5% | 19.24% | 16.51% | 12.92% | 10.14% | 12.2% | 15.99% | 17.87% | 18.48% | 18.16% | 17.33% | 16.61% | 15.89% | 14.36%
Overheads % of revenue | PL | 11.81% | 13.2% | 13.16% | 15.33% | 17.59% | 19.31% | 18.32% | 15.29% | 10.2% | 9.167% | 8.498% | 8.502% | 9.551% | 10.53% | 13.01% | 15.88% | 18.35% | 15.76% | 12.52% | 10.99% | 10.56% | 10.97% | 12.16% | 13.27% | 14.11% | 15.06%
EBITDA % | PL | 4.613% | 2.72% | 2.556% | 0.2583% | -4.706% | -5.872% | -11.17% | -4.333% | 7.038% | 10.03% | 8.793% | 9.806% | 9.947% | 8.711% | 3.499% | -2.954% | -8.205% | -3.569% | 3.462% | 6.878% | 7.921% | 7.186% | 5.17% | 3.336% | 1.788% | -0.6964%
EBITDA | PL | 424278.3155 | 263955.8684 | 16970.3758 | 1462.055 | -23103.8525 | -26620.5583 | -53248.4042 | -28006.4217 | 61987.5583 | 95183.0533 | 94463.8509 | 105374.1468 | 100290.6508 | 79525.8612 | 28781.9712 | -19906.0626 | -47726.459 | -24132.0137 | 29474.64 | 66696.32 | 80035.8182 | 69907.1183 | 45410.4106 | 26818.8299 | 13516.7008 | -4921.4056
ORDER BOOK
Secured work in hand | Pipeline | 2859805.7283 | 580729.5475 | 712548.03 | 1693908.01 | 1689957.66 | 2833344.6 | 3714487.05 | 3426439.2 | 3463790.21 | 5341427.57 | 4685945.1388 | 4025273.4391 | 3391635.8625 | 2859805.7283 | 2450143.3138 | 2280982.9948 | 2242096.2463 | 2153627.79 | 1975395.6124 | 1725366.2592 | 1430218.0961 | 1135015.6665 | 912352.6667 | 745008.0969 | 649338.991 | 580729.5475
Months of cover | Pipeline | 2.8639 | 0.76861 | 1.0731 | 2.754 | 2.9458 | 5.6276 | 7.8419 | 6.5203 | 5.1855 | 6.4712 | 4.8407 | 3.8981 | 3.2229 | 2.8639 | 2.6791 | 2.8403 | 3.2369 | 3.3446 | 2.8097 | 2.0727 | 1.5153 | 1.1531 | 0.95652 | 0.84185 | 0.79894 | 0.76861
Weighted pipeline | Pipeline | 3106562.5 | 820550.1549 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3106562.5 | 2972500 | 2810615.2344 | 2676328.125 | 2543738.0642 | 2352638.8889 | 2121153.0469 | 1878922.9861 | 1658800.0175 | 1488669.8451 | 1321628.5988 | 1091496.4012 | 820550.1549
Book-to-bill, trailing three months | Pipeline |  |  | 0.37014 | 1.3471 | 1.2114 | 2.2573 | 2.3551 | 2.0509 | 1.2705 | 1.5981 | 1.3977 | 1.1552 | 0.49972 | 0.49264 | 0.72881 | 0.65729 | 0.99497 | 0.82644 | 0.90823 | 0.64285 | 0.70891 | 0.72021 | 1.04 | 0.97495 | 0.91757 | 0.55894
SITE TEAM
Site headcount | Resources | 29 | 32 | 25 | 25 | 25 | 24 | 24 | 26 | 27 | 27 | 27 | 27 | 29 | 29 | 29 | 30 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Utilisation of productive hours | Resources | 85.63% | 80.55% | 77.91% | 64.84% | 61.31% | 62.21% | 74.46% | 81.83% | 100% | 100% | 100% | 100% | 100% | 95.26% | 84.36% | 69.93% | 61.62% | 67.84% | 82.31% | 92.29% | 95.83% | 93.03% | 86.43% | 81.4% | 77.88% | 72.84%
Labour recovery % | Resources | 100% | 95.57% | 92.12% | 77.06% | 70.66% | 72.04% | 86.21% | 95.58% | 111% | 124.5% | 110.3% | 111% | 116.9% | 113.4% | 100.4% | 83.2% | 73.75% | 80.36% | 97.5% | 109.3% | 113.5% | 110.2% | 102.4% | 96.42% | 92.24% | 86.27%
Agency labour cost | Resources | 97772.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 5400 | 6900 | 39447.9329 | 34520.218 | 8904.4859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WORKING CAPITAL, CASH AND BONDS
Trade receivable days | Receivables | 25.4849 | 19.7905 | 22.4395 | 23.8031 | 22.354 | 19.6434 | 17.4908 | 16.4484 | 26.0288 | 28.1026 | 25.4361 | 28.0312 | 27.1604 | 25.4849 | 23.0333 | 22.3989 | 21.4271 | 18.5836 | 19.3151 | 23.6669 | 25.0587 | 23.9379 | 22.0188 | 19.9908 | 17.6954 | 19.7905
SEAI grant days outstanding | Residential | 58.6563 | 60.0001 | 95.2153 | 71.7476 | 70.1522 | 67.3943 | 73.1655 | 78.1193 | 82.0375 | 60.4426 | 65.1401 | 71.3652 | 65.1221 | 58.6563 | 58.7943 | 58.5253 | 56.7163 | 55.5776 | 59.8359 | 65.7119 | 64.4936 | 62.7464 | 61.33 | 60.0134 | 59.0974 | 60.0001
Contract assets | BS | 705867.619 | 468288.9499 | 522647.8875 | 440404.2179 | 345645.3777 | 294471.5115 | 295297.3391 | 426028.5316 | 630048.7206 | 721625.1539 | 884433.0477 | 880707.5726 | 803811.5619 | 705867.619 | 629096.0062 | 488965.5452 | 388388.4998 | 468267.0098 | 622283.0983 | 720521.0981 | 751033.0005 | 712262.1669 | 616641.8154 | 541742.0859 | 502973.9472 | 468288.9499
Retentions receivable | BS | 186751.8001 | 176168.1174 | 116889.7435 | 136345.335 | 152728.1885 | 137761.1805 | 117960.5975 | 117103.181 | 132455.7665 | 154454.4872 | 176901.2311 | 207048.6532 | 209445.9303 | 186751.8001 | 201220.9813 | 223572.2227 | 192039.6179 | 152299.6764 | 138714.1932 | 158533.8981 | 182112.4426 | 206952.4779 | 230396.2121 | 227718.1961 | 238923.9874 | 176168.1174
Variations raised and undecided (claimed value) | WIP | 0 | 0 | 65300 | 84400 | 52600 | 48300 | 41400 | 129400 | 133500 | 168400 | 152200 | 76200 | 37600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Working capital tied up in contracts | BS | 970968.4202 | 565641.9869 | 720363.1368 | 668946.5088 | 544298.6316 | 440363.4459 | 313068.6114 | 294104.64 | 493587.5847 | 579507.722 | 751635.3333 | 992302.5044 | 1038275.0443 | 970968.4202 | 852189.2408 | 760364.5895 | 598923.9747 | 451092.3805 | 455616.8479 | 614447.2641 | 747860.5678 | 801905.6366 | 772390.2001 | 681269.5696 | 591124.1536 | 565641.9869
Cash at bank | BS | 632766.8777 | 1114521.6169 | 499752.2155 | 561106.3231 | 643340.8883 | 716245.6465 | 775741.1707 | 768659.8843 | 613881.9196 | 634504.3727 | 531875.8317 | 418470.3684 | 446648.1805 | 632766.8777 | 708530.0195 | 813835.8582 | 861509.0219 | 1004245.7449 | 980842.7312 | 894873.0139 | 832481.0993 | 863046.2299 | 912832.725 | 1048223.5762 | 1076823.2571 | 1114521.6169
Cash headroom over the minimum buffer |  | 432766.8777 | 914521.6169 | 299752.2155 | 361106.3231 | 443340.8883 | 516245.6465 | 575741.1707 | 568659.8843 | 413881.9196 | 434504.3727 | 331875.8317 | 218470.3684 | 246648.1805 | 432766.8777 | 508530.0195 | 613835.8582 | 661509.0219 | 804245.7449 | 780842.7312 | 694873.0139 | 632481.0993 | 663046.2299 | 712832.725 | 848223.5762 | 876823.2571 | 914521.6169
Net cash / (debt) | BS | 510691.8777 | 990871.6169 | 363652.2155 | 428906.3231 | 515040.8883 | 557195.6465 | 621313.0457 | 618853.6343 | 468697.5446 | 493941.8727 | 395935.2067 | 287151.6184 | 319951.3055 | 510691.8777 | 591076.8945 | 701004.6082 | 683099.6469 | 831920.7449 | 814602.1062 | 734716.7639 | 678409.2243 | 715058.7299 | 770929.6 | 912404.8262 | 947088.8821 | 990871.6169
Bond facility utilisation | Debt | 72.53% | 20.8% | 27.47% | 43.2% | 43.2% | 47.73% | 45.87% | 45.87% | 51.07% | 83.07% | 83.07% | 83.07% | 88.27% | 72.53% | 75.97% | 75.97% | 51.03% | 37.3% | 39.7% | 39.7% | 44.82% | 49.14% | 60.5% | 46.67% | 44.27% | 20.8%
Operating cash flow, trailing three months | CF |  |  | 85452.2155 | 150706.3231 | 243440.8883 | 239543.4309 | 238406.7227 | 146312.746 | -84198.1018 | -121171.1731 | -218618.4277 | -177245.9262 | -170390.5672 | 118356.671 | 319567.276 | 396737.3027 | 266133.7692 | 322569.8504 | 195323.498 | 55343.117 | -149785.5205 | -95817.3762 | 39938.8361 | 237721.6019 | 235756.1522 | 223668.0169

## PL
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
PROFIT AND LOSS
Monthly, actual Jan-26 to Aug-26 and forecast to Dec-27 for the selected scenario. Revenue positive, costs negative. Every line links to a schedule.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
REVENUE
Residential deep retrofit (SEAI One Stop Shop) | Residential / WIP | 2132818.9817 | 2905008.4202 | 138592.05 | 124444 | 142249.4 | 151103.95 | 137267.55 | 139448.5 | 185267 | 228950.4 | 239079.5646 | 229597.056 | 217521.4124 | 199298.0987 | 176098.7287 | 171231.5094 | 194339.8081 | 228831.7969 | 255647.4463 | 271417.8092 | 275528.386 | 271111.9223 | 271037.6059 | 274574.4916 | 268856.4657 | 246332.45
Residential renovation and extensions | Residential / WIP | 1982039.2699 | 2164837.1292 | 131409.36 | 114236.45 | 128758.65 | 145125.35 | 170056.66 | 189129.45 | 203261.87 | 194333.83 | 190402.7797 | 174017.342 | 175545.234 | 165762.2944 | 163015.4155 | 149877.12 | 145284.8234 | 153026.7244 | 170385.1309 | 189199.3336 | 200559.0651 | 203890.198 | 202917.2479 | 200483.1718 | 196781.4096 | 189417.4889
Commercial fit-out | Residential / WIP | 3290084.0536 | 2461146.1065 | 158017.94 | 139314.06 | 114056.91 | 103444.17 | 136039.43 | 218730.2 | 343193.12 | 346480.13 | 441839.7972 | 466575.4467 | 428352.9879 | 394039.8618 | 378959.3609 | 314292.3837 | 181694.5168 | 132590.0608 | 191099.1753 | 231485.842 | 242230.0608 | 220122.9686 | 170130.1724 | 130431.8714 | 133616.5725 | 134493.1214
Public sector retrofit (council) | Residential / WIP | 1792491.938 | 2172433.867 | 236014.85 | 188104.4 | 105874.14 | 53699.29 | 33347.91 | 99114.7 | 149061 | 179277.28 | 202963.0682 | 204379.2995 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 198365.2049 | 156872.2779 | 136453.125
NET REVENUE |  | 9197434.2432 | 9703425.5229 | 664034.2 | 566098.91 | 490939.1 | 453372.76 | 476711.55 | 646422.85 | 880782.99 | 949041.64 | 1074285.2096 | 1074569.1442 | 1008230.9892 | 912944.9002 | 822468.0859 | 673862.1744 | 581675.8012 | 676204.412 | 851315.566 | 969743.5884 | 1010443.7122 | 972765.6925 | 878268.8397 | 803854.7397 | 756126.7258 | 706696.1853
Growth vs prior month (memo) |  |  |  |  | -14.75% | -13.28% | -7.652% | 5.148% | 35.6% | 36.25% | 7.75% | 13.2% | 0.02643% | -6.173% | -9.451% | -9.91% | -18.07% | -13.68% | 16.25% | 25.9% | 13.91% | 4.197% | -3.729% | -9.714% | -8.473% | -5.937% | -6.537%
DIRECT COSTS (incl. own labour at standard rate and onerous contract provisions)
Residential deep retrofit (SEAI One Stop Shop) | Residential / WIP | -1651408.2607 | -2222331.4415 | -106634.62 | -97899.08 | -116131.69 | -112974.04 | -107981.48 | -110242.99 | -145716.33 | -176423.49 | -182895.8669 | -175641.7479 | -166403.8805 | -152463.0455 | -134715.5275 | -130992.1047 | -148669.9532 | -175056.3246 | -195570.2964 | -207634.624 | -210779.2153 | -207400.6206 | -207343.7685 | -210049.4861 | -205675.1963 | -188444.3242
Residential renovation and extensions | Residential / WIP | -1489057.4039 | -1645276.2182 | -98074.47 | -81754.09 | -93655.2 | -102798.83 | -132975.19 | -147901.24 | -152073.82 | -143471.55 | -144706.1125 | -132253.1799 | -133414.3778 | -125979.3437 | -123891.7158 | -113906.6112 | -110416.4658 | -116300.3105 | -129492.6995 | -143791.4936 | -152424.8895 | -154956.5505 | -154217.1084 | -152367.2106 | -149553.8713 | -143957.2916
Commercial fit-out | Residential / WIP | -2846148.5104 | -2120386.2276 | -126726.14 | -105238.29 | -84756.08 | -88882.17 | -143323.67 | -211431.66 | -298743.67 | -313658.41 | -387432.686 | -397071.6389 | -359754.9489 | -329129.1466 | -323212.277 | -269256.2134 | -156486.9792 | -114650.463 | -165219.9074 | -200114.1296 | -209381.1296 | -190263.578 | -147070.7688 | -112798.7026 | -115582.7203 | -116349.3588
Public sector retrofit (council) | Residential / WIP | -1530176.9142 | -1908961.4033 | -205399.87 | -152554.55 | -84207.19 | -41672.02 | -29255.21 | -85890.76 | -132110.44 | -152267.13 | -175973.0186 | -175973.0186 | -161704.936 | -133168.7709 | -90364.5231 | -33292.1927 | -53086.4198 | -142271.6049 | -205975.3086 | -244197.5309 | -256938.2716 | -244197.5309 | -205975.3086 | -174498.1674 | -138047.3573 | -120117.1875
TOTAL DIRECT COSTS |  | -7516791.0893 | -7896955.2905 | -536835.1 | -437446.01 | -378750.16 | -346327.06 | -413535.55 | -555466.65 | -728644.26 | -785820.58 | -891007.6841 | -880939.5853 | -821278.1432 | -740740.3066 | -672184.0434 | -547447.122 | -468659.8179 | -548278.7031 | -696258.2119 | -795737.7781 | -829523.506 | -796818.2799 | -714606.9544 | -649713.5667 | -608859.1451 | -568868.1622
GROSS PROFIT BY SEGMENT
Residential deep retrofit (SEAI One Stop Shop) | revenue + direct costs | 481410.7209 | 682676.9787 | 31957.43 | 26544.92 | 26117.71 | 38129.91 | 29286.07 | 29205.51 | 39550.67 | 52526.91 | 56183.6977 | 53955.3082 | 51117.5319 | 46835.0532 | 41383.2013 | 40239.4047 | 45669.8549 | 53775.4723 | 60077.1499 | 63783.1852 | 64749.1707 | 63711.3018 | 63693.8374 | 64525.0055 | 63181.2694 | 57888.1257
Residential renovation and extensions | revenue + direct costs | 492981.866 | 519560.911 | 33334.89 | 32482.36 | 35103.45 | 42326.52 | 37081.47 | 41228.21 | 51188.05 | 50862.28 | 45696.6671 | 41764.1621 | 42130.8561 | 39782.9506 | 39123.6997 | 35970.5088 | 34868.3576 | 36726.4139 | 40892.4314 | 45407.8401 | 48134.1756 | 48933.6475 | 48700.1395 | 48115.9612 | 47227.5383 | 45460.1973
Commercial fit-out | revenue + direct costs | 443935.5432 | 340759.8789 | 31291.8 | 34075.77 | 29300.83 | 14562 | -7284.24 | 7298.54 | 44449.45 | 32821.72 | 54407.1112 | 69503.8077 | 68598.039 | 64910.7153 | 55747.0839 | 45036.1703 | 25207.5376 | 17939.5978 | 25879.2679 | 31371.7124 | 32848.9311 | 29859.3907 | 23059.4036 | 17633.1688 | 18033.8523 | 18143.7625
Public sector retrofit (council) | revenue + direct costs | 262315.0238 | 263472.4637 | 30614.98 | 35549.85 | 21666.95 | 12027.27 | 4092.7 | 13223.94 | 16950.56 | 27010.15 | 26990.0495 | 28406.2809 | 25106.4189 | 20675.8744 | 14030.0576 | 5168.9686 | 7270.2332 | 19484.225 | 28208.5048 | 33443.0727 | 35187.9287 | 33443.0727 | 28208.5048 | 23867.0375 | 18824.9207 | 16335.9375
Gross margin %: residential deep retrofit (seai one stop shop) |  | 22.57% | 23.5% | 23.06% | 21.33% | 18.36% | 25.23% | 21.34% | 20.94% | 21.35% | 22.94% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5%
Gross margin %: residential renovation and extensions |  | 24.87% | 24% | 25.37% | 28.43% | 27.26% | 29.17% | 21.81% | 21.8% | 25.18% | 26.17% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24%
Gross margin %: commercial fit-out |  | 13.49% | 13.85% | 19.8% | 24.46% | 25.69% | 14.08% | -5.355% | 3.337% | 12.95% | 9.473% | 12.31% | 14.9% | 16.01% | 16.47% | 14.71% | 14.33% | 13.87% | 13.53% | 13.54% | 13.55% | 13.56% | 13.56% | 13.55% | 13.52% | 13.5% | 13.49%
Gross margin %: public sector retrofit (council) |  | 14.63% | 12.13% | 12.97% | 18.9% | 20.46% | 22.4% | 12.27% | 13.34% | 11.37% | 15.07% | 13.3% | 13.9% | 13.44% | 13.44% | 13.44% | 13.44% | 12.05% | 12.05% | 12.05% | 12.05% | 12.05% | 12.05% | 12.05% | 12.03% | 12% | 11.97%
GROSS PROFIT |  | 1680643.1539 | 1806470.2324 | 127199.1 | 128652.9 | 112188.94 | 107045.7 | 63176 | 90956.2 | 152138.73 | 163221.06 | 183277.5255 | 193629.5588 | 186952.846 | 172204.5935 | 150284.0425 | 126415.0524 | 113015.9833 | 127925.7089 | 155057.354 | 174005.8103 | 180920.2061 | 175947.4126 | 163661.8853 | 154141.173 | 147267.5807 | 137828.0231
Gross margin % |  | 18.27% | 18.62% | 19.16% | 22.73% | 22.85% | 23.61% | 13.25% | 14.07% | 17.27% | 17.2% | 17.06% | 18.02% | 18.54% | 18.86% | 18.27% | 18.76% | 19.43% | 18.92% | 18.21% | 17.94% | 17.91% | 18.09% | 18.63% | 19.18% | 19.48% | 19.5%
SITE RESOURCE COSTS NOT CHARGED TO JOBS
Labour recovery variance (+ over / - under-recovery) | Resources | 87.7116 | -80877.756 | -9212.5325 | -26691.4325 | -35199.9925 | -32046.9625 | -15810.925 | -5442.955 | 15012.195 | 32481.7475 | 17058.2421 | 17682.0546 | 24216.0714 | 18042.201 | 572.4294 | -24246.6143 | -38917.275 | -30369.8886 | -3870.88 | 14402.3437 | 20878.6461 | 15765.9397 | 3668.3593 | -5540.8424 | -11993.3793 | -21226.5947
Fleet running costs and small tools | Resources | -170254 | -181083.6 | -13626 | -13713 | -13725 | -14065 | -13284 | -14685 | -15315 | -13521 | -14580 | -14580 | -14580 | -14580 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3 | -15090.3
Total site resource costs |  | -170166.2884 | -261961.356 | -22838.5325 | -40404.4325 | -48924.9925 | -46111.9625 | -29094.925 | -20127.955 | -302.805 | 18960.7475 | 2478.2421 | 3102.0546 | 9636.0714 | 3462.201 | -14517.8706 | -39336.9143 | -54007.575 | -45460.1886 | -18961.18 | -687.9563 | 5788.3461 | 675.6397 | -11421.9407 | -20631.1424 | -27083.6793 | -36316.8947
CONTRIBUTION AFTER SITE RESOURCES |  | 1510476.8655 | 1544508.8764 | 104360.5675 | 88248.4675 | 63263.9475 | 60933.7375 | 34081.075 | 70828.245 | 151835.925 | 182181.8075 | 185755.7676 | 196731.6134 | 196588.9174 | 175666.7945 | 135766.1719 | 87078.1381 | 59008.4083 | 82465.5203 | 136096.174 | 173317.854 | 186708.5522 | 176623.0523 | 152239.9446 | 133510.0306 | 120183.9015 | 101511.1284
Contribution % |  | 16.42% | 15.92% | 15.72% | 15.59% | 12.89% | 13.44% | 7.149% | 10.96% | 17.24% | 19.2% | 17.29% | 18.31% | 19.5% | 19.24% | 16.51% | 12.92% | 10.14% | 12.2% | 15.99% | 17.87% | 18.48% | 18.16% | 17.33% | 16.61% | 15.89% | 14.36%
OVERHEADS
Office payroll (incl. employer PRSI and pension) | Overheads | -603137.55 | -782117.208 | -50724.525 | -50337.4125 | -45997.8 | -45626.9625 | -45389.8125 | -50964 | -50303.7 | -50614.0875 | -50801.25 | -50866.8 | -55755.6 | -55755.6 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434 | -65176.434
Rent: office and yard | Overheads | -86912 | -91908 | -6023 | -5858 | -8709 | -7347 | -7358 | -7044 | -8501 | -6472 | -7400 | -7400 | -7400 | -7400 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659 | -7659
Insurance (public, employer and contractors all risks) | Overheads | -113931 | -120474 | -10070 | -8856 | -8959 | -9674 | -9909 | -9772 | -9369 | -8522 | -9700 | -9700 | -9700 | -9700 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5 | -10039.5
IT, software and estimating tools | Overheads | -46834 | -48438 | -3706 | -4237 | -4035 | -4028 | -3676 | -4033 | -3989 | -3530 | -3900 | -3900 | -3900 | -3900 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5 | -4036.5
Marketing and lead generation (residential) | Overheads | -79676 | -84456 | -3684 | -5487 | -7730 | -8125 | -8707 | -6050 | -6484 | -6209 | -6800 | -6800 | -6800 | -6800 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038 | -7038
Professional fees (audit, legal, tax) | Overheads | -49640 | -52164 | -5000 | -4331 | -3264 | -4655 | -4063 | -3755 | -3675 | -4097 | -4200 | -4200 | -4200 | -4200 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347 | -4347
Training, health and safety, PPE | Overheads | -31928 | -34776 | -3015 | -2508 | -2777 | -2372 | -3007 | -2630 | -1867 | -2552 | -2800 | -2800 | -2800 | -2800 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898 | -2898
Office and administration | Overheads | -26868 | -27945 | -2372 | -2245 | -1938 | -2556 | -2479 | -2112 | -2318 | -1848 | -2250 | -2250 | -2250 | -2250 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75 | -2328.75
Motor (non-site vehicles) | Overheads | -20345 | -21735 | -1687 | -1848 | -1800 | -1716 | -1422 | -1619 | -1791 | -1462 | -1750 | -1750 | -1750 | -1750 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25 | -1811.25
Subscriptions and memberships | Overheads | -10283 | -10681.2 | -834 | -647 | -726 | -977 | -860 | -897 | -1040 | -862 | -860 | -860 | -860 | -860 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1 | -890.1
Bond commission | Overheads | -7144 | -5858.6 | -274.6667 | -432 | -432 | -477.3333 | -458.6667 | -458.6667 | -510.6667 | -830.6667 | -830.6667 | -830.6667 | -882.6667 | -725.3333 | -759.6667 | -759.6667 | -510.3333 | -373 | -397 | -397 | -448.2 | -491.4 | -605 | -466.6667 | -442.6667 | -208
Bad debts and specific provisions | Overheads | -9500 | 0 | 0 | 0 | 0 | 0 | 0 | -9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OVERHEADS |  | -1086198.55 | -1280553.008 | -87390.1917 | -86786.4125 | -86367.8 | -87554.2958 | -87329.4792 | -98834.6667 | -89848.3667 | -86998.7542 | -91291.9167 | -91357.4667 | -96298.2667 | -96140.9333 | -106984.2007 | -106984.2007 | -106734.8673 | -106597.534 | -106621.534 | -106621.534 | -106672.734 | -106715.934 | -106829.534 | -106691.2007 | -106667.2007 | -106432.534
Overheads % of revenue |  | 11.81% | 13.2% | 13.16% | 15.33% | 17.59% | 19.31% | 18.32% | 15.29% | 10.2% | 9.167% | 8.498% | 8.502% | 9.551% | 10.53% | 13.01% | 15.88% | 18.35% | 15.76% | 12.52% | 10.99% | 10.56% | 10.97% | 12.16% | 13.27% | 14.11% | 15.06%
EBITDA |  | 424278.3155 | 263955.8684 | 16970.3758 | 1462.055 | -23103.8525 | -26620.5583 | -53248.4042 | -28006.4217 | 61987.5583 | 95183.0533 | 94463.8509 | 105374.1468 | 100290.6508 | 79525.8612 | 28781.9712 | -19906.0626 | -47726.459 | -24132.0137 | 29474.64 | 66696.32 | 80035.8182 | 69907.1183 | 45410.4106 | 26818.8299 | 13516.7008 | -4921.4056
EBITDA % |  | 4.613% | 2.72% | 2.556% | 0.2583% | -4.706% | -5.872% | -11.17% | -4.333% | 7.038% | 10.03% | 8.793% | 9.806% | 9.947% | 8.711% | 3.499% | -2.954% | -8.205% | -3.569% | 3.462% | 6.878% | 7.921% | 7.186% | 5.17% | 3.336% | 1.788% | -0.6964%
BELOW EBITDA
Depreciation | Fixed_Assets | -139009.7222 | -153104.3611 | -10856.9444 | -10856.9444 | -11023.6111 | -11684.0278 | -11684.0278 | -11748.6111 | -11773.6111 | -11826.3889 | -11851.3889 | -11876.3889 | -11901.3889 | -11926.3889 | -12285.5972 | -12311.4722 | -13637.3472 | -13663.2222 | -13689.0972 | -13714.9722 | -13740.8472 | -13766.7222 | -11603.7083 | -11537.9167 | -11563.7917 | -11589.6667
EBIT |  | 285268.5933 | 110851.5073 | 6113.4314 | -9394.8894 | -34127.4636 | -38304.5861 | -64932.4319 | -39755.0328 | 50213.9472 | 83356.6644 | 82612.462 | 93497.7579 | 88389.2619 | 67599.4723 | 16496.374 | -32217.5348 | -61363.8062 | -37795.2359 | 15785.5428 | 52981.3478 | 66294.971 | 56140.3961 | 33806.7023 | 15280.9133 | 1952.9091 | -16511.0723
Hire purchase interest | Debt | -9657.6281 | -9999.2859 | -805 | -782.575 | -760.15 | -737.725 | -914.5375 | -887.9617 | -861.3859 | -834.8102 | -808.2344 | -781.6586 | -755.0828 | -728.507 | -701.9312 | -675.3555 | -648.7797 | -1025.8539 | -990.8687 | -955.8836 | -920.8984 | -885.9133 | -850.9281 | -815.943 | -780.9578 | -745.9727
PROFIT BEFORE TAX |  | 275610.9651 | 100852.2214 | 5308.4314 | -10177.4644 | -34887.6136 | -39042.3111 | -65846.9694 | -40642.9945 | 49352.5613 | 82521.8543 | 81804.2277 | 92716.0993 | 87634.1791 | 66870.9653 | 15794.4428 | -32892.8902 | -62012.5859 | -38821.0898 | 14794.6741 | 52025.4642 | 65374.0726 | 55254.4828 | 32955.7742 | 14464.9703 | 1171.9513 | -17257.0449
Profit before tax, financial year to date (memo) |  |  |  | 5308.4314 | -4869.0331 | -39756.6467 | -78798.9578 | -144645.9272 | -185288.9217 | -135936.3604 | -53414.5061 | 28389.7215 | 121105.8208 | 208739.9998 | 275610.9651 | 15794.4428 | -17098.4475 | -79111.0334 | -117932.1232 | -103137.4491 | -51111.9849 | 14262.0877 | 69516.5705 | 102472.3447 | 116937.315 | 118109.2663 | 100852.2214
Corporation tax on the year to date (12.5%, no tax on losses) |  |  |  | 663.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3548.7152 | 15138.2276 | 26092.5 | 34451.3706 | 1974.3053 | 0 | 0 | 0 | 0 | 0 | 1782.761 | 8689.5713 | 12809.0431 | 14617.1644 | 14763.6583 | 12606.5277
Corporation tax | cumulative method | -34451.3706 | -12606.5277 | -663.5539 | 663.5539 | 0 | 0 | 0 | 0 | 0 | 0 | -3548.7152 | -11589.5124 | -10954.2724 | -8358.8707 | -1974.3053 | 1974.3053 | 0 | 0 | 0 | 0 | -1782.761 | -6906.8104 | -4119.4718 | -1808.1213 | -146.4939 | 2157.1306
NET PROFIT |  | 241159.5945 | 88245.6937 | 4644.8775 | -9513.9105 | -34887.6136 | -39042.3111 | -65846.9694 | -40642.9945 | 49352.5613 | 82521.8543 | 78255.5125 | 81126.5869 | 76679.9067 | 58512.0946 | 13820.1374 | -30918.5849 | -62012.5859 | -38821.0898 | 14794.6741 | 52025.4642 | 63591.3116 | 48347.6725 | 28836.3024 | 12656.849 | 1025.4574 | -15099.9143
Net margin % |  | 2.622% | 0.9094% | 0.6995% | -1.681% | -7.106% | -8.612% | -13.81% | -6.287% | 5.603% | 8.695% | 7.284% | 7.55% | 7.605% | 6.409% | 1.68% | -4.588% | -10.66% | -5.741% | 1.738% | 5.365% | 6.293% | 4.97% | 3.283% | 1.575% | 0.1356% | -2.137%
Own site labour sits in direct costs at the standard rate; the difference to actual payroll and agency cost is the recovery variance. Corporation tax accrues on the cumulative profit of each year; losses are not carried forward in the model.

## BS
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
BALANCE SHEET
Every balance comes from a schedule. The check row must be zero in every month. Retentions are shown in current assets as they fall within the operating cycle (IAS 1.68).
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
ASSETS
Cash at bank | CF | 632766.8777 | 1114521.6169 | 499752.2155 | 561106.3231 | 643340.8883 | 716245.6465 | 775741.1707 | 768659.8843 | 613881.9196 | 634504.3727 | 531875.8317 | 418470.3684 | 446648.1805 | 632766.8777 | 708530.0195 | 813835.8582 | 861509.0219 | 1004245.7449 | 980842.7312 | 894873.0139 | 832481.0993 | 863046.2299 | 912832.725 | 1048223.5762 | 1076823.2571 | 1114521.6169
Trade receivables (homeowners, commercial clients, council) | Receivables | 900600.9838 | 528495.4982 | 469893.4905 | 489890.7264 | 456356.3813 | 377392.696 | 318466.0725 | 277981.8962 | 491050.8721 | 639439.1131 | 701003.0815 | 887154.5995 | 924958.1947 | 900600.9838 | 770940.4309 | 680482.4203 | 581583.0035 | 456245.626 | 454908.9139 | 585730.4241 | 699158.8842 | 736646.1494 | 698821.1604 | 616524.0607 | 504161.5211 | 528495.4982
SEAI grant claims receivable | Receivables | 180933.3291 | 205972.7586 | 240218.66 | 178192.3 | 153187.4 | 127253.19 | 121763.65 | 152013.29 | 155368 | 108387.05 | 116372 | 168942 | 189148 | 180933.3291 | 174210.1793 | 164503.538 | 146104.5851 | 127168.1549 | 133584.6022 | 161861.3395 | 186499.9806 | 202841.4403 | 210487.8986 | 209029.1868 | 202795.3064 | 205972.7586
Retentions receivable, net of provision | Retentions | 186751.8001 | 176168.1174 | 116889.7435 | 136345.335 | 152728.1885 | 137761.1805 | 117960.5975 | 117103.181 | 132455.7665 | 154454.4872 | 176901.2311 | 207048.6532 | 209445.9303 | 186751.8001 | 201220.9813 | 223572.2227 | 192039.6179 | 152299.6764 | 138714.1932 | 158533.8981 | 182112.4426 | 206952.4779 | 230396.2121 | 227718.1961 | 238923.9874 | 176168.1174
Contract assets (work done, not yet invoiced) | WIP + Residential | 705867.619 | 468288.9499 | 522647.8875 | 440404.2179 | 345645.3777 | 294471.5115 | 295297.3391 | 426028.5316 | 630048.7206 | 721625.1539 | 884433.0477 | 880707.5726 | 803811.5619 | 705867.619 | 629096.0062 | 488965.5452 | 388388.4998 | 468267.0098 | 622283.0983 | 720521.0981 | 751033.0005 | 712262.1669 | 616641.8154 | 541742.0859 | 502973.9472 | 468288.9499
Prepayments and other receivables | opening balance, no movement modelled | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000 | 46000
Fixed assets, net book value | Fixed_Assets | 216790.2778 | 168589.9167 | 287943.0556 | 277086.1111 | 272662.5 | 300378.4722 | 288694.4444 | 280045.8333 | 269472.2222 | 259545.8333 | 248894.4444 | 238218.0556 | 227516.6667 | 216790.2778 | 217746.6806 | 206677.2083 | 272281.8611 | 259860.6389 | 247413.5417 | 234940.5694 | 222441.7222 | 209917 | 199555.2917 | 189259.375 | 178937.5833 | 168589.9167
TOTAL ASSETS |  | 2869710.8874 | 2708036.8577 | 2183345.0526 | 2129025.0135 | 2069920.7357 | 1999502.6967 | 1963923.2743 | 2067832.6165 | 2338277.5011 | 2563956.0101 | 2705479.6364 | 2846541.2493 | 2847528.534 | 2869710.8874 | 2747744.2977 | 2624036.7926 | 2487906.5893 | 2514086.8508 | 2623747.0804 | 2802460.3432 | 2919727.1296 | 2977665.4645 | 2914735.1032 | 2878496.4807 | 2750615.6026 | 2708036.8577
LIABILITIES
Trade payables: subcontractors | Payables | 376097.7874 | 291880.8572 | 252395.4585 | 218548.6225 | 180318.2245 | 158742.0755 | 174451.557 | 229204.573 | 336942.863 | 405551.8435 | 424201.605 | 429265.408 | 401333.5686 | 376097.7874 | 330962.344 | 260768.7553 | 239722.8281 | 270480.3819 | 334893.1917 | 375050.676 | 394309.0256 | 380268.2905 | 337018.1402 | 309925.2349 | 277464.8638 | 291880.8572
Retentions held from subcontractors | WIP | 101607.3933 | 93286.5735 | 35307.1965 | 42257.5025 | 46736.3405 | 39731.0295 | 30987.578 | 38466.992 | 49491.122 | 61484.1515 | 76097.2132 | 90951.2487 | 104472.8606 | 101607.3933 | 108063.1318 | 115726.7185 | 94680.1896 | 80100.7156 | 76897.0374 | 88737.4215 | 101166.2214 | 112760.3417 | 122204.4195 | 118697.8358 | 123508.9798 | 93286.5735
Trade payables: materials suppliers | Payables | 371685.8943 | 292584.4996 | 218555.8369 | 214146.3441 | 210234.8021 | 179830.1234 | 189119.496 | 261846.9917 | 362464.743 | 400005.8374 | 413888.6837 | 425911.443 | 405840.4591 | 371685.8943 | 337796.2026 | 289695.1938 | 247050.9873 | 258982.313 | 316739.3031 | 371221.8903 | 398121.2782 | 394301.9865 | 365391.4289 | 333895.459 | 311848.6004 | 292584.4996
Trade payables: plant hire and site services | Payables | 87835.106 | 67015.9011 | 61614.4819 | 48915.2997 | 42861.8215 | 39095.4823 | 51569.1803 | 73416.6069 | 76893.3621 | 104898.6373 | 105265.0089 | 104026.6327 | 97039.2702 | 87835.106 | 80455.6701 | 66517.0081 | 56339.2317 | 63938.399 | 80572.7675 | 91868.4874 | 95710.7098 | 92001.3892 | 82829.6628 | 75622.1138 | 71493.7099 | 67015.9011
Trade payables: overhead, fleet and agency suppliers | Payables | 50106.3115 | 51425.8564 | 51160.6213 | 43646.2395 | 51745.4983 | 52506.7116 | 52841.7109 | 46566.5087 | 57268.9238 | 56433.5189 | 89007.3441 | 84158.4726 | 58994.1922 | 50106.3115 | 51867.1897 | 51867.1897 | 51667.723 | 51557.8564 | 51577.0564 | 51577.0564 | 51618.0164 | 51652.5764 | 51743.4564 | 51632.7897 | 51613.5897 | 51425.8564
RCT payable to Revenue | VAT_RCT | 13118.4399 | 9075.5791 | 6029.1855 | 8282.0656 | 7034.1048 | 6026.1105 | 5720.1426 | 6221.8105 | 7168.5491 | 9652.5023 | 13379.9469 | 13819.461 | 14015.2439 | 13118.4399 | 12290.9893 | 10829.4763 | 8550.8021 | 7833.4643 | 8811.575 | 10898.4016 | 12225.6445 | 12864.3401 | 12423.949 | 11026.5121 | 10130.6904 | 9075.5791
PAYE, USC, PRSI and pension payable | Overheads | 66114.6 | 76289.643 | 58044.9275 | 57708.035 | 57462.9125 | 55481.405 | 55407.7475 | 59364.725 | 62800.465 | 61120.43 | 61200.125 | 61428.2 | 66114.6 | 66114.6 | 71021.079 | 72714.546 | 74073.501 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643
VAT payable / (repayable) | VAT_RCT | 90920.6641 | 47491.9467 | 11889.957 | 23131.969 | 16575.7428 | 24543.1004 | 15908.2321 | 22020.5874 | 7038.7914 | 24951.0953 | 8809.2845 | 36632.7902 | 44187.2662 | 90920.6641 | 33609.433 | 73303.9595 | 22495.3413 | 48385.9085 | 7371.8552 | 19731.6662 | 17637.2674 | 39913.9413 | 25843.6541 | 52834.7997 | 21226.889 | 47491.9467
Contract liabilities (invoiced ahead of work, deposits) | WIP + Residential | 15852.8193 | 17089.6493 | 10253.0496 | 8372.0622 | 31722.0289 | 26609.7098 | 41449.5256 | 29520.5866 | 32274.7606 | 16024.0936 | 18614.1722 | 17237.1158 | 21408.2919 | 15852.8193 | 14133.8188 | 12584.2712 | 19730.772 | 27828.4208 | 33194.6037 | 33743.9641 | 30018.489 | 25812.0137 | 24769.7785 | 23970.5268 | 21800.8651 | 17089.6493
Onerous contract provisions | WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corporation tax: opening (memo) |  |  |  | 6000 | 6663.5539 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3548.7152 | 15138.2276 | -5907.5 | 2451.3706 | 4425.676 | 2451.3706 | 2451.3706 | 2451.3706 | 2451.3706 | 2451.3706 | 4234.1316 | 11140.942 | 12809.0431 | 14617.1644 | -19687.7124
Corporation tax: charge (memo) | PL | 34451.3706 | 12606.5277 | 663.5539 | -663.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 3548.7152 | 11589.5124 | 10954.2724 | 8358.8707 | 1974.3053 | -1974.3053 | 0 | 0 | 0 | 0 | 1782.761 | 6906.8104 | 4119.4718 | 1808.1213 | 146.4939 | -2157.1306
Corporation tax: paid (balance 23-Sep, preliminary 23-Nov) | small company rules on Assumptions | -38000 | -36902.7413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000 | 0 | -32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2451.3706 | 0 | -34451.3706 | 0
Corporation tax payable / (recoverable) | opening + charge + paid | 2451.3706 | -21844.843 | 6663.5539 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3548.7152 | 15138.2276 | -5907.5 | 2451.3706 | 4425.676 | 2451.3706 | 2451.3706 | 2451.3706 | 2451.3706 | 2451.3706 | 4234.1316 | 11140.942 | 12809.0431 | 14617.1644 | -19687.7124 | -21844.843
Hire purchase: current portion | Debt | 55462.5 | 73012.5 | 46800 | 46800 | 46800 | 46800 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5
Hire purchase: non-current portion | Debt | 66612.5 | 50637.5 | 89300 | 85400 | 81500 | 112250 | 98965.625 | 94343.75 | 89721.875 | 85100 | 80478.125 | 75856.25 | 71234.375 | 66612.5 | 61990.625 | 57368.75 | 122946.875 | 99312.5 | 93228.125 | 87143.75 | 81059.375 | 74975 | 68890.625 | 62806.25 | 56721.875 | 50637.5
TOTAL LIABILITIES |  | 1297865.3864 | 1047945.663 | 848014.2686 | 803208.14 | 778991.4759 | 747615.748 | 777883.295 | 922435.6318 | 1143527.955 | 1286684.6098 | 1349952.7236 | 1409887.7496 | 1334195.1277 | 1297865.3864 | 1162078.6593 | 1069289.7391 | 995172.1217 | 1060173.473 | 1155039.0285 | 1281726.8271 | 1335402.3019 | 1344992.9644 | 1253226.3006 | 1204330.8291 | 1075424.4936 | 1047945.663
EQUITY
Share capital | opening balance | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
Retained earnings: opening (memo) |  |  |  | 1230685.9 | 1235330.7775 | 1225816.8669 | 1190929.2533 | 1151886.9422 | 1086039.9728 | 1045396.9783 | 1094749.5396 | 1177271.3939 | 1255526.9063 | 1336653.4932 | 1413333.3999 | 1471845.4945 | 1485665.6319 | 1454747.047 | 1392734.4611 | 1353913.3713 | 1368708.0454 | 1420733.5096 | 1484324.8212 | 1532672.4937 | 1561508.7961 | 1574165.6451 | 1575191.1025
Net profit (memo) | PL | 241159.5945 | 88245.6937 | 4644.8775 | -9513.9105 | -34887.6136 | -39042.3111 | -65846.9694 | -40642.9945 | 49352.5613 | 82521.8543 | 78255.5125 | 81126.5869 | 76679.9067 | 58512.0946 | 13820.1374 | -30918.5849 | -62012.5859 | -38821.0898 | 14794.6741 | 52025.4642 | 63591.3116 | 48347.6725 | 28836.3024 | 12656.849 | 1025.4574 | -15099.9143
Dividends paid | input (none planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retained earnings |  | 1471845.4945 | 1560091.1882 | 1235330.7775 | 1225816.8669 | 1190929.2533 | 1151886.9422 | 1086039.9728 | 1045396.9783 | 1094749.5396 | 1177271.3939 | 1255526.9063 | 1336653.4932 | 1413333.3999 | 1471845.4945 | 1485665.6319 | 1454747.047 | 1392734.4611 | 1353913.3713 | 1368708.0454 | 1420733.5096 | 1484324.8212 | 1532672.4937 | 1561508.7961 | 1574165.6451 | 1575191.1025 | 1560091.1882
TOTAL EQUITY |  | 1571845.4945 | 1660091.1882 | 1335330.7775 | 1325816.8669 | 1290929.2533 | 1251886.9422 | 1186039.9728 | 1145396.9783 | 1194749.5396 | 1277271.3939 | 1355526.9063 | 1436653.4932 | 1513333.3999 | 1571845.4945 | 1585665.6319 | 1554747.047 | 1492734.4611 | 1453913.3713 | 1468708.0454 | 1520733.5096 | 1584324.8212 | 1632672.4937 | 1661508.7961 | 1674165.6451 | 1675191.1025 | 1660091.1882
TOTAL LIABILITIES AND EQUITY |  | 2869710.8809 | 2708036.8512 | 2183345.0461 | 2129025.007 | 2069920.7292 | 1999502.6902 | 1963923.2678 | 2067832.61 | 2338277.4946 | 2563956.0036 | 2705479.6299 | 2846541.2428 | 2847528.5275 | 2869710.8809 | 2747744.2912 | 2624036.7861 | 2487906.5828 | 2514086.8443 | 2623747.0739 | 2802460.3367 | 2919727.1231 | 2977665.458 | 2914735.0967 | 2878496.4742 | 2750615.5961 | 2708036.8512
CHECK: assets less liabilities and equity (must be zero) |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
MEMO
Working capital tied up in contracts (receivables + SEAI + retentions + contract assets - payables - contract liabilities) |  | 970968.4202 | 565641.9869 | 720363.1368 | 668946.5088 | 544298.6316 | 440363.4459 | 313068.6114 | 294104.64 | 493587.5847 | 579507.722 | 751635.3333 | 992302.5044 | 1038275.0443 | 970968.4202 | 852189.2408 | 760364.5895 | 598923.9747 | 451092.3805 | 455616.8479 | 614447.2641 | 747860.5678 | 801905.6366 | 772390.2001 | 681269.5696 | 591124.1536 | 565641.9869
Net cash / (debt): cash less hire purchase |  | 510691.8777 | 990871.6169 | 363652.2155 | 428906.3231 | 515040.8883 | 557195.6465 | 621313.0457 | 618853.6343 | 468697.5446 | 493941.8727 | 395935.2067 | 287151.6184 | 319951.3055 | 510691.8777 | 591076.8945 | 701004.6082 | 683099.6469 | 831920.7449 | 814602.1062 | 734716.7639 | 678409.2243 | 715058.7299 | 770929.6 | 912404.8262 | 947088.8821 | 990871.6169

## CF
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
CASH FLOW STATEMENT
Indirect method from the P&L and balance sheet movements, reconciled every month to a direct build of the cash lines in each schedule.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
OPERATING ACTIVITIES (indirect)
Net profit | PL | 241159.5945 | 88245.6937 | 4644.8775 | -9513.9105 | -34887.6136 | -39042.3111 | -65846.9694 | -40642.9945 | 49352.5613 | 82521.8543 | 78255.5125 | 81126.5869 | 76679.9067 | 58512.0946 | 13820.1374 | -30918.5849 | -62012.5859 | -38821.0898 | 14794.6741 | 52025.4642 | 63591.3116 | 48347.6725 | 28836.3024 | 12656.849 | 1025.4574 | -15099.9143
Add back: depreciation |  | 139009.7222 | 153104.3611 | 10856.9444 | 10856.9444 | 11023.6111 | 11684.0278 | 11684.0278 | 11748.6111 | 11773.6111 | 11826.3889 | 11851.3889 | 11876.3889 | 11901.3889 | 11926.3889 | 12285.5972 | 12311.4722 | 13637.3472 | 13663.2222 | 13689.0972 | 13714.9722 | 13740.8472 | 13766.7222 | 11603.7083 | 11537.9167 | 11563.7917 | 11589.6667
Add back: interest |  | 9657.6281 | 9999.2859 | 805 | 782.575 | 760.15 | 737.725 | 914.5375 | 887.9617 | 861.3859 | 834.8102 | 808.2344 | 781.6586 | 755.0828 | 728.507 | 701.9312 | 675.3555 | 648.7797 | 1025.8539 | 990.8687 | 955.8836 | 920.8984 | 885.9133 | 850.9281 | 815.943 | 780.9578 | 745.9727
Add back: corporation tax charge |  | 34451.3706 | 12606.5277 | 663.5539 | -663.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 3548.7152 | 11589.5124 | 10954.2724 | 8358.8707 | 1974.3053 | -1974.3053 | 0 | 0 | 0 | 0 | 1782.761 | 6906.8104 | 4119.4718 | 1808.1213 | 146.4939 | -2157.1306
EBITDA (check equals PL) |  | 424278.3155 | 263955.8684 | 16970.3758 | 1462.055 | -23103.8525 | -26620.5583 | -53248.4042 | -28006.4217 | 61987.5583 | 95183.0533 | 94463.8509 | 105374.1468 | 100290.6508 | 79525.8612 | 28781.9712 | -19906.0626 | -47726.459 | -24132.0137 | 29474.64 | 66696.32 | 80035.8182 | 69907.1183 | 45410.4106 | 26818.8299 | 13516.7008 | -4921.4056
(Increase) / decrease in trade receivables | BS movement | -423721.4238 | 372105.4856 | 6986.0695 | -19997.2358 | 33534.3451 | 78963.6853 | 58926.6234 | 40484.1763 | -213068.9759 | -148388.2409 | -61563.9685 | -186151.518 | -37803.5952 | 24357.211 | 129660.5529 | 90458.0107 | 98899.4168 | 125337.3775 | 1336.7121 | -130821.5103 | -113428.4601 | -37487.2652 | 37824.989 | 82297.0997 | 112362.5396 | -24333.977
(Increase) / decrease in SEAI grant receivable | BS movement | -2201.6591 | -25039.4295 | -61486.99 | 62026.36 | 25004.9 | 25934.21 | 5489.54 | -30249.64 | -3354.71 | 46980.95 | -7984.95 | -52570 | -20206 | 8214.6709 | 6723.1499 | 9706.6413 | 18398.9529 | 18936.4301 | -6416.4473 | -28276.7372 | -24638.6412 | -16341.4597 | -7646.4583 | 1458.7119 | 6233.8803 | -3177.4522
(Increase) / decrease in retentions receivable | BS movement | -88066.0286 | 10583.6826 | -18203.972 | -19455.5915 | -16382.8535 | 14967.008 | 19800.583 | 857.4165 | -15352.5855 | -21998.7207 | -22446.7439 | -30147.4221 | -2397.2771 | 22694.1302 | -14469.1812 | -22351.2413 | 31532.6047 | 39739.9415 | 13585.4832 | -19819.705 | -23578.5445 | -24840.0353 | -23443.7342 | 2678.016 | -11205.7913 | 62755.87
(Increase) / decrease in contract assets | BS movement | -192138.039 | 237578.6691 | -8918.3075 | 82243.6696 | 94758.8403 | 51173.8661 | -825.8275 | -130731.1926 | -204020.1889 | -91576.4333 | -162807.8938 | 3725.4751 | 76896.0107 | 97943.9429 | 76771.6127 | 140130.461 | 100577.0454 | -79878.5099 | -154016.0886 | -98237.9998 | -30511.9024 | 38770.8336 | 95620.3516 | 74899.7294 | 38768.1387 | 34684.9973
(Increase) / decrease in other receivables | BS movement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase / (decrease) in subcontractor payables | BS movement | 194097.7874 | -84216.9302 | 70395.4585 | -33846.836 | -38230.398 | -21576.149 | 15709.4815 | 54753.016 | 107738.29 | 68608.9805 | 18649.7615 | 5063.8029 | -27931.8394 | -25235.7812 | -45135.4434 | -70193.5887 | -21045.9273 | 30757.5538 | 64412.8098 | 40157.4843 | 19258.3496 | -14040.7351 | -43250.1503 | -27092.9053 | -32460.3711 | 14415.9934
Increase / (decrease) in subcontractor retentions | BS movement | 75190.0883 | -8320.8198 | 8889.8915 | 6950.306 | 4478.838 | -7005.311 | -8743.4515 | 7479.414 | 11024.13 | 11993.0295 | 14613.0617 | 14854.0355 | 13521.6119 | -2865.4673 | 6455.7384 | 7663.5867 | -21046.529 | -14579.474 | -3203.6782 | 11840.3841 | 12428.7998 | 11594.1203 | 9444.0779 | -3506.5837 | 4811.144 | -30222.4063
Increase / (decrease) in materials payables | BS movement | 223685.8943 | -79101.3947 | 70555.8369 | -4409.4928 | -3911.542 | -30404.6787 | 9289.3726 | 72727.4957 | 100617.7513 | 37541.0944 | 13882.8463 | 12022.7594 | -20070.9839 | -34154.5648 | -33889.6917 | -48101.0088 | -42644.2065 | 11931.3257 | 57756.9902 | 54482.5871 | 26899.3879 | -3819.2916 | -28910.5576 | -31495.9699 | -22046.8586 | -19264.1008
Increase / (decrease) in plant and site services payables | BS movement | 46835.106 | -20819.2048 | 20614.4819 | -12699.1822 | -6053.4782 | -3766.3392 | 12473.698 | 21847.4266 | 3476.7552 | 28005.2752 | 366.3716 | -1238.3761 | -6987.3625 | -9204.1642 | -7379.4359 | -13938.662 | -10177.7764 | 7599.1673 | 16634.3685 | 11295.72 | 3842.2223 | -3709.3206 | -9171.7264 | -7207.549 | -4128.4039 | -4477.8087
Increase / (decrease) in overhead payables | BS movement | 12106.3115 | 1319.5449 | 13160.6213 | -7514.3818 | 8099.2588 | 761.2133 | 334.9993 | -6275.2021 | 10702.4151 | -835.4049 | 32573.8252 | -4848.8715 | -25164.2804 | -8887.8808 | 1760.8782 | 0 | -199.4667 | -109.8667 | 19.2 | 0 | 40.96 | 34.56 | 90.88 | -110.6667 | -19.2 | -187.7333
Increase / (decrease) in RCT payable | BS movement | 7918.4399 | -4042.8609 | 829.1855 | 2252.8801 | -1247.9608 | -1007.9943 | -305.9678 | 501.6678 | 946.7386 | 2483.9532 | 3727.4447 | 439.514 | 195.7829 | -896.8039 | -827.4506 | -1461.513 | -2278.6742 | -717.3379 | 978.1107 | 2086.8266 | 1327.243 | 638.6956 | -440.3911 | -1397.437 | -895.8216 | -1055.1113
Increase / (decrease) in payroll taxes payable | BS movement | 4314.6 | 10175.043 | -3755.0725 | -336.8925 | -245.1225 | -1981.5075 | -73.6575 | 3956.9775 | 3435.74 | -1680.035 | 79.695 | 228.075 | 4686.4 | 0 | 4906.479 | 1693.467 | 1358.955 | 2216.142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase / (decrease) in VAT payable | BS movement | 44620.6641 | -43428.7174 | -34410.043 | 11242.012 | -6556.2262 | 7967.3576 | -8634.8683 | 6112.3553 | -14981.796 | 17912.304 | -16141.8108 | 27823.5057 | 7554.4761 | 46733.3979 | -57311.2311 | 39694.5264 | -50808.6182 | 25890.5673 | -41014.0533 | 12359.811 | -2094.3987 | 22276.6738 | -14070.2872 | 26991.1456 | -31607.9108 | 26265.0578
Increase / (decrease) in contract liabilities | BS movement | 10229.4493 | 1236.83 | 4629.6796 | -1880.9874 | 23349.9667 | -5112.3192 | 14839.8158 | -11928.939 | 2754.1741 | -16250.667 | 2590.0785 | -1377.0563 | 4171.176 | -5555.4726 | -1719.0005 | -1549.5476 | 7146.5008 | 8097.6488 | 5366.1829 | 549.3605 | -3725.4751 | -4206.4753 | -1042.2352 | -799.2518 | -2169.6617 | -4711.2157
Increase / (decrease) in onerous contract provisions | BS movement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash generated from operations |  | 337149.5058 | 631985.7665 | 86257.2155 | 66036.6825 | 93494.7152 | 82292.4832 | 65031.9368 | 1528.5503 | -148094.7038 | 27979.1382 | -89998.4316 | -106801.9297 | 66754.7698 | 192669.0792 | 94328.9481 | 111845.0692 | 61985.8184 | 151088.9519 | -15085.77 | -77687.4586 | -54144.6411 | 38777.4189 | 60415.1689 | 143533.1691 | 71158.3844 | 45770.7075
Interest paid | Debt | -9657.6281 | -9999.2859 | -805 | -782.575 | -760.15 | -737.725 | -914.5375 | -887.9617 | -861.3859 | -834.8102 | -808.2344 | -781.6586 | -755.0828 | -728.507 | -701.9312 | -675.3555 | -648.7797 | -1025.8539 | -990.8687 | -955.8836 | -920.8984 | -885.9133 | -850.9281 | -815.943 | -780.9578 | -745.9727
Corporation tax paid | BS | -38000 | -36902.7413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000 | 0 | -32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2451.3706 | 0 | -34451.3706 | 0
NET CASH FROM OPERATING ACTIVITIES |  | 289491.8777 | 585083.7392 | 85452.2155 | 65254.1076 | 92734.5652 | 81554.7582 | 64117.3993 | 640.5886 | -148956.0897 | 27144.328 | -96806.666 | -107583.5883 | 33999.687 | 191940.5722 | 93627.0168 | 111169.7137 | 61337.0387 | 150063.098 | -16076.6387 | -78643.3422 | -55065.5396 | 37891.5056 | 57112.8701 | 142717.2262 | 35926.0559 | 45024.7348
INVESTING ACTIVITIES
Capital expenditure | Fixed_Assets | -58800 | -104904 | -1800 | 0 | -6600 | -39400 | 0 | -3100 | -1200 | -1900 | -1200 | -1200 | -1200 | -1200 | -13242 | -1242 | -79242 | -1242 | -1242 | -1242 | -1242 | -1242 | -1242 | -1242 | -1242 | -1242
FINANCING ACTIVITIES
Hire purchase drawn | Debt | 34650 | 70200 | 0 | 0 | 0 | 34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hire purchase principal repaid | Debt | -52575 | -68625 | -3900 | -3900 | -3900 | -3900 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375
Dividends paid | BS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FROM FINANCING ACTIVITIES |  | -17925 | 1575 | -3900 | -3900 | -3900 | 30750 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | 65578.125 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375
CASH
NET CASH FLOW FOR THE MONTH |  | 212766.8777 | 481754.7392 | 79752.2155 | 61354.1076 | 82234.5652 | 72904.7582 | 59495.5243 | -7081.2864 | -154777.9647 | 20622.453 | -102628.541 | -113405.4633 | 28177.812 | 186118.6972 | 75763.1418 | 105305.8387 | 47673.1637 | 142736.723 | -23403.0137 | -85969.7172 | -62391.9146 | 30565.1306 | 49786.4951 | 135390.8512 | 28599.6809 | 37698.3598
Opening cash |  |  |  | 420000 | 499752.2155 | 561106.3231 | 643340.8883 | 716245.6465 | 775741.1707 | 768659.8843 | 613881.9196 | 634504.3727 | 531875.8317 | 418470.3684 | 446648.1805 | 632766.8777 | 708530.0195 | 813835.8582 | 861509.0219 | 1004245.7449 | 980842.7312 | 894873.0139 | 832481.0993 | 863046.2299 | 912832.725 | 1048223.5762 | 1076823.2571
CLOSING CASH (to balance sheet) |  | 632766.8777 | 1114521.6169 | 499752.2155 | 561106.3231 | 643340.8883 | 716245.6465 | 775741.1707 | 768659.8843 | 613881.9196 | 634504.3727 | 531875.8317 | 418470.3684 | 446648.1805 | 632766.8777 | 708530.0195 | 813835.8582 | 861509.0219 | 1004245.7449 | 980842.7312 | 894873.0139 | 832481.0993 | 863046.2299 | 912832.725 | 1048223.5762 | 1076823.2571 | 1114521.6169
Free cash flow (operating less capex) | memo | 230691.8777 | 480179.7392 | 83652.2155 | 65254.1076 | 86134.5652 | 42154.7582 | 64117.3993 | -2459.4114 | -150156.0897 | 25244.328 | -98006.666 | -108783.5883 | 32799.687 | 190740.5722 | 80385.0168 | 109927.7137 | -17904.9613 | 148821.098 | -17318.6387 | -79885.3422 | -56307.5396 | 36649.5056 | 55870.8701 | 141475.2262 | 34684.0559 | 43782.7348
DIRECT METHOD (built from the cash lines of each schedule)
Receipts: retrofit homeowners | schedule cash line | 1567482.4475 | 2174641.9231 | 106268.01 | 93670.97 | 96455.66 | 108853.19 | 102307.45 | 105686.06 | 125565.63 | 144622.44 | 185493.4482 | 175500.2502 | 167082.2753 | 155977.0638 | 140259.9019 | 129076.5308 | 136628.2565 | 159640.666 | 183001.3123 | 199147.8924 | 206761.1799 | 206604.0356 | 204611.962 | 206653.2229 | 206561.6194 | 195695.3434
Receipts: SEAI grants | schedule cash line | 807859.67 | 1046336.9886 | 14200.01 | 135355.36 | 72516.9 | 75030.21 | 58661.54 | 42614.36 | 41057.29 | 91094.95 | 64273.05 | 44114 | 72258 | 96684 | 92464 | 88469.3291 | 85740.8501 | 78762.6879 | 67341.8972 | 59826.2577 | 73758.3445 | 88102.9949 | 98396.9857 | 104444.4547 | 106043.444 | 102985.7428
Receipts: renovation homeowners | schedule cash line | 2268910.0554 | 2449224.9846 | 166567.19 | 124038.46 | 159820.04 | 151894.2 | 204243.51 | 214564.27 | 194818.62 | 235679 | 223121.1227 | 203646.7808 | 201300.9916 | 189215.8703 | 182659.2016 | 173258.3401 | 171456.9668 | 179587.2933 | 193943.8819 | 210069.0922 | 220725.6724 | 225562.7251 | 228299.1014 | 227470.2127 | 222803.3057 | 213389.1913
Receipts: commercial clients | schedule cash line | 3012018.731 | 3507935.7669 | 217597.9 | 205867.58 | 125893.45 | 159514.63 | 155797.28 | 137038.57 | 130050.73 | 247704.81 | 299690.0635 | 333679.0865 | 480332.0005 | 518852.6305 | 526062.7079 | 446573.6796 | 433060.7306 | 379338.5052 | 281751.3407 | 127718.3997 | 183838.2136 | 239803.9286 | 263315.8408 | 250913.9937 | 222297.6227 | 153260.8037
Receipts: Kildrum County Council | schedule cash line | 1747053.5283 | 2170292.6162 | 144766.1 | 163070.87 | 253854.78 | 178666.93 | 112812.06 | 68015.76 | 33354.11 | 89759.77 | 147462.086 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 57338.8203 | 181393.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 188446.9447
Receipts: legacy retentions | schedule cash line | 53912.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32347.5 | 21565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paid to subcontractors (net of RCT) | schedule cash line | -2875142.2355 | -3304428.4102 | -156921.7745 | -215557.5444 | -183076.8352 | -156841.7395 | -148878.3073 | -161935.2295 | -186576.0209 | -251225.9377 | -348240.2405 | -359679.4842 | -364775.131 | -341433.9906 | -319897.9115 | -281859.0733 | -222551.9584 | -203881.786 | -229339.0997 | -283652.9922 | -318197.181 | -334820.5288 | -323358.457 | -286987.3274 | -263671.7532 | -236210.3417
RCT paid to Revenue | schedule cash line | -102549.1226 | -131004.2847 | -5200 | -6029.1855 | -8282.0656 | -7034.1048 | -6026.1105 | -5720.1426 | -6221.8105 | -7168.5491 | -9652.5023 | -13379.9469 | -13819.461 | -14015.2439 | -13118.4399 | -12290.9893 | -10829.4763 | -8550.8021 | -7833.4643 | -8811.575 | -10898.4016 | -12225.6445 | -12864.3401 | -12423.949 | -11026.5121 | -10130.6904
Paid to materials suppliers | schedule cash line | -2188306.3664 | -2617562.463 | -98833.65 | -140309.29 | -130537.09 | -148213.23 | -128489.84 | -114926.95 | -137044.46 | -212489.96 | -266655.9417 | -264267.9967 | -278556.3731 | -267981.5849 | -246978.1502 | -224149.0247 | -195802.9186 | -165366.3408 | -164423.5575 | -198243.011 | -236434.9046 | -257676.3222 | -258911.5702 | -242724.2222 | -221240.3911 | -205612.0497
Paid for plant hire and site services | schedule cash line | -840686.9991 | -945184.255 | -39871.42 | -62356.57 | -48705.77 | -45209.91 | -38113.25 | -45633.35 | -84378.75 | -65188.43 | -104898.6373 | -105265.0089 | -104026.6327 | -97039.2702 | -87835.106 | -80455.6701 | -66517.0081 | -56339.2317 | -63938.399 | -80572.7675 | -91868.4874 | -95710.7098 | -92001.3892 | -82829.6628 | -75622.1138 | -71493.7099
Paid to overhead, fleet and agency suppliers | schedule cash line | -841975.1479 | -773430.9006 | -44200.79 | -64704.8 | -53584.95 | -63082.86 | -62637.05 | -69961.65 | -58478.97 | -66163.97 | -78685.3549 | -110046.9622 | -98907.0207 | -71520.7701 | -63073.1089 | -64833.9871 | -64784.1205 | -64557.1871 | -64452.1205 | -64471.3205 | -64481.5605 | -64531.1605 | -64588.4405 | -64651.6538 | -64536.1871 | -64470.0538
Net wages: site workforce | schedule cash line | -968217.96 | -1190715.75 | -76438.52 | -76055.48 | -78429.72 | -74930.68 | -74946.64 | -78774 | -85693.04 | -82317.88 | -82346 | -82346 | -87970 | -87970 | -91048.95 | -94234.68 | -96791.13 | -100960.11 | -100960.11 | -100960.11 | -100960.11 | -100960.11 | -100960.11 | -100960.11 | -100960.11 | -100960.11
Net salaries: office | schedule cash line | -394172.48 | -510660.72 | -33161.84 | -32908.76 | -30071.68 | -29829.24 | -29674.2 | -33318.4 | -32886.72 | -33089.64 | -33212 | -33212 | -36404 | -36404 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06 | -42555.06
PAYE, USC, PRSI and pension remitted | schedule cash line | -717933.5725 | -894240.87 | -61800 | -58044.9275 | -57708.035 | -57462.9125 | -55481.405 | -55407.7475 | -59364.725 | -62800.465 | -61120.43 | -61200.125 | -61428.2 | -66114.6 | -66114.6 | -71021.079 | -72714.546 | -74073.501 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643
VAT paid / (repaid) | schedule cash line | -177579.5423 | -325090.9393 | -46300 | 0 | -23131.969 | 0 | -24543.1004 | 0 | -22020.5874 | 0 | -24951.0953 | 0 | -36632.7902 | 0 | -90920.6641 | 0 | -73303.9595 | 0 | -48385.9085 | 0 | -19731.6662 | 0 | -39913.9413 | 0 | -52834.7997 | 0
Corporation tax paid | schedule cash line | -38000 | -36902.7413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000 | 0 | -32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2451.3706 | 0 | -34451.3706 | 0
Capex paid, incl. VAT | schedule cash line | -72324 | -129031.92 | -2214 | 0 | -8118 | -48462 | 0 | -3813 | -1476 | -2337 | -1476 | -1476 | -1476 | -1476 | -16287.66 | -1527.66 | -97467.66 | -1527.66 | -1527.66 | -1527.66 | -1527.66 | -1527.66 | -1527.66 | -1527.66 | -1527.66 | -1527.66
Hire purchase interest paid | schedule cash line | -9657.6281 | -9999.2859 | -805 | -782.575 | -760.15 | -737.725 | -914.5375 | -887.9617 | -861.3859 | -834.8102 | -808.2344 | -781.6586 | -755.0828 | -728.507 | -701.9312 | -675.3555 | -648.7797 | -1025.8539 | -990.8687 | -955.8836 | -920.8984 | -885.9133 | -850.9281 | -815.943 | -780.9578 | -745.9727
Hire purchase principal net of new agreements | schedule cash line | -17925 | 1575 | -3900 | -3900 | -3900 | 30750 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | 65578.125 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375
Dividends paid | schedule cash line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW, DIRECT METHOD |  | 212766.8777 | 481754.7392 | 79752.2155 | 61354.1076 | 82234.5652 | 72904.7582 | 59495.5243 | -7081.2864 | -154777.9647 | 20622.453 | -102628.541 | -113405.4633 | 28177.812 | 186118.6972 | 75763.1418 | 105305.8387 | 47673.1637 | 142736.723 | -23403.0137 | -85969.7172 | -62391.9146 | 30565.1306 | 49786.4951 | 135390.8512 | 28599.6809 | 37698.3598
CHECK: indirect less direct (must be zero) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BvA
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
BUDGET VS ACTUAL: YEAR TO DATE AND FULL-YEAR OUTLOOK (EUR)
YTD = actual months per the Timeline. Outlook = actual months plus the selected scenario forecast for the rest of FY2026. Variance = actual or outlook less budget; favourable is positive for revenue and profit lines.
Line | YTD actual | YTD budget | Variance | Variance % | FY26 outlook | FY26 budget | Variance | Variance % | Commentary
VOLUMES
Retrofit homes started | 22 | 28.35 | -6.35 | -22.4% | 35.4789 | 42 | -6.5211 | -15.53% | Coordinator vacancy Mar to May delayed surveys and grant applications; starts back to 4 in the last actual month.
Renovation jobs started | 11 | 12.14 | -1.14 | -9.39% | 16.4108 | 17.99 | -1.5792 | -8.778%
PROFIT AND LOSS
Revenue: residential deep retrofit (seai one stop shop) | 1247322.85 | 1647190 | -399867.15 | -24.28% | 2132818.9817 | 2525498 | -392679.0183 | -15.55%
Revenue: residential renovation and extensions | 1276311.62 | 1263625 | 12686.62 | 1.004% | 1982039.2699 | 2007754 | -25714.7301 | -1.281%
Revenue: commercial fit-out | 1559275.96 | 2059884 | -500608.04 | -24.3% | 3290084.0536 | 3649153 | -359068.9464 | -9.84% | CF-2602 and CF-2603 started two months after the budget dates; CF-2601 on programme.
Revenue: public sector retrofit (council) | 1044493.57 | 1395360 | -350866.43 | -25.15% | 1792491.938 | 1860000 | -67508.062 | -3.629% | PS-2601 started in May against a March budget start.
NET REVENUE | 5127404 | 6366059 | -1238655 | -19.46% | 9197434.2432 | 10042405 | -844970.7568 | -8.414% | Volume effect on gross profit EUR -214k, margin effect EUR -53k (bridge below).
Gross profit: residential deep retrofit (seai one stop shop) | 273319.13 | 403561.55 | -130242.42 | -32.27% | 481410.7209 | 618747.01 | -137336.2891 | -22.2%
Gross profit: residential renovation and extensions | 323607.23 | 322224.375 | 1382.855 | 0.4292% | 492981.866 | 511977.27 | -18995.404 | -3.71%
Gross profit: commercial fit-out | 186515.87 | 304862.832 | -118346.962 | -38.82% | 443935.5432 | 540074.644 | -96139.1008 | -17.8%
Gross profit: public sector retrofit (council) | 161136.4 | 181396.8 | -20260.4 | -11.17% | 262315.0238 | 241800 | 20515.0238 | 8.484%
GROSS PROFIT | 944578.63 | 1212045.557 | -267466.927 | -22.07% | 1680643.1539 | 1912598.924 | -231955.7701 | -12.13%
Gross margin %: residential deep retrofit (seai one stop shop) | 21.91% | 24.5% | -2.588% |  | 22.57% | 24.5% | -1.928%
Gross margin %: residential renovation and extensions | 25.35% | 25.5% | -0.1451% |  | 24.87% | 25.5% | -0.6275%
Gross margin %: commercial fit-out | 11.96% | 14.8% | -2.838% |  | 13.49% | 14.8% | -1.307% |  | CF-2601 cost at completion EUR 172k over tender (M&E subcontractor replaced, design changes).
Gross margin %: public sector retrofit (council) | 15.43% | 13% | 2.427% |  | 14.63% | 13% | 1.634%
Gross margin % | 18.42% | 19.04% | -0.617% |  | 18.27% | 19.05% | -0.7723%
Labour recovery variance | -76910.8575 | -24000 | -52910.8575 | -220.5% | 87.7116 | -36000 | 36087.7116 | 100.2% | Site team under-used Feb to Apr while named work ran down; fully used from July with agency support.
Fleet running costs and small tools | -111934 | -104000 | -7934 | -7.629% | -170254 | -156000 | -14254 | -9.137%
CONTRIBUTION AFTER SITE RESOURCES | 755733.7725 | 1084045.557 | -328311.7845 | -30.29% | 1510476.8655 | 1720598.924 | -210122.0585 | -12.21%
Office payroll | -389958.3 | -438960 | 49001.7 | 11.16% | -603137.55 | -658440 | 55302.45 | 8.399% | Retrofit coordinator vacancy March to May.
Rent: office and yard | -57312 | -59200 | 1888 | 3.189% | -86912 | -88800 | 1888 | 2.126%
Insurance (public, employer and contractors all risks) | -75131 | -76800 | 1669 | 2.173% | -113931 | -115200 | 1269 | 1.102%
IT, software and estimating tools | -31234 | -29600 | -1634 | -5.52% | -46834 | -44400 | -2434 | -5.482%
Marketing and lead generation (residential) | -52476 | -52000 | -476 | -0.9154% | -79676 | -78000 | -1676 | -2.149%
Professional fees (audit, legal, tax) | -32840 | -32000 | -840 | -2.625% | -49640 | -48000 | -1640 | -3.417%
Training, health and safety, PPE | -20728 | -20800 | 72 | 0.3462% | -31928 | -31200 | -728 | -2.333%
Office and administration | -17868 | -16800 | -1068 | -6.357% | -26868 | -25200 | -1668 | -6.619%
Motor (non-site vehicles) | -13345 | -13600 | 255 | 1.875% | -20345 | -20400 | 55 | 0.2696%
Subscriptions and memberships | -6843 | -6800 | -43 | -0.6324% | -10283 | -10200 | -83 | -0.8137%
Bond commission | -3874.6667 | -4160 | 285.3333 | 6.859% | -7144 | -6240 | -904 | -14.49%
Bad debts and specific provisions | -9500 | 0 | -9500 | 0% | -9500 | 0 | -9500 | 0% | Specific provision on the disputed CF-2311 legacy retention.
TOTAL OVERHEADS | -711109.9667 | -750720 | 39610.0333 | 5.276% | -1086198.55 | -1126080 | 39881.45 | 3.542%
EBITDA | 44623.8058 | 333325.557 | -288701.7512 | -86.61% | 424278.3155 | 594518.924 | -170240.6085 | -28.64% | EUR 289k behind budget YTD; EUR 170k on the full-year outlook.
EBITDA % | 0.8703% | 5.236% | -4.366% |  | 4.613% | 5.92% | -1.307%
NET PROFIT | -53414.5061 | 232470.0031 | -285884.5093 | -123% | 241159.5945 | 432917.9493 | -191758.3548 | -44.29%
BALANCES AT THE LAST ACTUAL MONTH (YTD columns) AND AT DEC-26 (FY columns)
Cash at bank | 634504.3727 | 560000 | 74504.3727 | 13.3% | 632766.8777 | 610000 | 22766.8777 | 3.732%
Trade receivables and SEAI grants | 747826.1631 | 740000 | 7826.1631 | 1.058% | 1081534.3129 | 720000 | 361534.3129 | 50.21%
Contract assets less contract liabilities | 705601.0603 | 490000 | 215601.0603 | 44% | 690014.7996 | 450000 | 240014.7996 | 53.34% | Certification lags progress on CF-2601 and PS-2601; valuations should be submitted with the cost report each month.
Retentions receivable | 154454.4872 | 185000 | -30545.5128 | -16.51% | 186751.8001 | 195000 | -8248.1999 | -4.23%
YTD GROSS PROFIT BRIDGE BY SEGMENT: VOLUME AND MARGIN EFFECTS
Segment | Actual revenue YTD | Budget revenue YTD | Actual margin | Budget margin | Volume effect | Margin effect | Total variance | Check vs P&L variance
Residential deep retrofit (SEAI One Stop Shop) | 1247322.85 | 1647190 | 21.91% | 24.5% | -97967.4517 | -32274.9683 | -130242.42 | 0
Residential renovation and extensions | 1276311.62 | 1263625 | 25.35% | 25.5% | 3235.0881 | -1852.2331 | 1382.855 | 0
Commercial fit-out | 1559275.96 | 2059884 | 11.96% | 14.8% | -74089.9899 | -44256.9721 | -118346.962 | 0
Public sector retrofit (council) | 1044493.57 | 1395360 | 15.43% | 13% | -45612.6359 | 25352.2359 | -20260.4 | 0
TOTAL | 5127404 | 6366059 |  |  | -214434.9895 | -53031.9375 | -267466.927 | 0
Volume effect = revenue variance x budget margin. Margin effect = actual revenue x (actual - budget margin). Together they equal the gross profit variance by segment.

## Scenarios
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
SCENARIO COMPARISON: BASE, DOWNSIDE (WORST) AND UPSIDE (BEST)
Columns C to E hold snapshot values written by running the full model under each scenario (run date in B5). Column F is live for the scenario selected on Assumptions and must equal its snapshot (check in G). Drivers below are live links to Assumptions.
Snapshot run date | 13-Sep-2026
Selected scenario (live) | Base
Metric | Unit | Base | Downside | Upside | Live (selected) | Check: live less snapshot
FY2026 revenue (outlook) | EUR | 9197434.2432 | 8568111.1722 | 9257328.1866 | 9197434.2432 | 0
FY2027 revenue | EUR | 9703425.5229 | 7971780.8255 | 10898085.6245 | 9703425.5229 | 0
FY2026 gross margin % | % | 18.27% | 16.44% | 19.02% | 18.27% | 0
FY2026 commercial fit-out gross margin % | % | 13.49% | 9.893% | 14.73% | 13.49% | 0
FY2026 EBITDA | EUR | 424278.3155 | 163434.0198 | 511888.1113 | 424278.3155 | 0
FY2026 EBITDA % | % | 4.613% | 1.907% | 5.53% | 4.613% | 0
FY2026 net profit | EUR | 241159.5945 | 12920.8358 | 317818.1659 | 241159.5945 | 0
FY2027 gross margin % | % | 18.62% | 15.33% | 19.51% | 18.62% | 0
FY2027 EBITDA | EUR | 263955.8684 | -181433.9905 | 735043.0992 | 263955.8684 | 0
FY2027 EBITDA % | % | 2.72% | -2.276% | 6.745% | 2.72% | 0
FY2027 net profit | EUR | 88245.6937 | -344537.6376 | 500447.0207 | 88245.6937 | 0
Cash at 31-Dec-26 | EUR | 632766.8777 | 40385.257 | 776221.4926 | 632766.8777 | 0
Cash at 31-Dec-27 | EUR | 1114521.6169 | 111554.2729 | 1633476.7296 | 1114521.6169 | 0
Lowest month-end cash, Sep-26 to Dec-27 | EUR | 418470.3684 | -26677.3565 | 543229.3388 | 418470.3684 | 0
Month of the lowest cash | month | 2026-10-31 | 2026-11-30 | 2026-10-31 | 2026-10-31 | 0
Headroom at the lowest point vs the cash buffer (negative = shortfall) | EUR | 218470.3684 | -226677.3565 | 343229.3388 | 218470.3684 | 0
Secured work in hand at 31-Dec-26 | EUR | 2859805.7283 | 3295961.3341 | 2873087.9372 | 2859805.7283 | 0
Weighted pipeline at 31-Dec-26 | EUR | 3106562.5 | 2022000 | 4081937.5 | 3106562.5 | 0
Working capital tied up in contracts at 31-Dec-26 | EUR | 970968.4202 | 1267652.027 | 915330.7096 | 970968.4202 | 0
Peak bond facility utilisation | % | 88.27% | 83.07% | 88.96% | 88.27% | 0
FY2027 site utilisation | % | 80.55% | 79.25% | 87.81% | 80.55% | 0
FY2027 labour recovery variance | EUR | -80877.756 | -96783.623 | 71610.2346 | -80877.756 | 0
Pending variations: expected final value | EUR | 109460 | 58940 | 143140 | 109460 | 0
Total of check column (must be zero) | [5 empty] | 0
KEY DRIVERS BY SCENARIO (live links to Assumptions)
Retrofit homes started: growth vs deseasonalised run-rate (annualised) | 0 | 20% | -10% | 35% | 20%
Renovation jobs started: growth vs run-rate (annualised) | 0 | 5% | -15% | 12% | 5%
Retrofit average contract value change (annualised) | 0 | 3% | 0% | 4% | 3%
Renovation average contract value change (annualised) | 0 | 3% | 0% | 4% | 3%
Retrofit gross margin on new and in-flight work | 0 | 23.5% | 20.5% | 24.5% | 23.5%
Renovation gross margin on new and in-flight work | 0 | 24% | 21% | 25.5% | 24%
Start delay: contracted and pipeline projects | months | 0 | 2 | 0 | 0
Completion delay: projects in progress | months | 0 | 1 | 0 | 0
Cost overrun on cost to complete, projects in progress | 0 | 0% | 5% | -1% | 0%
Cost overrun on tender budgets, projects not yet started | 0 | 0% | 4% | -1% | 0%
Pending variations: final agreed value as share of claimed | 0 | 65% | 35% | 85% | 65%
Commercial and council clients: extra payment days | days | 0 | 15 | 0 | 0
SEAI grant claims: days to payment | days | 60 | 90 | 45 | 60
Homeowners: days to payment | days | 10 | 20 | 7 | 10
Site hiring plan (1 = as planned, 0 = freeze) | flag | 1 | 0 | 1 | 1
Office hiring plan (1 = as planned, 0 = freeze) | flag | 1 | 0 | 1 | 1
Discretionary overheads factor (marketing, training, motor) | x | 1 | 0.9 | 1 | 1
Disputed retention CF-2311: share recovered | 0 | 75% | 50% | 90% | 75%
Disputed retention CF-2311: month of settlement | month | 2026-11-30 | 2027-02-28 | 2026-10-31 | 2026-11-30
Win probabilities by pipeline contract and scenario are on Project_Register. To refresh the snapshots: set Assumptions!C11 to 1, 2 and 3 in turn, recalculate, and paste column F as values into C, D and E.
Formulas:
Live (selected) = INDEX(Assumptions!M$95:AB95,MATCH([Live (selected), row above],BS!M9:AB9,0))

## Cash_13W
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
13-WEEK CASH FORECAST, DIRECT METHOD (EUR)
Weeks ending Friday 18-Sep-26 to Friday 11-Dec-26. Opening cash = Aug-26 ledger cash plus actual movements 1 to 11 Sep (column C, per bank). Each line phases its monthly model amount (columns D to G) into weeks with the timing rule in column B; closing cash at 11-Dec plus the remaining December flows reconciles to the monthly balance sheet.
Line | Timing rule | Actual 1-11 Sep | Sep-26 monthly model | Oct-26 monthly model | Nov-26 monthly model | Dec-26 monthly model | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | Total 13 weeks | Share of December inside the window | December flows after 11-Dec
Week ending (Friday) | [6 empty] | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11
Week starting (Saturday) | opening as at | 2026-09-11 |  |  |  |  | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05
Month of week end | [6 empty] | 2026-09-30 | 2026-09-30 | 2026-10-31 | 2026-10-31 | 2026-10-31 | 2026-10-31 | 2026-10-31 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 2026-12-31 | 2026-12-31
PHASING WEIGHTS BY RULE AND MONTH (helper rows)
Calendar days: share of Sep-26 falling in the week (after the opening date) | [6 empty] | 0.36842 | 0.36842 | 0.26316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Calendar days: share of Oct-26 falling in the week (after the opening date) | [6 empty] | 0 | 0 | 0.064516 | 0.22581 | 0.22581 | 0.22581 | 0.22581 | 0.032258 | 0 | 0 | 0 | 0 | 0 | 1
Calendar days: share of Nov-26 falling in the week (after the opening date) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.23333 | 0.23333 | 0.23333 | 0.1 | 0 | 1
Calendar days: share of Dec-26 falling in the week (after the opening date) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12903 | 0.22581 | 0.35484
1st of Sep-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st of Oct-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
1st of Nov-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
1st of Dec-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
15th of Sep-26 falls in the week (1/0), after the opening date only | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15th of Oct-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15th of Nov-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
15th of Dec-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23rd of Sep-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
23rd of Oct-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
23rd of Nov-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
23rd of Dec-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25th of Sep-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
25th of Oct-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
25th of Nov-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
25th of Dec-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
last day of Sep-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
last day of Oct-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
last day of Nov-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
last day of Dec-26 falls in the week (1/0), after the opening date only | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RECEIPTS
Retrofit homeowners | calendar days | 68014 | 185493.4482 | 175500.2502 | 167082.2753 | 155977.0638 | 43281.902 | 43281.902 | 42238.2411 | 39629.0888 | 39629.0888 | 39629.0888 | 39629.0888 | 39077.7535 | 38985.8642 | 38985.8642 | 38985.8642 | 36834.3003 | 35220.6273 | 515408.6738 | 0.35484 | 100630.3637
SEAI grant payments | calendar days | 23567 | 64273.05 | 44114 | 72258 | 96684 | 14996.9658 | 14996.9658 | 13558.1829 | 9961.2258 | 9961.2258 | 9961.2258 | 9961.2258 | 15874.6323 | 16860.2 | 16860.2 | 16860.2 | 19701.1548 | 21831.871 | 191385.2758 | 0.35484 | 62376.7742
Renovation homeowners | calendar days | 81811 | 223121.1227 | 203646.7808 | 201300.9916 | 189215.8703 | 52061.6242 | 52061.6242 | 50325.3764 | 45984.757 | 45984.757 | 45984.757 | 45984.757 | 46829.4493 | 46970.2314 | 46970.2314 | 46970.2314 | 44545.0502 | 42726.1643 | 613399.0104 | 0.35484 | 122074.755
Commercial clients (payment claims fall due at month end) | month end | 0 | 299690.0635 | 333679.0865 | 480332.0005 | 518852.6305 | 0 | 0 | 299690.0635 | 0 | 0 | 0 | 0 | 333679.0865 | 0 | 0 | 0 | 480332.0005 | 0 | 1113701.1505 | 0 | 518852.6305
Kildrum County Council (payment run on the 25th) | 25th (payment run) | 0 | 147462.086 | 165931.4768 | 196229.6111 | 193129.9743 | 0 | 147462.086 | 0 | 0 | 0 | 0 | 165931.4768 | 0 | 0 | 0 | 196229.6111 | 0 | 0 | 509623.1739 | 0 | 193129.9743
Legacy retention settlements | 15th of month | 0 | 0 | 0 | 32347.5 | 21565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32347.5 | 0 | 0 | 0 | 32347.5 | 0 | 21565
TOTAL RECEIPTS | n/a | 173392 | 920039.7704 | 922871.5943 | 1149550.3785 | 1175424.5389 | 110340.4919 | 257802.5779 | 405811.8639 | 95575.0715 | 95575.0715 | 95575.0715 | 261506.5483 | 435460.9215 | 102816.2956 | 135163.7956 | 299045.9068 | 581412.5058 | 99778.6625 | 2975864.7844
PAYMENTS
Subcontractors, net of RCT (payment run on the 25th) | 25th (payment run) | 0 | -348240.2405 | -359679.4842 | -364775.131 | -341433.9906 | 0 | -348240.2405 | 0 | 0 | 0 | 0 | -359679.4842 | 0 | 0 | 0 | -364775.131 | 0 | 0 | -1072694.8558 | 0 | -341433.9906
Materials suppliers (month-end account settlement) | month end | 0 | -266655.9417 | -264267.9967 | -278556.3731 | -267981.5849 | 0 | 0 | -266655.9417 | 0 | 0 | 0 | 0 | -264267.9967 | 0 | 0 | 0 | -278556.3731 | 0 | -809480.3116 | 0 | -267981.5849
Plant hire and site services | calendar days | -38463 | -104898.6373 | -105265.0089 | -104026.6327 | -97039.2702 | -24476.2874 | -24476.2874 | -24274.3533 | -23769.5181 | -23769.5181 | -23769.5181 | -23769.5181 | -24200.972 | -24272.881 | -24272.881 | -24272.881 | -22923.8594 | -21912.0933 | -310160.5683 | 0.35484 | -62605.9808
Overhead, fleet and agency suppliers | calendar days | -28851 | -78685.3549 | -110046.9622 | -98907.0207 | -71520.7701 | -18360.0255 | -18360.0255 | -20214.1079 | -24849.3141 | -24849.3141 | -24849.3141 | -24849.3141 | -23331.3061 | -23078.3048 | -23078.3048 | -23078.3048 | -19119.1885 | -16149.8513 | -284166.6756 | 0.35484 | -46142.4323
Site wages (weekly) | calendar days | -30194 | -82346 | -82346 | -87970 | -87970 | -19213.8947 | -19213.8947 | -19036.8557 | -18594.2581 | -18594.2581 | -18594.2581 | -18594.2581 | -20250.3226 | -20526.3333 | -20526.3333 | -20526.3333 | -20147.9677 | -19864.1935 | -253683.1613 | 0.35484 | -56754.8387
Office salaries (25th) | 25th (payment run) | 0 | -33212 | -33212 | -36404 | -36404 | 0 | -33212 | 0 | 0 | 0 | 0 | -33212 | 0 | 0 | 0 | -36404 | 0 | 0 | -102828 | 0 | -36404
PAYE, USC, PRSI and pension (23rd) | 23rd (ROS) | 0 | -61120.43 | -61200.125 | -61428.2 | -66114.6 | 0 | -61120.43 | 0 | 0 | 0 | -61200.125 | 0 | 0 | 0 | 0 | -61428.2 | 0 | 0 | -183748.755 | 0 | -66114.6
RCT deducted from subcontractors (23rd) | 23rd (ROS) | 0 | -9652.5023 | -13379.9469 | -13819.461 | -14015.2439 | 0 | -9652.5023 | 0 | 0 | 0 | -13379.9469 | 0 | 0 | 0 | 0 | -13819.461 | 0 | 0 | -36851.9102 | 0 | -14015.2439
VAT, bi-monthly return (23rd) | 23rd (ROS) | 0 | -24951.0953 | 0 | -36632.7902 | 0 | 0 | -24951.0953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36632.7902 | 0 | 0 | -61583.8855 | 0 | 0
Corporation tax: FY2025 balance 23-Sep, FY2026 preliminary 23-Nov | 23rd (ROS) | 0 | -6000 | 0 | -32000 | 0 | 0 | -6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32000 | 0 | 0 | -38000 | 0 | 0
Hire purchase instalments (1st) | 1st of month | -5430.1094 | -5430.1094 | -5403.5336 | -5376.9578 | -5350.382 | 0 | 0 | -5403.5336 | 0 | 0 | 0 | 0 | -5376.9578 | 0 | 0 | 0 | -5350.382 | 0 | -16130.8734 | 1 | 0
Capex incl. VAT | calendar days | -541 | -1476 | -1476 | -1476 | -1476 | -344.4737 | -344.4737 | -341.2784 | -333.2903 | -333.2903 | -333.2903 | -333.2903 | -342.8129 | -344.4 | -344.4 | -344.4 | -338.0516 | -333.2903 | -4410.7419 | 0.35484 | -952.2581
TOTAL PAYMENTS | n/a | -103479.1094 | -1022668.3114 | -1036277.0576 | -1121372.5665 | -989305.8417 | -62394.6813 | -545570.9494 | -335926.0707 | -67546.3806 | -67546.3806 | -142126.4525 | -460437.8648 | -337770.3682 | -68221.9191 | -68221.9191 | -613281.5013 | -346435.8225 | -58259.4285 | -3173739.7386
CASH
NET CASH FLOW FOR THE WEEK | n/a | 69912.8906 | -102628.541 | -113405.4633 | 28177.812 | 186118.6972 | 47945.8106 | -287768.3715 | 69885.7931 | 28028.6909 | 28028.6909 | -46551.381 | -198931.3165 | 97690.5534 | 34594.3765 | 66941.8765 | -314235.5945 | 234976.6833 | 41519.2341 | -197874.9542
Opening cash | ledger + actual to date | 704417.2633 |  |  |  |  | 704417.2633 | 752363.0739 | 464594.7024 | 534480.4955 | 562509.1864 | 590537.8774 | 543986.4964 | 345055.1799 | 442745.7333 | 477340.1098 | 544281.9863 | 230046.3917 | 465023.075
CLOSING CASH | [6 empty] | 752363.0739 | 464594.7024 | 534480.4955 | 562509.1864 | 590537.8774 | 543986.4964 | 345055.1799 | 442745.7333 | 477340.1098 | 544281.9863 | 230046.3917 | 465023.075 | 506542.3091
CASH CONTROL
Minimum cash buffer (board policy) | [6 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
HEADROOM / (SHORTFALL) VS BUFFER | [6 empty] | 552363.0739 | 264594.7024 | 334480.4955 | 362509.1864 | 390537.8774 | 343986.4964 | 145055.1799 | 242745.7333 | 277340.1098 | 344281.9863 | 30046.3917 | 265023.075 | 306542.3091
Status | bar: 2026-09-30 to 2026-12-31
Low point in the 13 weeks |  | 230046.3917
Week ending of the low point |  | 2026-11-27
Headroom at the low point (negative = action needed) |  | 30046.3917
Undrawn overdraft facility |  | 250000
Facility headroom after covering any shortfall |  | 250000
Tax paid in the weeks containing the 23rd (PAYE, RCT, VAT, corporation tax) |  | 320184.5507
RECONCILIATION TO THE MONTHLY MODEL
Closing cash at the end of week 13 (11-Dec-26) |  | 506542.3091
Add: December flows after 11-Dec (column W, by line) |  | 126224.5686
Implied cash at 31-Dec-26 |  | 632766.8777
Cash at 31-Dec-26 per the monthly balance sheet |  | 632766.8777
CHECK: difference (must be zero) |  | 0
LEVERS IF THE LOW POINT BREACHES THE BUFFER, IN ORDER
1. Draw the overdraft facility (EUR 250k undrawn) across the weeks containing the 23rd, when PAYE, RCT, VAT and corporation tax fall due together.
2. Agree the pending variations on CF-2601 (EUR 118k claimed) before the October valuation, so they are certified in October and paid in November.
3. Collect the CF-2601 July short payment and the renovation snag retention: together EUR 58k already overdue.
4. Chase SEAI on the queried claim and lodge completion claims the week the post-works BER publishes; SEAI days are the largest controllable receivable lever.
5. Defer the planned November retrofit hires by one month and move discretionary marketing spend into Q1 if the low point sits below the buffer.

## Project_Profitability
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
PROJECT AND PROGRAMME PROFITABILITY WITH COST ALLOCATION (FY2026 OUTLOOK)
Gross profit by contract and programme, then full cost allocation: labour recovery variance and fleet costs by share of own labour charged; overheads absorbed by share of revenue. The allocated net contributions add up to FY2026 EBITDA (check below).
Contract or programme | Segment | Status | Revenue YTD | Gross profit YTD | Margin YTD | Revenue FY2026 | Direct costs FY2026 | Gross profit FY2026 | Margin FY2026 | Own labour charged FY2026 | Share of labour recovery variance | Share of fleet costs | Overhead absorption | Net contribution FY2026 | Net margin | Tender margin | Forecast final margin | Margin movement vs tender | Pending variations (claimed) | Contract position at last actual (+ asset / - liability) | Receivable at last actual | Retention held at last actual | Cash collected less cost to date (ex VAT)
CF-2501 | CF | Completed | 363553.44 | 81199.46 | 22.33% | 363553.44 | -282353.98 | 81199.46 | 22.33% | 46241.49 | 2.5681 | -4984.7987 | -42934.9326 | 33282.2968 | 9.155% | 14.08% | 18.46% | 4.382% | 0 | 0 | 0.00143 | 26092.5 | 166607.4987
PS-2502 | PS | Completed | 583692.68 | 99859.05 | 17.11% | 583692.68 | -483833.63 | 99859.05 | 17.11% | 62064.74 | 3.4468 | -6690.5334 | -68932.9356 | 24239.0278 | 4.153% | 12.22% | 15.15% | 2.927% | 0 | 0 | 0.0035 | 27725 | 140274.9865
CF-2601 | CF | In progress | 909074.82 | 58603.88 | 6.447% | 1289700 | -1190000 | 99700 | 7.73% | 190556.2896 | 10.5828 | -20541.828 | -152310.9851 | -73142.2304 | -5.671% | 13.73% | 7.73% | -5.998% | 118000 | 202464.01 | 234156.1059 | 35330.5405 | -385495.6096
CF-2602 | CF | In progress | 247330.09 | 40283.05 | 16.29% | 855363.1136 | -713911.7179 | 141451.3957 | 16.54% | 115625.2485 | 6.4214 | -12464.3169 | -101016.6693 | 27976.8309 | 3.271% | 13.62% | 16.54% | 2.92% | 19500 | 126492.45 | 115446.5098 | 3625.1292 | -191549.5158
CF-2603 | CF | In progress | 39317.61 | 6429.48 | 16.35% | 400530 | -333000 | 67530 | 16.86% | 53553.1692 | 2.9741 | -5772.9923 | -47301.7902 | 14458.1916 | 3.61% | 15.64% | 16.86% | 1.219% | 16200 | 39317.61 | 0 | 0 | -32888.13
PS-2601 | PS | In progress | 460800.89 | 61277.35 | 13.3% | 1208799.258 | -1046343.2842 | 162455.9738 | 13.44% | 135866.0467 | 7.5455 | -14646.26 | -142756.7696 | 5060.4896 | 0.4186% | 12.27% | 13.44% | 1.167% | 14700 | 177174.54 | 147462.0825 | 14181.3175 | -277540.59
CF-2604 | CF | Contracted | 0 | 0 | 0% | 320000 | -274500 | 45500 | 14.22% | 43920 | 2.4391 | -4734.5437 | -37791.3586 | 2976.5368 | 0.9302% | 14.22% | 14.22% | 0% | 0 | 0 | 0 | 0 | 0
PS-2602 | PS | Contracted | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 12.05% | 12.05% | 0% | 0 | 0 | 0 | 0 | 0
CF-P01 | CF | Pipeline | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 13.51% | 13.51% | 0% | 0 | 0 | 0 | 0 | 0
CF-P02 | CF | Pipeline | 0 | 0 | 0% | 60937.5 | -52382.8125 | 8554.6875 | 14.04% | 8381.25 | 0.46546 | -903.4926 | -7196.5966 | 455.0638 | 0.7468% | 14.04% | 14.04% | 0% | 0 | 0 | 0 | 0 | 0
CF-P03 | CF | Pipeline | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 13.59% | 13.59% | 0% | 0 | 0 | 0 | 0 | 0
PS-P01 | PS | Pipeline | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 11.97% | 11.97% | 0% | 0 | 0 | 0 | 0 | 0
CF-P04 | CF | Pipeline | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 13.61% | 13.61% | 0% | 0 | 0 | 0 | 0 | 0
CF-P05 | CF | Pipeline | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 13.54% | 13.54% | 0% | 0 | 0 | 0 | 0 | 0
CF-P06 | CF | Pipeline | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 13.43% | 13.43% | 0% | 0 | 0 | 0 | 0 | 0
Deep retrofit programme (SEAI One Stop Shop) | RR | Programme | 1247322.85 | 273319.13 | 21.91% | 2132818.9817 | -1651408.2607 | 481410.7209 | 22.57% | 522239.093 | 29.0031 | -56296.9906 | -251881.647 | 173261.0865 | 8.124% | n/a | 23.5% | n/a | 0 | 176176.5439 | 173671.6 | 0 | n/a
Renovation and extensions programme | RX | Programme | 1276311.62 | 323607.23 | 25.35% | 1982039.2699 | -1489057.4039 | 492981.866 | 24.87% | 400914.0838 | 22.2652 | -43218.2437 | -234074.8652 | 215711.0222 | 10.88% | n/a | 24% | n/a | 0 | -16024.0936 | 77089.86 | 0 | n/a
TOTAL |  |  | 5127404 | 944578.63 | 18.42% | 9197434.2432 | -7516791.0893 | 1680643.1539 | 18.27% | 1579361.4108 | 87.7116 | -170254 | -1086198.55 | 424278.3155 | 4.613% |  |  |  | 168400 | 705601.0603 | 747826.1631 | 106954.4872
FY2026 EBITDA per the P&L | [13 empty] | 424278.3155
Check: allocated net contributions less EBITDA (must be zero) | [13 empty] | 0
Pipeline contracts are probability-weighted. Forecast final margin = (contract revenue at the end of the horizon - forecast cost at completion) / contract revenue; for programmes, the scenario gross margin. Cash collected less cost to date is a funding indicator, not a cash balance: cost incurred is not all paid.

## WIP
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
WORK IN PROGRESS: NAMED CONTRACTS (PERCENTAGE OF COMPLETION, COST TO COMPLETE, VALUATIONS, RETENTIONS, CASH)
Revenue over time on the cost-to-cost input method (IFRS 15.B18): % complete = cost to date / estimated cost at completion. Actual months from the ledger and certificates; forecast months spread the remaining cost on an S-curve to the effective completion date. Expected losses are provided in full (IAS 37 onerous contracts).
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
CF-2501 Office fit-out, 1,850 m2, Dublin 2 ¦ Northwall Analytics Ltd ¦ segment CF ¦ Completed
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0.75 | 0.875 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0.84375 | 0.95703 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0.68359 | 0.84375 | 0.95703 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 46241.49 | 0 | 20871.48 | 17684.27 | 7685.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 139442.55 | 0 | 61951.26 | 52022.57 | 25468.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 68644.3 | 0 | 31369.52 | 25055.71 | 12219.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 8504.12 | 0 | 3705.32 | 3404.59 | 1394.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 19521.52 | 0 | 8828.56 | 7071.15 | 3621.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 282353.98 | 0 | 126726.14 | 105238.29 | 50389.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 851000 | 851000 | 695372.16 | 800610.45 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000 | 851000
Percentage complete | cost to date / cost at completion | 100% | 100% | 81.71% | 94.08% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 63700 | 63700 | 22400 | 22400 | 51000 | 51000 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700 | 63700
Variations raised, not yet decided (claimed) |  | 0 | 0 | 46700 | 73200 | 41400 | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 1043700 | 1043700 | 1025750 | 1039000 | 1051700 | 1051700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 1043700 | 1043700 | 838164.5 | 977478.56 | 1051700 | 1051700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700
REVENUE IN THE MONTH | change in revenue to date | 363553.44 | 0 | 158017.94 | 139314.06 | 74221.44 | 0 | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 81199.46 | 0 | 31291.8 | 34075.77 | 23831.89 | 0 | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 1043700 | 1043700 | 1002400 | 1002400 | 1031000 | 1031000 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 1043700 | 1043700 | 676972.41 | 819084.67 | 969952.26 | 1031000 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700 | 1043700
Certified in the month |  | 541726.44 | 0 | 174998.85 | 142112.26 | 150867.59 | 61047.74 | 12700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 26092.5 | 0 | 33848.6205 | 40954.2335 | 48497.613 | 25775 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 26092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention withheld / (released) in the month |  | 993.822 | -26092.5 | 8749.9425 | 7105.613 | 7543.3795 | -22722.613 | 317.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 540732.618 | 26092.5 | 166248.9075 | 135006.647 | 143324.2105 | 83770.353 | 12382.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 72998.9034 | 3522.4875 | 22443.6025 | 18225.8973 | 19348.7684 | 11308.9977 | 1671.6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3522.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 613731.5214 | 29614.9875 | 188692.51 | 153232.5443 | 162672.9789 | 95079.3507 | 14054.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29614.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 834128.2614 | 29614.9875 | 217597.9 | 205867.58 | 125893.45 | 155017.36 | 115232.36 | 14519.61 | 0 | 0 | 0.00143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29614.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 0 | 0 | 191491.35 | 138856.3144 | 175635.8433 | 115697.8339 | 14519.6114 | 0.00143 | 0.00143 | 0.00143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29614.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 161192.09 | 158393.89 | 81747.74 | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 161192.09 | 158393.89 | 81747.74 | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 415048.62 | 415048.62 | 337557.33 | 389579.9 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62 | 415048.62
Retention held from subcontractors |  | 10376.2155 | 0 | 16877.8665 | 19478.995 | 20752.431 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 10376.2155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontractor retention withheld / (released) |  | -3404.088 | -10376.2155 | 3097.563 | 2601.1285 | 1273.436 | -10376.2155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10376.2155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 0 | 98000 | 98000 | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 0 | 0 | 187585.5 | 61521.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check (actual months): revenue to date less % complete x contract revenue | must be zero |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS-2502 Deep retrofit of 24 council homes, Phase 1 ¦ Kildrum County Council ¦ segment PS ¦ Completed
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0.625 | 0.75 | 0.875 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0.68359 | 0.84375 | 0.95703 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0.5 | 0.68359 | 0.84375 | 0.95703 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 62064.74 | 0 | 25139.45 | 19305.56 | 11616.66 | 6003.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 271319.35 | 0 | 115846.57 | 86983.55 | 45995.01 | 22494.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 111445.86 | 0 | 47365.64 | 34162.6 | 19879.12 | 10038.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 14462.99 | 0 | 5935.65 | 4596.24 | 2738.29 | 1192.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 24540.69 | 0 | 11112.56 | 7506.6 | 3978.11 | 1943.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 483833.63 | 0 | 205399.87 | 152554.55 | 84207.19 | 41672.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 941000.01 | 941000.01 | 662566.25 | 815120.8 | 899327.99 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 941000.01 | 941000.01 | 948000 | 948000 | 941000 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01 | 941000.01
Percentage complete | cost to date / cost at completion | 100% | 100% | 69.89% | 85.98% | 95.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 29000 | 29000 | 0 | 18600 | 18600 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
Variations raised, not yet decided (claimed) |  | 0 | 0 | 18600 | 11200 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 1109000 | 1109000 | 1089300 | 1104200 | 1104200 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 1109000 | 1109000 | 761322.17 | 949426.57 | 1055300.71 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000
REVENUE IN THE MONTH | change in revenue to date | 583692.68 | 0 | 236014.85 | 188104.4 | 105874.14 | 53699.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 99859.05 | 0 | 30614.98 | 35549.85 | 21666.95 | 12027.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 1109000 | 1109000 | 1080000 | 1098600 | 1098600 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 1109000 | 1109000 | 520822.46 | 767822.03 | 944611.51 | 1059888.14 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000 | 1109000
Certified in the month |  | 777258.13 | 0 | 189080.59 | 246999.57 | 176789.48 | 115276.63 | 49111.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 27725 | 0 | 26041.123 | 38391.1015 | 47230.5755 | 52994.407 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 27725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention withheld / (released) in the month |  | 11137.9065 | -27725 | 9454.0295 | 12349.9785 | 8839.474 | 5763.8315 | -25269.407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27725 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 766120.2235 | 27725 | 179626.5605 | 234649.5915 | 167950.006 | 109512.7985 | 74381.267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27725 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 766120.2235 | 27725 | 179626.5605 | 234649.5915 | 167950.006 | 109512.7985 | 74381.267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27725 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 922317.4335 | 27725 | 144766.1 | 163070.87 | 253854.78 | 178666.93 | 112812.06 | 69146.69 | 0 | 0 | 0.0035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27725 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 0 | 0 | 191057.6705 | 262636.392 | 176731.618 | 107577.4865 | 69146.6935 | 0.0035 | 0.0035 | 0.0035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27725 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 240499.71 | 181604.54 | 110689.2 | 49111.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 240499.71 | 181604.54 | 110689.2 | 49111.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 524059.38 | 524059.38 | 368586.6 | 455570.15 | 501565.16 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38 | 524059.38
Retention held from subcontractors |  | 13101.4845 | 0 | 18429.33 | 22778.5075 | 25078.258 | 26202.969 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 13101.4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontractor retention withheld / (released) |  | 464.483 | -13101.4845 | 5792.3285 | 4349.1775 | 2299.7505 | 1124.711 | -13101.4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13101.4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 0 | 108000 | 108000 | 108000 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 0 | 0 | 327977.83 | 154773.43 | 48899.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check (actual months): revenue to date less % complete x contract revenue | must be zero |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-2601 Office fit-out, 2,300 m2, Dublin 4 ¦ Harbourline Insurance DAC ¦ segment CF ¦ In progress
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0.11111 | 0.22222 | 0.33333 | 0.44444 | 0.55556 | 0.66667 | 0.77778 | 0.88889 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0.034294 | 0.1262 | 0.25926 | 0.41701 | 0.58299 | 0.74074 | 0.8738 | 0.96571 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0.034294 | 0.1262 | 0.25926 | 0.41701 | 0.58299 | 0.74074 | 0.8738 | 0.96571 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 190556.2896 | 0 | 0 | 0 | 4847.06 | 13397.14 | 23717.38 | 29166.41 | 35066.67 | 30036.98 | 27880.9048 | 19257.9446 | 7185.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 592896.86 | 0 | 0 | 0 | 18113.03 | 44923.87 | 70640.96 | 89625.98 | 109569.75 | 90258.74 | 87127.8276 | 60181.0768 | 22455.6257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 286204.7844 | 0 | 0 | 0 | 7969.6 | 21409.7 | 34121.09 | 47617.47 | 55295.75 | 38304.2 | 41821.3572 | 28886.9169 | 10778.7003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 35360.5218 | 0 | 0 | 0 | 989.86 | 2574.07 | 4285.88 | 5906.54 | 6585.68 | 4832.62 | 5227.6697 | 3610.8646 | 1347.3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 84981.5442 | 0 | 0 | 0 | 2446.98 | 6577.39 | 10558.36 | 13057.1 | 16107.85 | 12466.83 | 12197.8959 | 8425.3507 | 3143.7876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 1190000 | 0 | 0 | 0 | 34366.53 | 88882.17 | 143323.67 | 185373.5 | 222625.7 | 175899.37 | 174255.6551 | 120362.1535 | 44911.2513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 1190000 | 1190000 | 0 | 0 | 34366.53 | 123248.7 | 266572.37 | 451945.87 | 674571.57 | 850470.94 | 1024726.5951 | 1145088.7487 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 1190000 | 1190000 | 1018000 | 1018000 | 1018000 | 1018000 | 1114000 | 1158000 | 1158000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000 | 1190000
Percentage complete | cost to date / cost at completion | 100% | 100% | 0% | 0% | 3.376% | 12.11% | 23.93% | 39.03% | 58.25% | 71.47% | 86.11% | 96.23% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 6900 | 41400 | 76300 | 80400 | 118000 | 118000 | 76200 | 37600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 118000 | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 80400 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 1289700 | 1289700 | 1180000 | 1180000 | 1180000 | 1183450 | 1200700 | 1218150 | 1253200 | 1272000 | 1272000 | 1278270 | 1284060 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 1289700 | 1289700 | 0 | 0 | 39835.47 | 143279.64 | 287319.07 | 475421.3 | 730028.58 | 909074.82 | 1095338.0076 | 1230027.3906 | 1284060 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700
REVENUE IN THE MONTH | change in revenue to date | 1289700 | 0 | 0 | 0 | 39835.47 | 103444.17 | 144039.43 | 188102.23 | 254607.28 | 179046.24 | 186263.1876 | 134689.383 | 54032.6094 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 99700 | 0 | 0 | 0 | 5468.94 | 14562 | 715.76 | 2728.73 | 31981.58 | 3146.87 | 12007.5324 | 14327.2294 | 9121.3581 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 1289700 | 1289700 | 1180000 | 1180000 | 1180000 | 1180000 | 1180000 | 1180000 | 1213000 | 1213000 | 1213000 | 1240170 | 1265260 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 1289700 | 1289700 | 0 | 0 | 0 | 39835.47 | 142861.95 | 282365.71 | 473411.35 | 706610.81 | 866908.6136 | 1067928.7239 | 1217508.3951 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700 | 1289700
Certified in the month |  | 1289700 | 0 | 0 | 0 | 0 | 39835.47 | 103026.48 | 139503.76 | 191045.64 | 233199.46 | 160297.8036 | 201020.1103 | 149579.6711 | 72191.6049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 32242.5 | 0 | 0 | 0 | 0 | 1991.7735 | 7143.0975 | 14118.2855 | 23670.5675 | 35330.5405 | 43345.4307 | 53396.4362 | 60875.4198 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 32242.5 | 0
Retention withheld / (released) in the month |  | 32242.5 | -32242.5 | 0 | 0 | 0 | 1991.7735 | 5151.324 | 6975.188 | 9552.282 | 11659.973 | 8014.8902 | 10051.0055 | 7478.9836 | -28632.9198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32242.5
Invoiced ex VAT (certified less retention movement) |  | 1257457.5 | 32242.5 | 0 | 0 | 0 | 37843.6965 | 97875.156 | 132528.572 | 181493.358 | 221539.487 | 152282.9134 | 190969.1048 | 142100.6876 | 100824.5247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32242.5
Output VAT on invoices | 0% where the council accounts under the reverse charge | 169756.7625 | 4352.7375 | 0 | 0 | 0 | 5108.899 | 13213.1461 | 17891.3572 | 24501.6033 | 29907.8307 | 20558.1933 | 25780.8291 | 19183.5928 | 13611.3108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4352.7375
Invoiced incl. VAT |  | 1427214.2625 | 36595.2375 | 0 | 0 | 0 | 42952.5955 | 111088.3021 | 150419.9292 | 205994.9613 | 251447.3177 | 172841.1068 | 216749.9339 | 161284.2804 | 114435.8355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36595.2375
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 1312778.427 | 114435.8355 | 0 | 0 | 0 | 4497.27 | 40564.92 | 122518.96 | 136091.39 | 224074.46 | 234156.1059 | 172841.1068 | 216749.9339 | 161284.2804 | 114435.8355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 114435.8355 | 36595.2375 | 0 | 0 | 0 | 38455.3255 | 108978.7076 | 136879.6768 | 206783.2481 | 234156.1059 | 172841.1068 | 216749.9339 | 161284.2804 | 114435.8355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36595.2375
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 0 | 0 | 39835.47 | 103444.17 | 144457.12 | 193055.59 | 256617.23 | 202464.01 | 228429.3939 | 162098.6666 | 66551.6049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 0 | 0 | 39835.47 | 103444.17 | 144457.12 | 193055.59 | 256617.23 | 202464.01 | 228429.3939 | 162098.6666 | 66551.6049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 592896.86 | 592896.86 | 0 | 0 | 18113.03 | 63036.9 | 133677.86 | 223303.84 | 332873.59 | 423132.33 | 510260.1576 | 570441.2343 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86 | 592896.86
Retention held from subcontractors |  | 14822.4215 | 0 | 0 | 0 | 905.6515 | 3151.845 | 6683.893 | 11165.192 | 16643.6795 | 21156.6165 | 25513.0079 | 28522.0617 | 29644.843 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 14822.4215 | 0
Subcontractor retention withheld / (released) |  | 14822.4215 | -14822.4215 | 0 | 0 | 905.6515 | 2246.1935 | 3532.048 | 4481.299 | 5478.4875 | 4512.937 | 4356.3914 | 3009.0538 | 1122.7813 | -14822.4215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14822.4215
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 0 | 0 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 0 | 0 | 0 | 1180000 | 1140164.53 | 1040170.36 | 913380.93 | 742728.7 | 523171.42 | 362925.18 | 176661.9924 | 48242.6094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 1180000 | 0 | 0 | 1180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check (actual months): revenue to date less % complete x contract revenue | must be zero |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-2602 Hotel bedroom refurbishment, 64 rooms ¦ Tolka Hospitality Ltd ¦ segment CF ¦ In progress
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0.11111 | 0.22222 | 0.33333 | 0.44444 | 0.55556 | 0.66667 | 0.77778 | 0.88889 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0.034294 | 0.1262 | 0.25926 | 0.41701 | 0.58299 | 0.74074 | 0.8738 | 0.96571 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.034294 | 0.1262 | 0.25926 | 0.41701 | 0.58299 | 0.74074 | 0.8738 | 0.96571 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 115625.2485 | 16654.1251 | 0 | 0 | 0 | 0 | 0 | 3938.24 | 12971.66 | 17617 | 20817.6564 | 21903.795 | 20817.6564 | 17559.2406 | 12128.5477 | 4525.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 353677.019 | 52044.141 | 0 | 0 | 0 | 0 | 0 | 13677.06 | 35197.37 | 51370.25 | 65055.1763 | 68449.3594 | 65055.1763 | 54872.627 | 37901.7114 | 14142.4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 172994.6827 | 24981.1877 | 0 | 0 | 0 | 0 | 0 | 5956.3 | 20397.19 | 24993.67 | 31226.4846 | 32855.6925 | 31226.4846 | 26338.8609 | 18192.8215 | 6788.3662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 21570.3203 | 3122.6485 | 0 | 0 | 0 | 0 | 0 | 766.17 | 2359.28 | 3238.93 | 3903.3106 | 4106.9616 | 3903.3106 | 3292.3576 | 2274.1027 | 848.5458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 50044.4475 | 7286.1797 | 0 | 0 | 0 | 0 | 0 | 1720.39 | 5192.47 | 7651.06 | 9107.7247 | 9582.9103 | 9107.7247 | 7682.1678 | 5306.2396 | 1979.9401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 713911.7179 | 104088.2821 | 0 | 0 | 0 | 0 | 0 | 26058.16 | 76117.97 | 104870.91 | 130110.3526 | 136898.7188 | 130110.3526 | 109745.2539 | 75803.4228 | 28284.8593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 713911.7179 | 818000 | 0 | 0 | 0 | 0 | 0 | 26058.16 | 102176.13 | 207047.04 | 337157.3926 | 474056.1114 | 604166.464 | 713911.7179 | 789715.1407 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 818000 | 818000 | 812000 | 812000 | 812000 | 812000 | 812000 | 812000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000 | 818000
Percentage complete | cost to date / cost at completion | 87.28% | 100% | 0% | 0% | 0% | 0% | 0% | 3.209% | 12.49% | 25.31% | 41.22% | 57.95% | 73.86% | 87.28% | 96.54% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 27400 | 27400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400 | 27400
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 28800 | 19500 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 19500 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 980075 | 980075 | 940000 | 940000 | 940000 | 940000 | 940000 | 954400 | 954400 | 977150 | 977150 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 855363.1136 | 980075 | 0 | 0 | 0 | 0 | 0 | 30627.97 | 119213.81 | 247330.09 | 402754.7019 | 567983.5494 | 723873.4073 | 855363.1136 | 946185.9004 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075
REVENUE IN THE MONTH | change in revenue to date | 855363.1136 | 124711.8864 | 0 | 0 | 0 | 0 | 0 | 30627.97 | 88585.84 | 128116.28 | 155424.6119 | 165228.8475 | 155889.858 | 131489.7063 | 90822.7868 | 33889.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 141451.3957 | 20623.6043 | 0 | 0 | 0 | 0 | 0 | 4569.81 | 12467.87 | 23245.37 | 25314.2593 | 28330.1286 | 25779.5054 | 21744.4524 | 15019.364 | 5604.2403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 980075 | 980075 | 940000 | 940000 | 940000 | 940000 | 940000 | 940000 | 940000 | 967400 | 967400 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 723873.4073 | 980075 | 0 | 0 | 0 | 0 | 0 | 0 | 30165.85 | 120837.64 | 244862.2329 | 403960.3075 | 567983.5494 | 723873.4073 | 855363.1136 | 946185.9004 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075 | 980075
Certified in the month |  | 723873.4073 | 256201.5927 | 0 | 0 | 0 | 0 | 0 | 0 | 30165.85 | 90671.79 | 124024.5929 | 159098.0746 | 164023.2419 | 155889.858 | 131489.7063 | 90822.7868 | 33889.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 21716.2022 | 14701.125 | 0 | 0 | 0 | 0 | 0 | 0 | 904.9755 | 3625.1292 | 7345.867 | 12118.8092 | 17039.5065 | 21716.2022 | 25660.8934 | 28385.577 | 14701.125 | 14701.125 | 14701.125 | 14701.125 | 14701.125 | 14701.125 | 14701.125 | 14701.125 | 14701.125 | 14701.125
Retention withheld / (released) in the month |  | 21716.2022 | -7015.0772 | 0 | 0 | 0 | 0 | 0 | 0 | 904.9755 | 2720.1537 | 3720.7378 | 4772.9422 | 4920.6973 | 4676.6957 | 3944.6912 | 2724.6836 | -13684.452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 702157.2051 | 263216.6699 | 0 | 0 | 0 | 0 | 0 | 0 | 29260.8745 | 87951.6363 | 120303.8551 | 154325.1324 | 159102.5446 | 151213.1622 | 127545.0151 | 88098.1032 | 47573.5516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 94791.2227 | 35534.2504 | 0 | 0 | 0 | 0 | 0 | 0 | 3950.2181 | 11873.4709 | 16241.0204 | 20833.8929 | 21478.8435 | 20413.7769 | 17218.577 | 11893.2439 | 6422.4295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 796948.4278 | 298750.9203 | 0 | 0 | 0 | 0 | 0 | 0 | 33211.0926 | 99825.1072 | 136544.8755 | 175159.0253 | 180581.3881 | 171626.9391 | 144763.5921 | 99991.3471 | 53995.981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 535030.7946 | 560668.5535 | 0 | 0 | 0 | 0 | 0 | 0 | -6040.66 | 23630.35 | 65533.9562 | 118184.9914 | 155851.9504 | 177870.2067 | 176104.1636 | 158195.2656 | 122377.4696 | 76993.6641 | 26997.9905 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 261917.6332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39251.7526 | 115446.5098 | 186457.4291 | 243431.463 | 268160.9008 | 261917.6332 | 230577.0617 | 172373.1432 | 103991.6546 | 26997.9905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 131489.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 30627.97 | 89047.96 | 126492.45 | 157892.469 | 164023.2419 | 155889.858 | 131489.7063 | 90822.7868 | 33889.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 131489.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 30627.97 | 89047.96 | 126492.45 | 157892.469 | 164023.2419 | 155889.858 | 131489.7063 | 90822.7868 | 33889.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 353677.019 | 405721.16 | 0 | 0 | 0 | 0 | 0 | 13677.06 | 48874.43 | 100244.68 | 165299.8563 | 233749.2157 | 298804.392 | 353677.019 | 391578.7304 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16 | 405721.16
Retention held from subcontractors |  | 17683.8509 | 10143.029 | 0 | 0 | 0 | 0 | 0 | 683.853 | 2443.7215 | 5012.234 | 8264.9928 | 11687.4608 | 14940.2196 | 17683.8509 | 19578.9365 | 20286.058 | 10143.029 | 10143.029 | 10143.029 | 10143.029 | 10143.029 | 10143.029 | 10143.029 | 10143.029 | 10143.029 | 10143.029
Subcontractor retention withheld / (released) |  | 17683.8509 | -7540.8219 | 0 | 0 | 0 | 0 | 0 | 683.853 | 1759.8685 | 2568.5125 | 3252.7588 | 3422.468 | 3252.7588 | 2743.6313 | 1895.0856 | 707.1215 | -10143.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 94000 | 0 | 0 | 0 | 0 | 0 | 94000 | 94000 | 94000 | 94000 | 94000 | 94000 | 94000 | 94000 | 94000 | 94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 124711.8864 | 0 | 0 | 0 | 0 | 0 | 940000 | 923772.03 | 835186.19 | 729819.91 | 574395.2981 | 412091.4506 | 256201.5927 | 124711.8864 | 33889.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 940000 | 0 | 0 | 0 | 0 | 0 | 940000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check (actual months): revenue to date less % complete x contract revenue | must be zero |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-2603 Restaurant fit-out, Dublin 7 ¦ Ember & Oak Restaurants Ltd ¦ segment CF ¦ In progress
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.6 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.104 | 0.352 | 0.648 | 0.896 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.104 | 0.352 | 0.648 | 0.896 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 53553.1692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5535.27 | 13290.6685 | 15863.056 | 13290.6685 | 5573.5062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 166191.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16135.07 | 41533.3392 | 49572.05 | 41533.3392 | 17417.2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 79789.8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.05 | 19936.0028 | 23794.584 | 19936.0028 | 8360.2592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 10062.2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058.88 | 2492.0003 | 2974.323 | 2492.0003 | 1045.0324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 23403.6909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2395.86 | 5814.6675 | 6940.087 | 5814.6675 | 2438.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 333000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32888.13 | 83066.6783 | 99144.0999 | 83066.6783 | 34834.4135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 333000 | 333000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32888.13 | 115954.8083 | 215098.9082 | 298165.5865 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 333000 | 333000 | 329000 | 329000 | 329000 | 329000 | 329000 | 329000 | 329000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000 | 333000
Percentage complete | cost to date / cost at completion | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.876% | 34.82% | 64.59% | 89.54% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 16200 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200 | 16200
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 400530 | 400530 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 398100 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 400530 | 400530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39317.61 | 139469.6077 | 258719.4165 | 358631.4185 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530
REVENUE IN THE MONTH | change in revenue to date | 400530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39317.61 | 100151.9977 | 119249.8088 | 99912.002 | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 67530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6429.48 | 17085.3194 | 20105.7089 | 16845.3237 | 7064.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 400530 | 400530 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 358631.4185 | 400530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39557.6057 | 139469.6077 | 258719.4165 | 358631.4185 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530 | 400530
Certified in the month |  | 358631.4185 | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39557.6057 | 99912.002 | 119249.8088 | 99912.002 | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 17931.5709 | 10013.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977.8803 | 6973.4804 | 12935.9708 | 17931.5709 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25 | 10013.25
Retention withheld / (released) in the month |  | 17931.5709 | -7918.3209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977.8803 | 4995.6001 | 5962.4904 | 4995.6001 | -7918.3209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 340699.8476 | 49816.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37579.7254 | 94916.4019 | 113287.3184 | 94916.4019 | 49816.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 45994.4794 | 6725.2818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5073.2629 | 12813.7143 | 15293.788 | 12813.7143 | 6725.2818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 386694.327 | 56542.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42652.9884 | 107730.1161 | 128581.1064 | 107730.1161 | 56542.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 278964.2109 | 164272.3004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42652.9884 | 107730.1161 | 128581.1064 | 107730.1161 | 56542.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 107730.1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42652.9884 | 107730.1161 | 128581.1064 | 107730.1161 | 56542.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39317.61 | 99912.002 | 119249.8088 | 99912.002 | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39317.61 | 99912.002 | 119249.8088 | 99912.002 | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 166191.005 | 166191.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16135.07 | 57668.4092 | 107240.4591 | 148773.7983 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005 | 166191.005
Retention held from subcontractors |  | 8309.5503 | 4154.7751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.7535 | 2883.4205 | 5362.023 | 7438.6899 | 8309.5503 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751 | 4154.7751
Subcontractor retention withheld / (released) |  | 8309.5503 | -4154.7751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.7535 | 2076.667 | 2478.6025 | 2076.667 | 870.8603 | -4154.7751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 358782.39 | 261060.3923 | 141810.5835 | 41898.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check (actual months): revenue to date less % complete x contract revenue | must be zero |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS-2601 Deep retrofit of 30 council homes, Phase 2 ¦ Kildrum County Council ¦ segment PS ¦ In progress
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0.028 | 0.104 | 0.216 | 0.352 | 0.5 | 0.648 | 0.784 | 0.896 | 0.972 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.028 | 0.104 | 0.216 | 0.352 | 0.5 | 0.648 | 0.784 | 0.896 | 0.972 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 135866.0467 | 16075.3731 | 0 | 0 | 0 | 0 | 3765.57 | 10550.21 | 15618.82 | 21844.88 | 22876.4924 | 22876.4924 | 21021.6417 | 17311.9402 | 11747.388 | 4327.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 582836.0068 | 69247.7608 | 0 | 0 | 0 | 0 | 16519.7 | 46285.24 | 75715.48 | 82096.53 | 98544.8904 | 98544.8904 | 90554.7642 | 74574.5117 | 50604.1329 | 18643.6279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 243419.4912 | 28441.0446 | 0 | 0 | 0 | 0 | 6470.19 | 22278.85 | 29929.2 | 35972.71 | 40473.7943 | 40473.7943 | 37192.1353 | 30628.8173 | 20783.8403 | 7657.2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 31556.8223 | 3709.7015 | 0 | 0 | 0 | 0 | 914.62 | 2460.24 | 4183.21 | 4594.16 | 5279.1906 | 5279.1906 | 4851.1481 | 3995.0631 | 2710.9357 | 998.7658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 52664.9172 | 6182.8358 | 0 | 0 | 0 | 0 | 1585.13 | 4316.22 | 6663.73 | 7758.85 | 8798.6509 | 8798.6509 | 8085.2468 | 6658.4385 | 4518.2262 | 1664.6096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 1046343.2842 | 123656.7158 | 0 | 0 | 0 | 0 | 29255.21 | 85890.76 | 132110.44 | 152267.13 | 175973.0186 | 175973.0186 | 161704.936 | 133168.7709 | 90364.5231 | 33292.1927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 1046343.2842 | 1170000 | 0 | 0 | 0 | 0 | 29255.21 | 115145.97 | 247256.41 | 399523.54 | 575496.5586 | 751469.5773 | 913174.5133 | 1046343.2842 | 1136707.8073 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 1170000 | 1170000 | 1158000 | 1158000 | 1158000 | 1158000 | 1158000 | 1158000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000
Percentage complete | cost to date / cost at completion | 89.43% | 100% | 0% | 0% | 0% | 0% | 2.526% | 9.944% | 21.13% | 34.15% | 49.19% | 64.23% | 78.05% | 89.43% | 97.15% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 22100 | 22100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100 | 22100
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24300 | 24300 | 14700 | 14700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 14700 | 14700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 1351655 | 1351655 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1332150 | 1332150 | 1349450 | 1349450 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 1208799.258 | 1351655 | 0 | 0 | 0 | 0 | 33347.91 | 132462.61 | 281523.61 | 460800.89 | 663763.9582 | 868143.2577 | 1054954.6127 | 1208799.258 | 1313193.8387 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655
REVENUE IN THE MONTH | change in revenue to date | 1208799.258 | 142855.742 | 0 | 0 | 0 | 0 | 33347.91 | 99114.7 | 149061 | 179277.28 | 202963.0682 | 204379.2995 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 162455.9738 | 19199.0262 | 0 | 0 | 0 | 0 | 4092.7 | 13223.94 | 16950.56 | 27010.15 | 26990.0495 | 28406.2809 | 25106.4189 | 20675.8744 | 14030.0576 | 5168.9686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 1351655 | 1351655 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1342100 | 1342100 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 1054954.6127 | 1351655 | 0 | 0 | 0 | 0 | 0 | 33347.91 | 131254.47 | 283626.35 | 458291.0624 | 664848.5478 | 868143.2577 | 1054954.6127 | 1208799.258 | 1313193.8387 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655 | 1351655
Certified in the month |  | 1054954.6127 | 296700.3873 | 0 | 0 | 0 | 0 | 0 | 33347.91 | 97906.56 | 152371.88 | 174664.7124 | 206557.4854 | 203294.7098 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 52747.7306 | 33791.375 | 0 | 0 | 0 | 0 | 0 | 1667.3955 | 6562.7235 | 14181.3175 | 22914.5531 | 33242.4274 | 43407.1629 | 52747.7306 | 60439.9629 | 65659.6919 | 33791.375 | 33791.375 | 33791.375 | 33791.375 | 33791.375 | 33791.375 | 33791.375 | 33791.375 | 33791.375 | 33791.375
Retention withheld / (released) in the month |  | 52747.7306 | -18956.3556 | 0 | 0 | 0 | 0 | 0 | 1667.3955 | 4895.328 | 7618.594 | 8733.2356 | 10327.8743 | 10164.7355 | 9340.5677 | 7692.2323 | 5219.729 | -31868.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 1002206.882 | 315656.743 | 0 | 0 | 0 | 0 | 0 | 31680.5145 | 93011.232 | 144753.286 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 1002206.882 | 315656.743 | 0 | 0 | 0 | 0 | 0 | 31680.5145 | 93011.232 | 144753.286 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 824736.0948 | 493127.5302 | 0 | 0 | 0 | 0 | 0 | -1130.93 | 33354.11 | 89759.77 | 147462.0825 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 177470.7872 | 0 | 0 | 0 | 0 | 0 | 0 | 32811.4445 | 92468.5665 | 147462.0825 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 153844.6453 | 0 | 0 | 0 | 0 | 0 | 33347.91 | 99114.7 | 150269.14 | 177174.54 | 205472.8957 | 203294.7098 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 153844.6453 | 0 | 0 | 0 | 0 | 0 | 33347.91 | 99114.7 | 150269.14 | 177174.54 | 205472.8957 | 203294.7098 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 582836.0068 | 652083.7676 | 0 | 0 | 0 | 0 | 16519.7 | 62804.94 | 138520.42 | 220616.95 | 319161.8404 | 417706.7309 | 508261.4951 | 582836.0068 | 633440.1397 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676 | 652083.7676
Retention held from subcontractors |  | 29141.8003 | 16302.0942 | 0 | 0 | 0 | 0 | 825.985 | 3140.247 | 6926.021 | 11030.8475 | 15958.092 | 20885.3365 | 25413.0748 | 29141.8003 | 31672.007 | 32604.1884 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942 | 16302.0942
Subcontractor retention withheld / (released) |  | 29141.8003 | -12839.7061 | 0 | 0 | 0 | 0 | 825.985 | 2314.262 | 3785.774 | 4104.8265 | 4927.2445 | 4927.2445 | 4527.7382 | 3728.7256 | 2530.2066 | 932.1814 | -16302.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 132000 | 0 | 0 | 0 | 0 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 142855.742 | 0 | 0 | 0 | 0 | 1320000 | 1286652.09 | 1199687.39 | 1050626.39 | 888649.11 | 685686.0418 | 483511.7423 | 296700.3873 | 142855.742 | 38461.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check (actual months): revenue to date less % complete x contract revenue | must be zero |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-2604 Medical clinic fit-out, Dublin 15 ¦ Liffeyside Medical Partners ¦ segment CF ¦ Contracted
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.33333 | 0.5 | 0.66667 | 0.83333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.5 | 0.74074 | 0.92593 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.5 | 0.74074 | 0.92593 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 43920 | 43920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6506.6667 | 16266.6667 | 21146.6667 | 21146.6667 | 16266.6667 | 6506.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 137250 | 137250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20333.3333 | 50833.3333 | 66083.3333 | 66083.3333 | 50833.3333 | 20333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 65880 | 65880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760 | 24400 | 31720 | 31720 | 24400 | 9760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 8235 | 8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 3050 | 3965 | 3965 | 3050 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 19215 | 19215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2846.6667 | 7116.6667 | 9251.6667 | 9251.6667 | 7116.6667 | 2846.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 274500 | 274500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40666.6667 | 101666.6667 | 132166.6667 | 132166.6667 | 101666.6667 | 40666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 274500 | 549000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40666.6667 | 142333.3333 | 274500 | 406666.6667 | 508333.3333 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000 | 549000
Percentage complete | cost to date / cost at completion | 50% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.407% | 25.93% | 50% | 74.07% | 92.59% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 320000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47407.4074 | 165925.9259 | 320000 | 474074.0741 | 592592.5926 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000
REVENUE IN THE MONTH | change in revenue to date | 320000 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47407.4074 | 118518.5185 | 154074.0741 | 154074.0741 | 118518.5185 | 47407.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 45500 | 45500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6740.7407 | 16851.8519 | 21907.4074 | 21907.4074 | 16851.8519 | 6740.7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 165925.9259 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47407.4074 | 165925.9259 | 320000 | 474074.0741 | 592592.5926 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000
Certified in the month |  | 165925.9259 | 474074.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47407.4074 | 118518.5185 | 154074.0741 | 154074.0741 | 118518.5185 | 47407.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 8296.2963 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2370.3704 | 8296.2963 | 16000 | 23703.7037 | 29629.6296 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
Retention withheld / (released) in the month |  | 8296.2963 | 7703.7037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2370.3704 | 5925.9259 | 7703.7037 | 7703.7037 | 5925.9259 | -13629.6296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 157629.6296 | 466370.3704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45037.037 | 112592.5926 | 146370.3704 | 146370.3704 | 112592.5926 | 61037.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 21280 | 62960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6080 | 15200 | 19760 | 19760 | 15200 | 8240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 178909.6296 | 529330.3704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51117.037 | 127792.5926 | 166130.3704 | 166130.3704 | 127792.5926 | 69277.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 51117.037 | 657122.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51117.037 | 127792.5926 | 166130.3704 | 166130.3704 | 127792.5926 | 69277.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 127792.5926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51117.037 | 127792.5926 | 166130.3704 | 166130.3704 | 127792.5926 | 69277.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 154074.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47407.4074 | 118518.5185 | 154074.0741 | 154074.0741 | 118518.5185 | 47407.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 154074.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47407.4074 | 118518.5185 | 154074.0741 | 154074.0741 | 118518.5185 | 47407.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 137250 | 274500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20333.3333 | 71166.6667 | 137250 | 203333.3333 | 254166.6667 | 274500 | 274500 | 274500 | 274500 | 274500 | 274500 | 274500 | 274500 | 274500 | 274500
Retention held from subcontractors |  | 6862.5 | 6862.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016.6667 | 3558.3333 | 6862.5 | 10166.6667 | 12708.3333 | 13725 | 6862.5 | 6862.5 | 6862.5 | 6862.5 | 6862.5 | 6862.5 | 6862.5 | 6862.5 | 6862.5
Subcontractor retention withheld / (released) |  | 6862.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016.6667 | 2541.6667 | 3304.1667 | 3304.1667 | 2541.6667 | 1016.6667 | -6862.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 640000 | 592592.5926 | 474074.0741 | 320000 | 165925.9259 | 47407.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS-2602 Deep retrofit of 40 council homes, Phase 3 ¦ Kildrum County Council ¦ segment PS ¦ Contracted
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11111 | 0.22222 | 0.33333 | 0.44444 | 0.55556 | 0.66667 | 0.77778 | 0.88889 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034294 | 0.1262 | 0.25926 | 0.41701 | 0.58299 | 0.74074 | 0.8738 | 0.96571 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034294 | 0.1262 | 0.25926 | 0.41701 | 0.58299 | 0.74074 | 0.8738 | 0.96571 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 201240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6901.2346 | 18495.3086 | 26776.7901 | 31745.679 | 33401.9753 | 31745.679 | 26776.7901 | 18495.3086 | 6901.2346 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 866880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29728.3951 | 79672.0988 | 115346.1728 | 136750.6173 | 143885.4321 | 136750.6173 | 115346.1728 | 79672.0988 | 29728.3951 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 356040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12209.8765 | 32722.4691 | 47374.321 | 56165.4321 | 59095.8025 | 56165.4321 | 47374.321 | 32722.4691 | 12209.8765 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 46440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592.5926 | 4268.1481 | 6179.2593 | 7325.9259 | 7708.1481 | 7325.9259 | 6179.2593 | 4268.1481 | 1592.5926 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 77400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2654.321 | 7113.5802 | 10298.7654 | 12209.8765 | 12846.9136 | 12209.8765 | 10298.7654 | 7113.5802 | 2654.321 | 0
COST INCURRED IN THE MONTH | sum of cost types | 0 | 1548000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53086.4198 | 142271.6049 | 205975.3086 | 244197.5309 | 256938.2716 | 244197.5309 | 205975.3086 | 142271.6049 | 53086.4198 | 0
Cost to date | opening + cost | 0 | 1548000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53086.4198 | 195358.0247 | 401333.3333 | 645530.8642 | 902469.1358 | 1146666.6667 | 1352641.9753 | 1494913.5802 | 1548000 | 1548000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000 | 1548000
Percentage complete | cost to date / cost at completion | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.429% | 12.62% | 25.93% | 41.7% | 58.3% | 74.07% | 87.38% | 96.57% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60356.6529 | 222112.4829 | 456296.2963 | 733936.8999 | 1026063.1001 | 1303703.7037 | 1537887.5171 | 1699643.3471 | 1760000 | 1760000
REVENUE IN THE MONTH | change in revenue to date | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 161755.8299 | 60356.6529 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 212000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7270.2332 | 19484.225 | 28208.5048 | 33443.0727 | 35187.9287 | 33443.0727 | 28208.5048 | 19484.225 | 7270.2332 | 0
Billing basis (contract + approved + agreed variations) |  | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60356.6529 | 222112.4829 | 456296.2963 | 733936.8999 | 1026063.1001 | 1303703.7037 | 1537887.5171 | 1699643.3471 | 1760000
Certified in the month |  | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 161755.8299 | 60356.6529
Retention held by the client | retention % x certified x unreleased share | 0 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017.8326 | 11105.6241 | 22814.8148 | 36696.845 | 51303.155 | 65185.1852 | 76894.3759 | 84982.1674 | 44000
Retention withheld / (released) in the month |  | 0 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017.8326 | 8087.7915 | 11709.1907 | 13882.0302 | 14606.31 | 13882.0302 | 11709.1907 | 8087.7915 | -40982.1674
Invoiced ex VAT (certified less retention movement) |  | 0 | 1716000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57338.8203 | 153668.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 153668.0384 | 101338.8203
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 0 | 1716000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57338.8203 | 153668.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 153668.0384 | 101338.8203
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 1614661.1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57338.8203 | 153668.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 153668.0384
Trade receivable incl. VAT | opening + invoiced - received | 0 | 101338.8203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57338.8203 | 153668.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 153668.0384 | 101338.8203
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 161755.8299 | 60356.6529 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 161755.8299 | 60356.6529 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 866880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29728.3951 | 109400.4938 | 224746.6667 | 361497.284 | 505382.716 | 642133.3333 | 757479.5062 | 837151.6049 | 866880 | 866880
Retention held from subcontractors |  | 0 | 21672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1486.4198 | 5470.0247 | 11237.3333 | 18074.8642 | 25269.1358 | 32106.6667 | 37873.9753 | 41857.5802 | 43344 | 21672
Subcontractor retention withheld / (released) |  | 0 | 21672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1486.4198 | 3983.6049 | 5767.3086 | 6837.5309 | 7194.2716 | 6837.5309 | 5767.3086 | 3983.6049 | 1486.4198 | -21672
Performance bond outstanding | bond % x contract, award to practical completion | 176000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1760000 | 1699643.3471 | 1537887.5171 | 1303703.7037 | 1026063.1001 | 733936.8999 | 456296.2963 | 222112.4829 | 60356.6529 | 0 | 0
Order intake (contract value in the award month) |  | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-P01 Office fit-out, 3,100 m2, Dublin 2 ¦ Quayside Capital Partners ¦ segment CF ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.25 | 0.375 | 0.5 | 0.625 | 0.75 | 0.875 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042969 | 0.15625 | 0.31641 | 0.5 | 0.68359 | 0.84375 | 0.95703 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042969 | 0.15625 | 0.31641 | 0.5 | 0.68359 | 0.84375 | 0.95703 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 89600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 10150 | 14350 | 16450 | 16450 | 14350 | 10150 | 3850 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12031.25 | 31718.75 | 44843.75 | 51406.25 | 51406.25 | 44843.75 | 31718.75 | 12031.25 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 134400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5775 | 15225 | 21525 | 24675 | 24675 | 21525 | 15225 | 5775 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721.875 | 1903.125 | 2690.625 | 3084.375 | 3084.375 | 2690.625 | 1903.125 | 721.875 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 39200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.375 | 4440.625 | 6278.125 | 7196.875 | 7196.875 | 6278.125 | 4440.625 | 1684.375 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24062.5 | 63437.5 | 89687.5 | 102812.5 | 102812.5 | 89687.5 | 63437.5 | 24062.5 | 0 | 0 | 0
Cost to date | opening + cost | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24062.5 | 87500 | 177187.5 | 280000 | 382812.5 | 472500 | 535937.5 | 560000 | 560000 | 560000 | 560000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000
Percentage complete | cost to date / cost at completion | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.297% | 15.62% | 31.64% | 50% | 68.36% | 84.38% | 95.7% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 647500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27822.2656 | 101171.875 | 204873.0469 | 323750 | 442626.9531 | 546328.125 | 619677.7344 | 647500 | 647500 | 647500 | 647500
REVENUE IN THE MONTH | change in revenue to date | 0 | 647500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27822.2656 | 73349.6094 | 103701.1719 | 118876.9531 | 118876.9531 | 103701.1719 | 73349.6094 | 27822.2656 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.7656 | 9912.1094 | 14013.6719 | 16064.4531 | 16064.4531 | 14013.6719 | 9912.1094 | 3759.7656 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 647500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27822.2656 | 101171.875 | 204873.0469 | 323750 | 442626.9531 | 546328.125 | 619677.7344 | 647500 | 647500 | 647500
Certified in the month |  | 0 | 647500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27822.2656 | 73349.6094 | 103701.1719 | 118876.9531 | 118876.9531 | 103701.1719 | 73349.6094 | 27822.2656 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 0 | 16187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391.1133 | 5058.5938 | 10243.6523 | 16187.5 | 22131.3477 | 27316.4062 | 30983.8867 | 16187.5 | 16187.5 | 16187.5
Retention withheld / (released) in the month |  | 0 | 16187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391.1133 | 3667.4805 | 5185.0586 | 5943.8477 | 5943.8477 | 5185.0586 | 3667.4805 | -14796.3867 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 0 | 631312.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26431.1523 | 69682.1289 | 98516.1133 | 112933.1055 | 112933.1055 | 98516.1133 | 69682.1289 | 42618.6523 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 85227.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3568.2056 | 9407.0874 | 13299.6753 | 15245.9692 | 15245.9692 | 13299.6753 | 9407.0874 | 5753.5181 | 0 | 0
Invoiced incl. VAT |  | 0 | 716539.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29999.3579 | 79089.2163 | 111815.7886 | 128179.0747 | 128179.0747 | 111815.7886 | 79089.2163 | 48372.1704 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 716539.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29999.3579 | 79089.2163 | 111815.7886 | 128179.0747 | 128179.0747 | 111815.7886 | 79089.2163 | 48372.1704 | 0
Trade receivable incl. VAT | opening + invoiced - received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29999.3579 | 79089.2163 | 111815.7886 | 128179.0747 | 128179.0747 | 111815.7886 | 79089.2163 | 48372.1704 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27822.2656 | 73349.6094 | 103701.1719 | 118876.9531 | 118876.9531 | 103701.1719 | 73349.6094 | 27822.2656 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27822.2656 | 73349.6094 | 103701.1719 | 118876.9531 | 118876.9531 | 103701.1719 | 73349.6094 | 27822.2656 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12031.25 | 43750 | 88593.75 | 140000 | 191406.25 | 236250 | 267968.75 | 280000 | 280000 | 280000 | 280000
Retention held from subcontractors |  | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601.5625 | 2187.5 | 4429.6875 | 7000 | 9570.3125 | 11812.5 | 13398.4375 | 14000 | 7000 | 7000 | 7000
Subcontractor retention withheld / (released) |  | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601.5625 | 1585.9375 | 2242.1875 | 2570.3125 | 2570.3125 | 2242.1875 | 1585.9375 | 601.5625 | -7000 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64750 | 64750 | 64750 | 64750 | 64750 | 64750 | 64750 | 64750 | 64750 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 647500 | 0 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 647500 | 619677.7344 | 546328.125 | 442626.9531 | 323750 | 204873.0469 | 101171.875 | 27822.2656 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 0 | 647500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-P02 Retail flagship fit-out, city centre ¦ Maple & Rowe Retail Ltd ¦ segment CF ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.75 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15625 | 0.5 | 0.84375 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15625 | 0.5 | 0.84375 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 8381.25 | 45258.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8381.25 | 18438.75 | 18438.75 | 8381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 26191.4062 | 141433.5938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26191.4062 | 57621.0938 | 57621.0938 | 26191.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 12571.875 | 67888.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12571.875 | 27658.125 | 27658.125 | 12571.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 1571.4844 | 8486.0156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571.4844 | 3457.2656 | 3457.2656 | 1571.4844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 3666.7969 | 19800.7031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3666.7969 | 8066.9531 | 8066.9531 | 3666.7969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 52382.8125 | 282867.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52382.8125 | 115242.1875 | 115242.1875 | 52382.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to date | opening + cost | 52382.8125 | 335250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52382.8125 | 167625 | 282867.1875 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250 | 335250
Percentage complete | cost to date / cost at completion | 15.62% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.62% | 50% | 84.38% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 60937.5 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60937.5 | 195000 | 329062.5 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000
REVENUE IN THE MONTH | change in revenue to date | 60937.5 | 329062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60937.5 | 134062.5 | 134062.5 | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 8554.6875 | 46195.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8554.6875 | 18820.3125 | 18820.3125 | 8554.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60937.5 | 195000 | 329062.5 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000
Certified in the month |  | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60937.5 | 134062.5 | 134062.5 | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 0 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046.875 | 9750 | 16453.125 | 9750 | 9750 | 9750 | 9750 | 9750 | 9750 | 9750 | 9750 | 9750
Retention withheld / (released) in the month |  | 0 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046.875 | 6703.125 | 6703.125 | -6703.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 0 | 380250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57890.625 | 127359.375 | 127359.375 | 67640.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 51333.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7815.2344 | 17193.5156 | 17193.5156 | 9131.4844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 0 | 431583.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65705.8594 | 144552.8906 | 144552.8906 | 76772.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 431583.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65705.8594 | 144552.8906 | 144552.8906 | 76772.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivable incl. VAT | opening + invoiced - received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65705.8594 | 144552.8906 | 144552.8906 | 76772.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60937.5 | 134062.5 | 134062.5 | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60937.5 | 134062.5 | 134062.5 | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 26191.4062 | 167625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26191.4062 | 83812.5 | 141433.5938 | 167625 | 167625 | 167625 | 167625 | 167625 | 167625 | 167625 | 167625 | 167625 | 167625
Retention held from subcontractors |  | 1309.5703 | 4190.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.5703 | 4190.625 | 7071.6797 | 8381.25 | 4190.625 | 4190.625 | 4190.625 | 4190.625 | 4190.625 | 4190.625 | 4190.625 | 4190.625 | 4190.625
Subcontractor retention withheld / (released) |  | 1309.5703 | 2881.0547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.5703 | 2881.0547 | 2881.0547 | 1309.5703 | -4190.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 39000 | 39000 | 39000 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 329062.5 | 0 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 329062.5 | 195000 | 60937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-P03 Hotel public areas refurbishment (phase 2) ¦ Tolka Hospitality Ltd ¦ segment CF ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.33333 | 0.5 | 0.66667 | 0.83333 | 1 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.5 | 0.74074 | 0.92593 | 1 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.5 | 0.74074 | 0.92593 | 1 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 53920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3994.0741 | 9985.1852 | 12980.7407 | 12980.7407 | 9985.1852 | 3994.0741 | 0 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 168500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12481.4815 | 31203.7037 | 40564.8148 | 40564.8148 | 31203.7037 | 12481.4815 | 0 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 80880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5991.1111 | 14977.7778 | 19471.1111 | 19471.1111 | 14977.7778 | 5991.1111 | 0 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 10110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748.8889 | 1872.2222 | 2433.8889 | 2433.8889 | 1872.2222 | 748.8889 | 0 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 23590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1747.4074 | 4368.5185 | 5679.0741 | 5679.0741 | 4368.5185 | 1747.4074 | 0 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 0 | 337000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24962.963 | 62407.4074 | 81129.6296 | 81129.6296 | 62407.4074 | 24962.963 | 0 | 0 | 0
Cost to date | opening + cost | 0 | 337000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24962.963 | 87370.3704 | 168500 | 249629.6296 | 312037.037 | 337000 | 337000 | 337000 | 337000
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000
Percentage complete | cost to date / cost at completion | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.407% | 25.93% | 50% | 74.07% | 92.59% | 100% | 100% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28888.8889 | 101111.1111 | 195000 | 288888.8889 | 361111.1111 | 390000 | 390000 | 390000 | 390000
REVENUE IN THE MONTH | change in revenue to date | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28888.8889 | 72222.2222 | 93888.8889 | 93888.8889 | 72222.2222 | 28888.8889 | 0 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3925.9259 | 9814.8148 | 12759.2593 | 12759.2593 | 9814.8148 | 3925.9259 | 0 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28888.8889 | 101111.1111 | 195000 | 288888.8889 | 361111.1111 | 390000 | 390000 | 390000
Certified in the month |  | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28888.8889 | 72222.2222 | 93888.8889 | 93888.8889 | 72222.2222 | 28888.8889 | 0 | 0
Retention held by the client | retention % x certified x unreleased share | 0 | 5850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866.6667 | 3033.3333 | 5850 | 8666.6667 | 10833.3333 | 5850 | 5850 | 5850
Retention withheld / (released) in the month |  | 0 | 5850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866.6667 | 2166.6667 | 2816.6667 | 2816.6667 | 2166.6667 | -4983.3333 | 0 | 0
Invoiced ex VAT (certified less retention movement) |  | 0 | 384150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28022.2222 | 70055.5556 | 91072.2222 | 91072.2222 | 70055.5556 | 33872.2222 | 0 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 51860.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783 | 9457.5 | 12294.75 | 12294.75 | 9457.5 | 4572.75 | 0 | 0
Invoiced incl. VAT |  | 0 | 436010.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31805.2222 | 79513.0556 | 103366.9722 | 103366.9722 | 79513.0556 | 38444.9722 | 0 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 436010.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15902.6111 | 55659.1389 | 91440.0139 | 103366.9722 | 91440.0139 | 58979.0139 | 19222.4861
Trade receivable incl. VAT | opening + invoiced - received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31805.2222 | 95415.6667 | 143123.5 | 155050.4583 | 131196.5417 | 78201.5 | 19222.4861 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28888.8889 | 72222.2222 | 93888.8889 | 93888.8889 | 72222.2222 | 28888.8889 | 0 | 0 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28888.8889 | 72222.2222 | 93888.8889 | 93888.8889 | 72222.2222 | 28888.8889 | 0 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 168500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12481.4815 | 43685.1852 | 84250 | 124814.8148 | 156018.5185 | 168500 | 168500 | 168500 | 168500
Retention held from subcontractors |  | 0 | 4212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.0741 | 2184.2593 | 4212.5 | 6240.7407 | 7800.9259 | 8425 | 4212.5 | 4212.5 | 4212.5
Subcontractor retention withheld / (released) |  | 0 | 4212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.0741 | 1560.1852 | 2028.2407 | 2028.2407 | 1560.1852 | 624.0741 | -4212.5 | 0 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 0 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 390000 | 0 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 361111.1111 | 288888.8889 | 195000 | 101111.1111 | 28888.8889 | 0 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS-P01 Deep retrofit of 32 council homes, Phase 4 ¦ Kildrum County Council ¦ segment PS ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.25 | 0.375
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042969 | 0.15625 | 0.31641
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042969 | 0.15625
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 30849.6094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4189.4531 | 11044.9219 | 15615.2344
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 132890.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18046.875 | 47578.125 | 67265.625
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 54580.0781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7412.1094 | 19541.0156 | 27626.9531
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 7119.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966.7969 | 2548.8281 | 3603.5156
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 11865.2344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1611.3281 | 4248.0469 | 6005.8594
COST INCURRED IN THE MONTH | sum of cost types | 0 | 237304.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32226.5625 | 84960.9375 | 120117.1875
Cost to date | opening + cost | 0 | 237304.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32226.5625 | 117187.5 | 237304.6875
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000
Percentage complete | cost to date / cost at completion | 0% | 31.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.297% | 15.62% | 31.64%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 269578.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36609.375 | 133125 | 269578.125
REVENUE IN THE MONTH | change in revenue to date | 0 | 269578.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36609.375 | 96515.625 | 136453.125
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 32273.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4382.8125 | 11554.6875 | 16335.9375
Billing basis (contract + approved + agreed variations) |  | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 133125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36609.375 | 133125
Certified in the month |  | 0 | 133125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36609.375 | 96515.625
Retention held by the client | retention % x certified x unreleased share | 0 | 6656.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830.4688 | 6656.25
Retention withheld / (released) in the month |  | 0 | 6656.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830.4688 | 4825.7812
Invoiced ex VAT (certified less retention movement) |  | 0 | 126468.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34778.9062 | 91689.8438
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT |  | 0 | 126468.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34778.9062 | 91689.8438
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 34778.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34778.9062
Trade receivable incl. VAT | opening + invoiced - received | 0 | 91689.8438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34778.9062 | 91689.8438
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 136453.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36609.375 | 96515.625 | 136453.125
Contract asset (work done, not yet certified) |  | 0 | 136453.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36609.375 | 96515.625 | 136453.125
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 132890.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18046.875 | 65625 | 132890.625
Retention held from subcontractors |  | 0 | 6644.5312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902.3438 | 3281.25 | 6644.5312
Subcontractor retention withheld / (released) |  | 0 | 6644.5312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902.3438 | 2378.9062 | 3363.2812
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 85200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85200 | 85200 | 85200 | 85200
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 852000 | 582421.875 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 852000 | 815390.625 | 718875 | 582421.875
Order intake (contract value in the award month) |  | 0 | 852000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852000 | 0 | 0 | 0
CF-P04 Office fit-out, 1,200 m2, Sandyford ¦ Brightlane Software Ltd ¦ segment CF ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.6 | 0.8 | 1 | 1 | 1
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.104 | 0.352 | 0.648 | 0.896 | 1 | 1 | 1
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.104 | 0.352 | 0.648 | 0.896 | 1 | 1
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 24880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2587.52 | 6170.24 | 7364.48 | 6170.24 | 2587.52 | 0 | 0
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 77750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8086 | 19282 | 23014 | 19282 | 8086 | 0 | 0
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 37320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.28 | 9255.36 | 11046.72 | 9255.36 | 3881.28 | 0 | 0
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 4665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.16 | 1156.92 | 1380.84 | 1156.92 | 485.16 | 0 | 0
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 10885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132.04 | 2699.48 | 3221.96 | 2699.48 | 1132.04 | 0 | 0
COST INCURRED IN THE MONTH | sum of cost types | 0 | 155500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16172 | 38564 | 46028 | 38564 | 16172 | 0 | 0
Cost to date | opening + cost | 0 | 155500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16172 | 54736 | 100764 | 139328 | 155500 | 155500 | 155500
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500 | 155500
Percentage complete | cost to date / cost at completion | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.4% | 35.2% | 64.8% | 89.6% | 100% | 100% | 100%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720 | 63360 | 116640 | 161280 | 180000 | 180000 | 180000
REVENUE IN THE MONTH | change in revenue to date | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720 | 44640 | 53280 | 44640 | 18720 | 0 | 0
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2548 | 6076 | 7252 | 6076 | 2548 | 0 | 0
Billing basis (contract + approved + agreed variations) |  | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720 | 63360 | 116640 | 161280 | 180000 | 180000
Certified in the month |  | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720 | 44640 | 53280 | 44640 | 18720 | 0
Retention held by the client | retention % x certified x unreleased share | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936 | 3168 | 5832 | 8064 | 4500 | 4500
Retention withheld / (released) in the month |  | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936 | 2232 | 2664 | 2232 | -3564 | 0
Invoiced ex VAT (certified less retention movement) |  | 0 | 175500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17784 | 42408 | 50616 | 42408 | 22284 | 0
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 23692.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400.84 | 5725.08 | 6833.16 | 5725.08 | 3008.34 | 0
Invoiced incl. VAT |  | 0 | 199192.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20184.84 | 48133.08 | 57449.16 | 48133.08 | 25292.34 | 0
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 199192.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20184.84 | 48133.08 | 57449.16 | 48133.08 | 25292.34
Trade receivable incl. VAT | opening + invoiced - received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20184.84 | 48133.08 | 57449.16 | 48133.08 | 25292.34 | 0
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720 | 44640 | 53280 | 44640 | 18720 | 0 | 0
Contract asset (work done, not yet certified) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720 | 44640 | 53280 | 44640 | 18720 | 0 | 0
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 77750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8086 | 27368 | 50382 | 69664 | 77750 | 77750 | 77750
Retention held from subcontractors |  | 0 | 1943.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404.3 | 1368.4 | 2519.1 | 3483.2 | 3887.5 | 1943.75 | 1943.75
Subcontractor retention withheld / (released) |  | 0 | 1943.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404.3 | 964.1 | 1150.7 | 964.1 | 404.3 | -1943.75 | 0
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 180000 | 0 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 161280 | 116640 | 63360 | 18720 | 0 | 0 | 0
Order intake (contract value in the award month) |  | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF-P05 Office refurbishment and M&E upgrade, Dublin 2 ¦ Merrion Row Holdings Ltd ¦ segment CF ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.28571 | 0.42857 | 0.57143 | 0.71429
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055394 | 0.19825 | 0.39359 | 0.60641 | 0.80175
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055394 | 0.19825 | 0.39359 | 0.60641
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 42588.9213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2942.5073 | 7588.5714 | 10376.2099 | 11305.4227 | 10376.2099
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 133090.379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9195.3353 | 23714.2857 | 32425.656 | 35329.4461 | 32425.656
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 63883.3819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413.7609 | 11382.8571 | 15564.3149 | 16958.1341 | 15564.3149
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 7985.4227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551.7201 | 1422.8571 | 1945.5394 | 2119.7668 | 1945.5394
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 18632.6531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287.3469 | 3320 | 4539.5918 | 4946.1224 | 4539.5918
COST INCURRED IN THE MONTH | sum of cost types | 0 | 266180.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18390.6706 | 47428.5714 | 64851.312 | 70658.8921 | 64851.312
Cost to date | opening + cost | 0 | 266180.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18390.6706 | 65819.242 | 130670.5539 | 201329.4461 | 266180.758
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000 | 332000
Percentage complete | cost to date / cost at completion | 0% | 80.17% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.539% | 19.83% | 39.36% | 60.64% | 80.17%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 307871.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271.137 | 76128.2799 | 151137.0262 | 232862.9738 | 307871.7201
REVENUE IN THE MONTH | change in revenue to date | 0 | 307871.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271.137 | 54857.1429 | 75008.7464 | 81725.9475 | 75008.7464
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 41690.9621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880.4665 | 7428.5714 | 10157.4344 | 11067.0554 | 10157.4344
Billing basis (contract + approved + agreed variations) |  | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 232862.9738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271.137 | 76128.2799 | 151137.0262 | 232862.9738
Certified in the month |  | 0 | 232862.9738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271.137 | 54857.1429 | 75008.7464 | 81725.9475
Retention held by the client | retention % x certified x unreleased share | 0 | 11643.1487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.5569 | 3806.414 | 7556.8513 | 11643.1487
Retention withheld / (released) in the month |  | 0 | 11643.1487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.5569 | 2742.8571 | 3750.4373 | 4086.2974
Invoiced ex VAT (certified less retention movement) |  | 0 | 221219.8251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20207.5802 | 52114.2857 | 71258.309 | 77639.6501
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 29864.6764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2728.0233 | 7035.4286 | 9619.8717 | 10481.3528
Invoiced incl. VAT |  | 0 | 251084.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22935.6035 | 59149.7143 | 80878.1808 | 88121.0029
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 162963.4985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22935.6035 | 59149.7143 | 80878.1808
Trade receivable incl. VAT | opening + invoiced - received | 0 | 88121.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22935.6035 | 59149.7143 | 80878.1808 | 88121.0029
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 75008.7464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271.137 | 54857.1429 | 75008.7464 | 81725.9475 | 75008.7464
Contract asset (work done, not yet certified) |  | 0 | 75008.7464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271.137 | 54857.1429 | 75008.7464 | 81725.9475 | 75008.7464
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 133090.379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9195.3353 | 32909.621 | 65335.277 | 100664.723 | 133090.379
Retention held from subcontractors |  | 0 | 6654.519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459.7668 | 1645.481 | 3266.7638 | 5033.2362 | 6654.519
Subcontractor retention withheld / (released) |  | 0 | 6654.519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459.7668 | 1185.7143 | 1621.2828 | 1766.4723 | 1621.2828
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 38400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38400 | 38400 | 38400 | 38400 | 38400 | 38400
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 384000 | 76128.2799 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 362728.863 | 307871.7201 | 232862.9738 | 151137.0262 | 76128.2799
Order intake (contract value in the award month) |  | 0 | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000 | 0 | 0 | 0 | 0 | 0
CF-P06 Hotel refurbishment, 48 rooms, Galway ¦ Corrib Bay Hotels Ltd ¦ segment CF ¦ Pipeline
Programme position (elapsed share of duration) | effective dates, Project_Register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.25 | 0.375 | 0.5
S-curve: cumulative share of cost at month end | 3x^2 - 2x^3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042969 | 0.15625 | 0.31641 | 0.5
S-curve: cumulative share at prior month end |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042969 | 0.15625 | 0.31641
Cost: own labour (allocated at standard rate) | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 22440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.4375 | 5084.0625 | 7187.8125 | 8239.6875
Cost: subcontractors | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 70125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6026.3672 | 15887.6953 | 22461.9141 | 25749.0234
Cost: materials | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 33660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2892.6562 | 7626.0938 | 10781.7188 | 12359.5312
Cost: plant hire | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 4207.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361.582 | 953.2617 | 1347.7148 | 1544.9414
Cost: preliminaries and site services | A: cost ledger; F: remaining cost x S-curve x mix | 0 | 9817.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843.6914 | 2224.2773 | 3144.668 | 3604.8633
COST INCURRED IN THE MONTH | sum of cost types | 0 | 140250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12052.7344 | 31775.3906 | 44923.8281 | 51498.0469
Cost to date | opening + cost | 0 | 140250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12052.7344 | 43828.125 | 88751.9531 | 140250
Estimated cost at completion | A: cost to date + cost report; F: Project_Register | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500 | 280500
Percentage complete | cost to date / cost at completion | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.297% | 15.62% | 31.64% | 50%
Variations approved to date | Variations register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variations raised, not yet decided (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending variations past their expected decision date (claimed) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract revenue estimate | contract + approved + policy x undecided + agreed x decided | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000
Revenue recognised to date | A: ledger; F: % complete x contract revenue | 0 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921.875 | 50625 | 102515.625 | 162000
REVENUE IN THE MONTH | change in revenue to date | 0 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921.875 | 36703.125 | 51890.625 | 59484.375
Onerous contract provision | max(0, cost at completion - contract revenue) x (1 - % complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous provision (charge) / release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS PROFIT IN THE MONTH | revenue - cost + provision movement | 0 | 21750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1869.1406 | 4927.7344 | 6966.7969 | 7986.3281
Billing basis (contract + approved + agreed variations) |  | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000
Gross value certified to date | A: certificates; F: prior-month % complete x billing basis; final account in full | 0 | 102515.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921.875 | 50625 | 102515.625
Certified in the month |  | 0 | 102515.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921.875 | 36703.125 | 51890.625
Retention held by the client | retention % x certified x unreleased share | 0 | 3075.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.6562 | 1518.75 | 3075.4688
Retention withheld / (released) in the month |  | 0 | 3075.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.6562 | 1101.0938 | 1556.7188
Invoiced ex VAT (certified less retention movement) |  | 0 | 99440.1562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13504.2188 | 35602.0312 | 50333.9062
Output VAT on invoices | 0% where the council accounts under the reverse charge | 0 | 13424.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823.0695 | 4806.2742 | 6795.0773
Invoiced incl. VAT |  | 0 | 112864.5773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15327.2883 | 40408.3055 | 57128.9836
Cash received incl. VAT | A: bank; F: opening + invoiced - closing at payment days | 0 | 35531.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7663.6441 | 27867.7969
Trade receivable incl. VAT | opening + invoiced - received | 0 | 77333.1363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15327.2883 | 48071.9496 | 77333.1363
Contract position: revenue to date less certified | + contract asset / - contract liability | 0 | 59484.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921.875 | 36703.125 | 51890.625 | 59484.375
Contract asset (work done, not yet certified) |  | 0 | 59484.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13921.875 | 36703.125 | 51890.625 | 59484.375
Contract liability (certified ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontract cost to date |  | 0 | 70125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6026.3672 | 21914.0625 | 44375.9766 | 70125
Retention held from subcontractors |  | 0 | 3506.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301.3184 | 1095.7031 | 2218.7988 | 3506.25
Subcontractor retention withheld / (released) |  | 0 | 3506.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301.3184 | 794.3848 | 1123.0957 | 1287.4512
Performance bond outstanding | bond % x contract, award to practical completion | 0 | 32400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 32400 | 32400 | 32400 | 32400
Remaining contract revenue (secured from award; pipeline weighted throughout) |  | 324000 | 162000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 310078.125 | 273375 | 221484.375 | 162000
Order intake (contract value in the award month) |  | 0 | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324000 | 0 | 0 | 0 | 0
TOTALS: COMMERCIAL FIT-OUT CONTRACTS
Revenue | sum of contracts | 3290084.0536 | 2461146.1065 | 158017.94 | 139314.06 | 114056.91 | 103444.17 | 136039.43 | 218730.2 | 343193.12 | 346480.13 | 441839.7972 | 466575.4467 | 428352.9879 | 394039.8618 | 378959.3609 | 314292.3837 | 181694.5168 | 132590.0608 | 191099.1753 | 231485.842 | 242230.0608 | 220122.9686 | 170130.1724 | 130431.8714 | 133616.5725 | 134493.1214
Direct cost | sum of contracts | 2846148.5104 | 2120386.2276 | 126726.14 | 105238.29 | 84756.08 | 88882.17 | 143323.67 | 211431.66 | 298743.67 | 313658.41 | 387432.686 | 397071.6389 | 359754.9489 | 329129.1466 | 323212.277 | 269256.2134 | 156486.9792 | 114650.463 | 165219.9074 | 200114.1296 | 209381.1296 | 190263.578 | 147070.7688 | 112798.7026 | 115582.7203 | 116349.3588
Own labour (allocated at standard rate) | sum of contracts | 458277.4473 | 339261.7964 | 20871.48 | 17684.27 | 12532.8 | 13397.14 | 23717.38 | 33104.65 | 48038.33 | 53189.25 | 61989.2298 | 63531.4622 | 57560.7918 | 52660.6635 | 51713.9643 | 43080.9941 | 25037.9167 | 18344.0741 | 26435.1852 | 32018.2607 | 33500.9807 | 30442.1725 | 23531.323 | 18047.7924 | 18493.2352 | 18615.8974
Subcontractors | sum of contracts | 1415648.8402 | 1060193.1138 | 61951.26 | 52022.57 | 43581.75 | 44923.87 | 70640.96 | 103303.04 | 144767.12 | 157764.06 | 193716.343 | 198535.8195 | 179877.4744 | 164564.5733 | 161606.1385 | 134628.1067 | 78243.4896 | 57325.2315 | 82609.9537 | 100057.0648 | 104690.5648 | 95131.789 | 73535.3844 | 56399.3513 | 57791.3601 | 58174.6794
Materials | sum of contracts | 686085.5409 | 508892.6946 | 31369.52 | 25055.71 | 20188.67 | 21409.7 | 34121.09 | 53573.77 | 75692.94 | 71060.92 | 92983.8446 | 95297.1933 | 86341.1877 | 78990.9952 | 77570.9465 | 64621.4912 | 37556.875 | 27516.1111 | 39652.7778 | 48027.3911 | 50251.4711 | 45663.2587 | 35296.9845 | 27071.6886 | 27739.8529 | 27923.8461
Plant hire | sum of contracts | 85303.6826 | 63611.5868 | 3705.32 | 3404.59 | 2384.07 | 2574.07 | 4285.88 | 6672.71 | 8944.96 | 9130.43 | 11622.9806 | 11912.1492 | 10792.6485 | 9873.8744 | 9696.3683 | 8077.6864 | 4694.6094 | 3439.5139 | 4956.5972 | 6003.4239 | 6281.4339 | 5707.9073 | 4412.1231 | 3383.9611 | 3467.4816 | 3490.4808
Preliminaries and site services | sum of contracts | 200832.9994 | 148427.0359 | 8828.56 | 7071.15 | 6068.79 | 6577.39 | 10558.36 | 14777.49 | 21300.32 | 22513.75 | 27120.288 | 27795.0147 | 25182.8464 | 23039.0403 | 22624.8594 | 18847.9349 | 10954.0885 | 8025.5324 | 11565.3935 | 14007.9891 | 14656.6791 | 13318.4505 | 10294.9538 | 7895.9092 | 8090.7904 | 8144.4551
Onerous provision movement | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gross profit | sum of contracts | 443935.5432 | 340759.8789 | 31291.8 | 34075.77 | 29300.83 | 14562 | -7284.24 | 7298.54 | 44449.45 | 32821.72 | 54407.1112 | 69503.8077 | 68598.039 | 64910.7153 | 55747.0839 | 45036.1703 | 25207.5376 | 17939.5978 | 25879.2679 | 31371.7124 | 32848.9311 | 29859.3907 | 23059.4036 | 17633.1688 | 18033.8523 | 18143.7625
Contract assets | sum of contracts | 388399.8618 | 134493.1214 | 161192.09 | 158393.89 | 121583.21 | 124144.17 | 144457.12 | 223683.56 | 345665.19 | 368274.07 | 486233.865 | 492779.1247 | 440871.9834 | 388399.8618 | 378959.3609 | 314292.3837 | 181694.5168 | 132590.0608 | 191099.1753 | 231485.842 | 242230.0608 | 220122.9686 | 170130.1724 | 130431.8714 | 133616.5725 | 134493.1214
Contract liabilities | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provisions | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention receivable | sum of contracts | 106279.0694 | 91720.4924 | 33848.6205 | 40954.2335 | 48497.613 | 27766.7735 | 33235.5975 | 40210.7855 | 50668.043 | 65048.1697 | 78761.678 | 98581.2258 | 119313.7674 | 106279.0694 | 113056.0184 | 130187.5307 | 130523.2429 | 87765.4688 | 93817.194 | 101927.7083 | 111624.2227 | 121857.9479 | 131419.6519 | 117032.4452 | 118319.9763 | 91720.4924
Retention withheld / (released) | sum of contracts | 81180.3914 | -14558.577 | 8749.9425 | 7105.613 | 7543.3795 | -20730.8395 | 5468.824 | 6975.188 | 10457.2575 | 14380.1267 | 13713.5083 | 19819.5479 | 20732.5416 | -13034.698 | 6776.949 | 17131.5123 | 335.7122 | -42757.7742 | 6051.7253 | 8110.5143 | 9696.5143 | 10233.7253 | 9561.704 | -14387.2067 | 1287.5311 | -26599.4839
Subcontractor retention payable | sum of contracts | 59364.1085 | 48667.9481 | 16877.8665 | 19478.995 | 21658.0825 | 13528.0605 | 17060.1085 | 22225.2605 | 29463.6165 | 37351.8195 | 47037.6367 | 56964.4276 | 65958.3013 | 59364.1085 | 63289.6403 | 70021.0456 | 63790.1911 | 45227.1122 | 49357.6099 | 54360.4631 | 59594.9914 | 64351.5808 | 68028.35 | 59635.8176 | 60581.6356 | 48667.9481
Subcontractor retention withheld / (released) | sum of contracts | 45583.805 | -10696.1604 | 3097.563 | 2601.1285 | 2179.0875 | -8130.022 | 3532.048 | 5165.152 | 7238.356 | 7888.203 | 9685.8172 | 9926.791 | 8993.8737 | -6594.1928 | 3925.5318 | 6731.4053 | -6230.8545 | -18563.0789 | 4130.4977 | 5002.8532 | 5234.5282 | 4756.5894 | 3676.7692 | -8392.5324 | 945.818 | -11913.6875
Invoiced ex VAT | sum of contracts | 2998676.8003 | 2729611.424 | 166248.9075 | 135006.647 | 143324.2105 | 121614.0495 | 110257.656 | 132528.572 | 210754.2325 | 309491.1233 | 310166.494 | 440210.6391 | 459527.5876 | 459546.6814 | 381622.9129 | 361827.8486 | 313956.6715 | 224452.2909 | 126538.3355 | 182988.661 | 221789.3277 | 231996.3355 | 210561.2646 | 184517.379 | 129144.3403 | 160216.0564
Output VAT | sum of contracts | 404821.368 | 368497.5422 | 22443.6025 | 18225.8973 | 19348.7684 | 16417.8967 | 14884.7836 | 17891.3572 | 28451.8214 | 41781.3016 | 41872.4767 | 59428.4363 | 62036.2243 | 62038.802 | 51519.0932 | 48846.7596 | 42384.1507 | 30301.0593 | 17082.6753 | 24703.4692 | 29941.5592 | 31319.5053 | 28425.7707 | 24909.8462 | 17434.4859 | 21629.1676
Invoiced incl. VAT | sum of contracts | 3403498.1684 | 3098108.9662 | 188692.51 | 153232.5443 | 162672.9789 | 138031.9462 | 125142.4396 | 150419.9292 | 239206.0539 | 351272.4249 | 352038.9707 | 499639.0753 | 521563.8119 | 521585.4834 | 433142.0061 | 410674.6081 | 356340.8222 | 254753.3502 | 143621.0108 | 207692.1303 | 251730.8869 | 263315.8408 | 238987.0354 | 209427.2252 | 146578.8262 | 181845.224
Cash received | sum of contracts | 3012018.731 | 3507935.7669 | 217597.9 | 205867.58 | 125893.45 | 159514.63 | 155797.28 | 137038.57 | 130050.73 | 247704.81 | 299690.0635 | 333679.0865 | 480332.0005 | 518852.6305 | 526062.7079 | 446573.6796 | 433060.7306 | 379338.5052 | 281751.3407 | 127718.3997 | 183838.2136 | 239803.9286 | 263315.8408 | 250913.9937 | 222297.6227 | 153260.8037
Trade receivables incl. VAT | sum of contracts | 611876.1774 | 202049.3767 | 191491.35 | 138856.3144 | 175635.8433 | 154153.1595 | 123498.319 | 136879.6782 | 246035.0021 | 349602.6171 | 401951.5243 | 567911.5131 | 609143.3246 | 611876.1774 | 518955.4757 | 483056.4042 | 406336.4957 | 281751.3407 | 143621.0108 | 223594.7414 | 291487.4147 | 314999.3269 | 290670.5215 | 249183.753 | 173464.9565 | 202049.3767
Performance bonds outstanding | sum of contracts | 236000 | 70800 | 98000 | 216000 | 216000 | 118000 | 212000 | 212000 | 251000 | 315000 | 315000 | 315000 | 354000 | 236000 | 261750 | 261750 | 206750 | 103750 | 121750 | 121750 | 160150 | 192550 | 192550 | 88800 | 70800 | 70800
Order book (remaining contract revenue) | sum of contracts | 2699274.3864 | 238128.2799 | 2503085.5 | 3557021.44 | 3455664.53 | 3355670.36 | 4168880.93 | 3982000.73 | 4063857.61 | 4407027.48 | 3967617.6828 | 3510237.2361 | 3087674.2482 | 2699274.3864 | 2320315.0255 | 2006022.6418 | 1824328.125 | 1691738.0642 | 1500638.8889 | 1269153.0469 | 1026922.9861 | 806800.0175 | 636669.8451 | 506237.9738 | 372621.4012 | 238128.2799
Order intake | sum of contracts | 3540000 | 1925500 | 0 | 1180000 | 0 | 0 | 940000 | 0 | 390000 | 640000 | 0 | 0 | 390000 | 0 | 647500 | 0 | 390000 | 0 | 180000 | 0 | 384000 | 324000 | 0 | 0 | 0 | 0
TOTALS: PUBLIC SECTOR RETROFIT CONTRACTS
Revenue | sum of contracts | 1792491.938 | 2172433.867 | 236014.85 | 188104.4 | 105874.14 | 53699.29 | 33347.91 | 99114.7 | 149061 | 179277.28 | 202963.0682 | 204379.2995 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 198365.2049 | 156872.2779 | 136453.125
Direct cost | sum of contracts | 1530176.9142 | 1908961.4033 | 205399.87 | 152554.55 | 84207.19 | 41672.02 | 29255.21 | 85890.76 | 132110.44 | 152267.13 | 175973.0186 | 175973.0186 | 161704.936 | 133168.7709 | 90364.5231 | 33292.1927 | 53086.4198 | 142271.6049 | 205975.3086 | 244197.5309 | 256938.2716 | 244197.5309 | 205975.3086 | 174498.1674 | 138047.3573 | 120117.1875
Own labour (allocated at standard rate) | sum of contracts | 197930.7867 | 248164.9824 | 25139.45 | 19305.56 | 11616.66 | 6003.07 | 3765.57 | 10550.21 | 15618.82 | 21844.88 | 22876.4924 | 22876.4924 | 21021.6417 | 17311.9402 | 11747.388 | 4327.9851 | 6901.2346 | 18495.3086 | 26776.7901 | 31745.679 | 33401.9753 | 31745.679 | 26776.7901 | 22684.7618 | 17946.1564 | 15615.2344
Subcontractors | sum of contracts | 854155.3568 | 1069018.3858 | 115846.57 | 86983.55 | 45995.01 | 22494.22 | 16519.7 | 46285.24 | 75715.48 | 82096.53 | 98544.8904 | 98544.8904 | 90554.7642 | 74574.5117 | 50604.1329 | 18643.6279 | 29728.3951 | 79672.0988 | 115346.1728 | 136750.6173 | 143885.4321 | 136750.6173 | 115346.1728 | 97718.9738 | 77306.5201 | 67265.625
Materials | sum of contracts | 354865.3512 | 439061.1228 | 47365.64 | 34162.6 | 19879.12 | 10038.5 | 6470.19 | 22278.85 | 29929.2 | 35972.71 | 40473.7943 | 40473.7943 | 37192.1353 | 30628.8173 | 20783.8403 | 7657.2043 | 12209.8765 | 32722.4691 | 47374.321 | 56165.4321 | 59095.8025 | 56165.4321 | 47374.321 | 40134.5785 | 31750.8922 | 27626.9531
Plant hire | sum of contracts | 46019.8123 | 57268.8421 | 5935.65 | 4596.24 | 2738.29 | 1192.81 | 914.62 | 2460.24 | 4183.21 | 4594.16 | 5279.1906 | 5279.1906 | 4851.1481 | 3995.0631 | 2710.9357 | 998.7658 | 1592.5926 | 4268.1481 | 6179.2593 | 7325.9259 | 7708.1481 | 7325.9259 | 6179.2593 | 5234.945 | 4141.4207 | 3603.5156
Preliminaries and site services | sum of contracts | 77205.6072 | 95448.0702 | 11112.56 | 7506.6 | 3978.11 | 1943.42 | 1585.13 | 4316.22 | 6663.73 | 7758.85 | 8798.6509 | 8798.6509 | 8085.2468 | 6658.4385 | 4518.2262 | 1664.6096 | 2654.321 | 7113.5802 | 10298.7654 | 12209.8765 | 12846.9136 | 12209.8765 | 10298.7654 | 8724.9084 | 6902.3679 | 6005.8594
Onerous provision movement | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gross profit | sum of contracts | 262315.0238 | 263472.4637 | 30614.98 | 35549.85 | 21666.95 | 12027.27 | 4092.7 | 13223.94 | 16950.56 | 27010.15 | 26990.0495 | 28406.2809 | 25106.4189 | 20675.8744 | 14030.0576 | 5168.9686 | 7270.2332 | 19484.225 | 28208.5048 | 33443.0727 | 35187.9287 | 33443.0727 | 28208.5048 | 23867.0375 | 18824.9207 | 16335.9375
Contract assets | sum of contracts | 153844.6453 | 136453.125 | 240499.71 | 181604.54 | 110689.2 | 49111.86 | 33347.91 | 99114.7 | 150269.14 | 177174.54 | 205472.8957 | 203294.7098 | 186811.355 | 153844.6453 | 104394.5807 | 38461.1613 | 60356.6529 | 161755.8299 | 234183.8134 | 277640.6036 | 292126.2003 | 277640.6036 | 234183.8134 | 198365.2049 | 156872.2779 | 136453.125
Contract liabilities | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provisions | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention receivable | sum of contracts | 80472.7306 | 84447.625 | 26041.123 | 38391.1015 | 47230.5755 | 52994.407 | 27725 | 29392.3955 | 34287.7235 | 41906.3175 | 50639.5531 | 60967.4274 | 71132.1629 | 80472.7306 | 88164.9629 | 93384.6919 | 61516.375 | 64534.2076 | 44896.9991 | 56606.1898 | 70488.22 | 85094.53 | 98976.5602 | 110685.7509 | 120604.0111 | 84447.625
Retention withheld / (released) | sum of contracts | 63885.6371 | 3974.8944 | 9454.0295 | 12349.9785 | 8839.474 | 5763.8315 | -25269.407 | 1667.3955 | 4895.328 | 7618.594 | 8733.2356 | 10327.8743 | 10164.7355 | 9340.5677 | 7692.2323 | 5219.729 | -31868.3169 | 3017.8326 | -19637.2085 | 11709.1907 | 13882.0302 | 14606.31 | 13882.0302 | 11709.1907 | 9918.2602 | -36156.3861
Subcontractor retention payable | sum of contracts | 42243.2848 | 44618.6254 | 18429.33 | 22778.5075 | 25078.258 | 26202.969 | 13927.4695 | 16241.7315 | 20027.5055 | 24132.332 | 29059.5765 | 33986.821 | 38514.5593 | 42243.2848 | 44773.4915 | 45705.6729 | 30889.9984 | 34873.6034 | 27539.4275 | 34376.9584 | 41571.23 | 48408.7609 | 54176.0695 | 59062.0182 | 62927.3442 | 44618.6254
Subcontractor retention withheld / (released) | sum of contracts | 29606.2833 | 2375.3406 | 5792.3285 | 4349.1775 | 2299.7505 | 1124.711 | -12275.4995 | 2314.262 | 3785.774 | 4104.8265 | 4927.2445 | 4927.2445 | 4527.7382 | 3728.7256 | 2530.2066 | 932.1814 | -14815.6744 | 3983.6049 | -7334.1759 | 6837.5309 | 7194.2716 | 6837.5309 | 5767.3086 | 4885.9487 | 3865.326 | -18308.7188
Invoiced ex VAT | sum of contracts | 1768327.1055 | 2185850.493 | 179626.5605 | 234649.5915 | 167950.006 | 109512.7985 | 74381.267 | 31680.5145 | 93011.232 | 144753.286 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 57338.8203 | 181393.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 188446.9447 | 193028.6641
Output VAT | sum of contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced incl. VAT | sum of contracts | 1768327.1055 | 2185850.493 | 179626.5605 | 234649.5915 | 167950.006 | 109512.7985 | 74381.267 | 31680.5145 | 93011.232 | 144753.286 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 57338.8203 | 181393.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 188446.9447 | 193028.6641
Cash received | sum of contracts | 1747053.5283 | 2170292.6162 | 144766.1 | 163070.87 | 253854.78 | 178666.93 | 112812.06 | 68015.76 | 33354.11 | 89759.77 | 147462.086 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 57338.8203 | 181393.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 188446.9447
Trade receivables incl. VAT | sum of contracts | 177470.7872 | 193028.6641 | 191057.6705 | 262636.392 | 176731.618 | 107577.4865 | 69146.6935 | 32811.448 | 92468.57 | 147462.086 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 57338.8203 | 181393.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 188446.9447 | 193028.6641
Performance bonds outstanding | sum of contracts | 308000 | 85200 | 108000 | 108000 | 108000 | 240000 | 132000 | 132000 | 132000 | 308000 | 308000 | 308000 | 308000 | 308000 | 308000 | 308000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 261200 | 261200 | 261200 | 85200
Order book (remaining contract revenue) | sum of contracts | 2754855.742 | 582421.875 | 1179977.83 | 1006773.43 | 900899.29 | 2172000 | 2138652.09 | 2051687.39 | 1902626.39 | 3500649.11 | 3297686.0418 | 3095511.7423 | 2908700.3873 | 2754855.742 | 2650461.1613 | 2612000 | 2551643.3471 | 2389887.5171 | 2155703.7037 | 1878063.1001 | 1585936.8999 | 1308296.2963 | 1074112.4829 | 875747.2779 | 718875 | 582421.875
Order intake | sum of contracts | 3080000 | 852000 | 0 | 0 | 0 | 1320000 | 0 | 0 | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852000 | 0 | 0 | 0
TOTALS: ALL NAMED CONTRACTS
Revenue | commercial + public sector | 5082575.9916 | 4633579.9735 | 394032.79 | 327418.46 | 219931.05 | 157143.46 | 169387.34 | 317844.9 | 492254.12 | 525757.41 | 644802.8654 | 670954.7462 | 615164.3429 | 547884.5071 | 483353.9416 | 352753.545 | 242051.1697 | 294345.8907 | 425282.9888 | 509126.4456 | 534356.261 | 497763.5722 | 404313.9858 | 328797.0763 | 290488.8505 | 270946.2464
Direct cost | commercial + public sector | 4376325.4246 | 4029347.6309 | 332126.01 | 257792.84 | 168963.27 | 130554.19 | 172578.88 | 297322.42 | 430854.11 | 465925.54 | 563405.7047 | 573044.6576 | 521459.8849 | 462297.9174 | 413576.8001 | 302548.4061 | 209573.3989 | 256922.0679 | 371195.216 | 444311.6605 | 466319.4012 | 434461.1088 | 353046.0774 | 287296.87 | 253630.0775 | 236466.5463
Own labour (allocated at standard rate) | commercial + public sector | 656208.234 | 587426.7788 | 46010.93 | 36989.83 | 24149.46 | 19400.21 | 27482.95 | 43654.86 | 63657.15 | 75034.13 | 84865.7222 | 86407.9547 | 78582.4335 | 69972.6037 | 63461.3523 | 47408.9792 | 31939.1512 | 36839.3827 | 53211.9753 | 63763.9398 | 66902.956 | 62187.8515 | 50308.1131 | 40732.5542 | 36439.3917 | 34231.1318
Subcontractors | commercial + public sector | 2269804.197 | 2129211.4996 | 177797.83 | 139006.12 | 89576.76 | 67418.09 | 87160.66 | 149588.28 | 220482.6 | 239860.59 | 292261.2335 | 297080.7099 | 270432.2386 | 239139.085 | 212210.2714 | 153271.7346 | 107971.8846 | 136997.3302 | 197956.1265 | 236807.6821 | 248575.9969 | 231882.4063 | 188881.5572 | 154118.3251 | 135097.8802 | 125440.3044
Materials | commercial + public sector | 1040950.8921 | 947953.8174 | 78735.16 | 59218.31 | 40067.79 | 31448.2 | 40591.28 | 75852.62 | 105622.14 | 107033.63 | 133457.6389 | 135770.9876 | 123533.323 | 109619.8125 | 98354.7868 | 72278.6955 | 49766.7515 | 60238.5802 | 87027.0988 | 104192.8232 | 109347.2736 | 101828.6908 | 82671.3055 | 67206.2671 | 59490.745 | 55550.7992
Plant hire | commercial + public sector | 131323.4949 | 120880.4289 | 9640.97 | 8000.83 | 5122.36 | 3766.88 | 5200.5 | 9132.95 | 13128.17 | 13724.59 | 16902.1711 | 17191.3397 | 15643.7965 | 13868.9375 | 12407.304 | 9076.4522 | 6287.202 | 7707.662 | 11135.8565 | 13329.3498 | 13989.582 | 13033.8333 | 10591.3823 | 8618.9061 | 7608.9023 | 7093.9964
Preliminaries and site services | commercial + public sector | 278038.6066 | 243875.1061 | 19941.12 | 14577.75 | 10046.9 | 8520.81 | 12143.49 | 19093.71 | 27964.05 | 30272.6 | 35918.939 | 36593.6657 | 33268.0932 | 29697.4788 | 27143.0855 | 20512.5446 | 13608.4095 | 15139.1127 | 21864.159 | 26217.8656 | 27503.5927 | 25528.327 | 20593.7192 | 16620.8176 | 14993.1583 | 14150.3145
Onerous provision movement | commercial + public sector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gross profit | commercial + public sector | 706250.567 | 604232.3426 | 61906.78 | 69625.62 | 50967.78 | 26589.27 | -3191.54 | 20522.48 | 61400.01 | 59831.87 | 81397.1607 | 97910.0886 | 93704.458 | 85586.5897 | 69777.1416 | 50205.1389 | 32477.7708 | 37423.8228 | 54087.7727 | 64814.7851 | 68036.8598 | 63302.4634 | 51267.9084 | 41500.2062 | 36858.773 | 34479.7
Contract assets | commercial + public sector | 542244.5071 | 270946.2464 | 401691.8 | 339998.43 | 232272.41 | 173256.03 | 177805.03 | 322798.26 | 495934.33 | 545448.61 | 691706.7607 | 696073.8346 | 627683.3384 | 542244.5071 | 483353.9416 | 352753.545 | 242051.1697 | 294345.8907 | 425282.9888 | 509126.4456 | 534356.261 | 497763.5722 | 404313.9858 | 328797.0763 | 290488.8505 | 270946.2464
Contract liabilities | commercial + public sector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onerous contract provisions | commercial + public sector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention receivable | commercial + public sector | 186751.8001 | 176168.1174 | 59889.7435 | 79345.335 | 95728.1885 | 80761.1805 | 60960.5975 | 69603.181 | 84955.7665 | 106954.4872 | 129401.2311 | 159548.6532 | 190445.9303 | 186751.8001 | 201220.9813 | 223572.2227 | 192039.6179 | 152299.6764 | 138714.1932 | 158533.8981 | 182112.4426 | 206952.4779 | 230396.2121 | 227718.1961 | 238923.9874 | 176168.1174
Retention withheld / (released) | commercial + public sector | 145066.0286 | -10583.6826 | 18203.972 | 19455.5915 | 16382.8535 | -14967.008 | -19800.583 | 8642.5835 | 15352.5855 | 21998.7207 | 22446.7439 | 30147.4221 | 30897.2771 | -3694.1302 | 14469.1812 | 22351.2413 | -31532.6047 | -39739.9415 | -13585.4832 | 19819.705 | 23578.5445 | 24840.0353 | 23443.7342 | -2678.016 | 11205.7913 | -62755.87
Subcontractor retention payable | commercial + public sector | 101607.3933 | 93286.5735 | 35307.1965 | 42257.5025 | 46736.3405 | 39731.0295 | 30987.578 | 38466.992 | 49491.122 | 61484.1515 | 76097.2132 | 90951.2487 | 104472.8606 | 101607.3933 | 108063.1318 | 115726.7185 | 94680.1896 | 80100.7156 | 76897.0374 | 88737.4215 | 101166.2214 | 112760.3417 | 122204.4195 | 118697.8358 | 123508.9798 | 93286.5735
Subcontractor retention withheld / (released) | commercial + public sector | 75190.0883 | -8320.8198 | 8889.8915 | 6950.306 | 4478.838 | -7005.311 | -8743.4515 | 7479.414 | 11024.13 | 11993.0295 | 14613.0617 | 14854.0355 | 13521.6119 | -2865.4673 | 6455.7384 | 7663.5867 | -21046.529 | -14579.474 | -3203.6782 | 11840.3841 | 12428.7998 | 11594.1203 | 9444.0779 | -3506.5837 | 4811.144 | -30222.4063
Invoiced ex VAT | commercial + public sector | 4767003.9059 | 4915461.9169 | 345875.468 | 369656.2385 | 311274.2165 | 231126.848 | 184638.923 | 164209.0865 | 303765.4645 | 454244.4093 | 476097.9708 | 636440.2502 | 652657.562 | 637017.4686 | 527775.3259 | 461002.7003 | 384286.1498 | 281791.1112 | 307931.3739 | 405463.2838 | 485547.9011 | 509516.2258 | 474319.838 | 406992.0018 | 317591.2849 | 353244.7204
Output VAT | commercial + public sector | 404821.368 | 368497.5422 | 22443.6025 | 18225.8973 | 19348.7684 | 16417.8967 | 14884.7836 | 17891.3572 | 28451.8214 | 41781.3016 | 41872.4767 | 59428.4363 | 62036.2243 | 62038.802 | 51519.0932 | 48846.7596 | 42384.1507 | 30301.0593 | 17082.6753 | 24703.4692 | 29941.5592 | 31319.5053 | 28425.7707 | 24909.8462 | 17434.4859 | 21629.1676
Invoiced incl. VAT | commercial + public sector | 5171825.2739 | 5283959.4592 | 368319.0705 | 387882.1358 | 330622.9849 | 247544.7447 | 199523.7066 | 182100.4437 | 332217.2859 | 496025.7109 | 517970.4475 | 695868.6865 | 714693.7863 | 699056.2706 | 579294.4191 | 509849.4598 | 426670.3004 | 312092.1705 | 325014.0492 | 430166.753 | 515489.4603 | 540835.7311 | 502745.6088 | 431901.848 | 335025.7709 | 374873.8881
Cash received | commercial + public sector | 4759072.2593 | 5678228.383 | 362364 | 368938.45 | 379748.23 | 338181.56 | 268609.34 | 205054.33 | 163404.84 | 337464.58 | 447152.1495 | 499610.5633 | 676561.6116 | 711982.6049 | 703533.4951 | 592726.0926 | 532235.5823 | 449667.9835 | 339090.161 | 309111.4381 | 406312.8364 | 503562.502 | 540835.7311 | 514672.5671 | 444772.2455 | 341707.7484
Trade receivables incl. VAT | commercial + public sector | 789346.9647 | 395078.0408 | 382549.0205 | 401492.7064 | 352367.4613 | 261730.646 | 192645.0125 | 169691.1262 | 338503.5721 | 497064.7031 | 567883.0011 | 764141.1243 | 802273.2989 | 789346.9647 | 665107.8887 | 582231.2559 | 476665.974 | 339090.161 | 325014.0492 | 446069.3641 | 555245.9881 | 592519.2172 | 554429.0949 | 471658.3757 | 361911.9011 | 395078.0408
Performance bonds outstanding | commercial + public sector | 544000 | 156000 | 206000 | 324000 | 324000 | 358000 | 344000 | 344000 | 383000 | 623000 | 623000 | 623000 | 662000 | 544000 | 569750 | 569750 | 382750 | 279750 | 297750 | 297750 | 336150 | 368550 | 453750 | 350000 | 332000 | 156000
Order book (remaining contract revenue) | commercial + public sector | 5454130.1284 | 820550.1549 | 3683063.33 | 4563794.87 | 4356563.82 | 5527670.36 | 6307533.02 | 6033688.12 | 5966484 | 7907676.59 | 7265303.7246 | 6605748.9784 | 5996374.6355 | 5454130.1284 | 4970776.1868 | 4618022.6418 | 4375971.4721 | 4081625.5814 | 3656342.5926 | 3147216.147 | 2612859.886 | 2115096.3138 | 1710782.328 | 1381985.2517 | 1091496.4012 | 820550.1549
Order intake | commercial + public sector | 6620000 | 2777500 | 0 | 1180000 | 0 | 1320000 | 940000 | 0 | 390000 | 2400000 | 0 | 0 | 390000 | 0 | 647500 | 0 | 390000 | 0 | 180000 | 0 | 384000 | 324000 | 852000 | 0 | 0 | 0
Secured order book: contracts in progress, contracted or completed |  | 2347567.6284 | 0 | 515563.33 | 1396294.87 | 1189063.82 | 2360170.36 | 3140033.02 | 2866188.12 | 2798984 | 4740176.59 | 4097803.7246 | 3438248.9784 | 2828874.6355 | 2347567.6284 | 1998276.1868 | 1807407.4074 | 1699643.3471 | 1537887.5171 | 1303703.7037 | 1026063.1001 | 733936.8999 | 456296.2963 | 222112.4829 | 60356.6529 | 0 | 0
Pipeline, probability-weighted remaining revenue |  | 3106562.5 | 820550.1549 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3106562.5 | 2972500 | 2810615.2344 | 2676328.125 | 2543738.0642 | 2352638.8889 | 2121153.0469 | 1878922.9861 | 1658800.0175 | 1488669.8451 | 1321628.5988 | 1091496.4012 | 820550.1549

## Residential
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
RESIDENTIAL PROGRAMMES: DEEP RETROFIT (SEAI ONE STOP SHOP) AND RENOVATION
Volume-driven: jobs started x average value, earned over the job duration by the monthly shares on Assumptions. Retrofit homeowners pay the price net of the SEAI grant, which the company claims after completion and the post-works BER. Positions are netted at programme level (see Guide).
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
DEEP RETROFIT PROGRAMME (SEAI ONE STOP SHOP)
Deseasonalised run-rate: jobs started per month | helper: single value in column C | 3.3333
Average contract value, latest three actual months (value-weighted) | helper: single value in column C | 60993.8182
Average SEAI grant per home, latest three actual months | helper: single value in column C | 23764.1818
Jobs started | A: job system; F: run-rate x seasonality x growth | 35.4789 | 47.0349 | 2 | 2 | 3 | 2 | 2 | 3 | 4 | 4 | 3.7228 | 3.608 | 3.3143 | 2.8338 | 2.5175 | 3.1038 | 3.7074 | 4.1406 | 4.395 | 4.4623 | 4.3337 | 4.2 | 4.4674 | 4.3296 | 3.9772 | 3.4005
Average contract value ex VAT | A: job system; F: latest average x price change | 61288.8549 | 62594.2 | 60550 | 64205 | 60211 | 62861 | 59224 | 60796 | 61317 | 60819 | 61144.2454 | 61295.0436 | 61446.2137 | 61597.7566 | 61749.6733 | 61901.9647 | 62054.6316 | 62207.6751 | 62361.096 | 62514.8953 | 62669.0739 | 62823.6327 | 62978.5728 | 63133.8949 | 63289.6001 | 63445.6893
Value of jobs started ex VAT | starts x average value | 2172231.5302 | 2945860.1614 | 121100 | 128410 | 180633 | 125722 | 118448 | 182388 | 245268 | 243276 | 227627.8818 | 221151.6974 | 203653.9271 | 174553.0239 | 155454.6208 | 192128.9137 | 230060.4725 | 257574.5196 | 274079.3146 | 278961.6258 | 271586.0859 | 263859.2575 | 281348.062 | 273343.4979 | 251716.2539 | 215747.5375
Average SEAI grant per home | A: grant applications; F: latest average | 23842.8939 | 23764.1818 | 24548 | 26586 | 24288 | 22206 | 22057 | 24086 | 24171 | 23116 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818 | 23764.1818
REVENUE EARNED | A: ledger; F: value started in each of the last months x monthly share | 2132818.9817 | 2905008.4202 | 138592.05 | 124444 | 142249.4 | 151103.95 | 137267.55 | 139448.5 | 185267 | 228950.4 | 239079.5646 | 229597.056 | 217521.4124 | 199298.0987 | 176098.7287 | 171231.5094 | 194339.8081 | 228831.7969 | 255647.4463 | 271417.8092 | 275528.386 | 271111.9223 | 271037.6059 | 274574.4916 | 268856.4657 | 246332.45
Cost: own labour (allocated at standard rate) | A: cost ledger; F: revenue x (1 - gross margin) x mix | 522239.093 | 711146.0613 | 34952.94 | 30901.58 | 35804.15 | 34793.39 | 34189.05 | 34966.75 | 46331.62 | 53530.16 | 58526.6774 | 56205.3593 | 53249.2418 | 48788.1746 | 43108.9688 | 41917.4735 | 47574.385 | 56018.0239 | 62582.4949 | 66443.0797 | 67449.3489 | 66368.1986 | 66350.0059 | 67215.8356 | 65816.0628 | 60302.1838
Cost: subcontractors | A: cost ledger; F: revenue x (1 - gross margin) x mix | 496388.2722 | 666699.4324 | 32660.2 | 30636.92 | 34877.7 | 33248.27 | 32405.16 | 32644.04 | 42365.01 | 54329.61 | 54868.7601 | 52692.5244 | 49921.1641 | 45738.9136 | 40414.6582 | 39297.6314 | 44600.986 | 52516.8974 | 58671.0889 | 62290.3872 | 63233.7646 | 62220.1862 | 62203.1306 | 63014.8458 | 61702.5589 | 56533.2973
Cost: materials | A: cost ledger; F: revenue x (1 - gross margin) x mix | 468732.2114 | 622252.8036 | 28661.76 | 26982.53 | 34747.57 | 33567.44 | 30802.91 | 31261.92 | 42076.48 | 50958.33 | 51210.8427 | 49179.6894 | 46593.0865 | 42689.6527 | 37720.3477 | 36677.7893 | 41627.5869 | 49015.7709 | 54759.683 | 58137.6947 | 59018.1803 | 58072.1738 | 58056.2552 | 58813.8561 | 57589.055 | 52764.4108
Cost: plant hire | A: cost ledger; F: revenue x (1 - gross margin) x mix | 50420.3862 | 66669.9432 | 3395.59 | 3166.79 | 3644.12 | 3381.04 | 3303.38 | 3487.62 | 4738.4 | 4981.31 | 5486.876 | 5269.2524 | 4992.1164 | 4573.8914 | 4041.4658 | 3929.7631 | 4460.0986 | 5251.6897 | 5867.1089 | 6229.0387 | 6323.3765 | 6222.0186 | 6220.3131 | 6301.4846 | 6170.2559 | 5653.3297
Cost: preliminaries and site services | A: cost ledger; F: revenue x (1 - gross margin) x mix | 113628.2979 | 155563.2009 | 6964.13 | 6211.26 | 7058.15 | 7983.9 | 7280.98 | 7882.66 | 10204.82 | 12624.08 | 12802.7107 | 12294.9224 | 11648.2716 | 10672.4132 | 9430.0869 | 9169.4473 | 10406.8967 | 12253.9427 | 13689.9207 | 14534.4237 | 14754.5451 | 14518.0434 | 14514.0638 | 14703.464 | 14397.2637 | 13191.1027
DIRECT COST | sum of cost types | 1651408.2607 | 2222331.4415 | 106634.62 | 97899.08 | 116131.69 | 112974.04 | 107981.48 | 110242.99 | 145716.33 | 176423.49 | 182895.8669 | 175641.7479 | 166403.8805 | 152463.0455 | 134715.5275 | 130992.1047 | 148669.9532 | 175056.3246 | 195570.2964 | 207634.624 | 210779.2153 | 207400.6206 | 207343.7685 | 210049.4861 | 205675.1963 | 188444.3242
GROSS PROFIT |  | 481410.7209 | 682676.9787 | 31957.43 | 26544.92 | 26117.71 | 38129.91 | 29286.07 | 29205.51 | 39550.67 | 52526.91 | 56183.6977 | 53955.3082 | 51117.5319 | 46835.0532 | 41383.2013 | 40239.4047 | 45669.8549 | 53775.4723 | 60077.1499 | 63783.1852 | 64749.1707 | 63711.3018 | 63693.8374 | 64525.0055 | 63181.2694 | 57888.1257
Gross margin % |  | 22.57% | 23.5% | 23.06% | 21.33% | 18.36% | 25.23% | 21.34% | 20.94% | 21.35% | 22.94% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5% | 23.5%
Homeowner portion of jobs started, incl. VAT (price less grant) | starts x (value x (1 + VAT) - grant) | 1620104.0224 | 2225805.7781 | 88352.5 | 92573.35 | 132154.455 | 98282.47 | 90324.48 | 134752.38 | 181695.18 | 183654.26 | 169888.3167 | 165266.3264 | 152384.5194 | 130775.7849 | 116614.7368 | 144307.9725 | 173015.6413 | 193950.094 | 206635.5674 | 210578.0013 | 205264.4647 | 199670.6936 | 213166.8554 | 207355.85 | 191182.7227 | 164063.1784
Homeowner invoices incl. VAT | A: sales ledger; F: stage shares of the homeowner portion | 1586135.9157 | 2187536.4023 | 105489.75 | 91239.53 | 99223.32 | 113505.73 | 106852.47 | 101597.46 | 130812.57 | 168004.16 | 180313.3473 | 173093.7017 | 164076.5621 | 151927.3146 | 134426.1956 | 126401.6984 | 141741.5356 | 168590.2312 | 190206.8529 | 203618.4122 | 208332.5638 | 205739.7715 | 204048.0573 | 207955.8058 | 205864.5262 | 190610.752
SEAI grant claims lodged incl. VAT | A: claims; F: homes completed the claim lag earlier x grant | 810061.3291 | 1071376.4181 | 75687 | 73329 | 47512 | 49096 | 53172 | 72864 | 44412 | 44114 | 72258 | 96684 | 92464 | 88469.3291 | 85740.8501 | 78762.6879 | 67341.8972 | 59826.2577 | 73758.3445 | 88102.9949 | 98396.9857 | 104444.4547 | 106043.444 | 102985.7428 | 99809.5636 | 106163.195
Total invoiced and claimed incl. VAT |  | 2396197.2448 | 3258912.8204 | 181176.75 | 164568.53 | 146735.32 | 162601.73 | 160024.47 | 174461.46 | 175224.57 | 212118.16 | 252571.3473 | 269777.7017 | 256540.5621 | 240396.6437 | 220167.0457 | 205164.3862 | 209083.4328 | 228416.489 | 263965.1974 | 291721.4071 | 306729.5495 | 310184.2261 | 310091.5012 | 310941.5486 | 305674.0898 | 296773.947
Invoiced ex VAT |  | 2111186.9998 | 2871288.8285 | 159627.0925 | 144994.2996 | 129282.2203 | 143261.4361 | 140990.7225 | 153710.5374 | 154382.8811 | 186888.2467 | 222529.8215 | 237689.605 | 226026.927 | 211803.2103 | 193979.776 | 180761.5738 | 184214.4782 | 201248.0079 | 232568.4559 | 257023.2662 | 270246.2991 | 273290.0671 | 273208.3711 | 273957.3115 | 269316.3787 | 261474.8432
Output VAT on invoices |  | 285010.245 | 387623.9919 | 21549.6575 | 19574.2304 | 17453.0997 | 19340.2939 | 19033.7475 | 20750.9226 | 20841.6889 | 25229.9133 | 30041.5259 | 32088.0967 | 30513.6351 | 28593.4334 | 26187.2698 | 24402.8125 | 24868.9546 | 27168.4811 | 31396.7415 | 34698.1409 | 36483.2504 | 36894.1591 | 36883.1301 | 36984.2371 | 36357.7111 | 35299.1038
Programme position: earned less invoiced ex VAT | + contract asset / - contract liability | 163623.1118 | 197342.7035 | 120956.0875 | 100405.7879 | 113372.9677 | 121215.4815 | 117492.3091 | 103230.2716 | 134114.3906 | 176176.5439 | 192726.287 | 184633.738 | 176128.2235 | 163623.1118 | 145742.0646 | 136212.0002 | 146337.3301 | 173921.1191 | 197000.1095 | 211394.6526 | 216676.7395 | 214498.5948 | 212327.8296 | 212945.0097 | 212485.0967 | 197342.7035
Contract asset |  | 163623.1118 | 197342.7035 | 120956.0875 | 100405.7879 | 113372.9677 | 121215.4815 | 117492.3091 | 103230.2716 | 134114.3906 | 176176.5439 | 192726.287 | 184633.738 | 176128.2235 | 163623.1118 | 145742.0646 | 136212.0002 | 146337.3301 | 173921.1191 | 197000.1095 | 211394.6526 | 216676.7395 | 214498.5948 | 212327.8296 | 212945.0097 | 212485.0967 | 197342.7035
Contract liability (deposits ahead of work) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received from homeowners | A: bank; F: opening + invoiced - closing at payment days | 1567482.4475 | 2174641.9231 | 106268.01 | 93670.97 | 96455.66 | 108853.19 | 102307.45 | 105686.06 | 125565.63 | 144622.44 | 185493.4482 | 175500.2502 | 167082.2753 | 155977.0638 | 140259.9019 | 129076.5308 | 136628.2565 | 159640.666 | 183001.3123 | 199147.8924 | 206761.1799 | 206604.0356 | 204611.962 | 206653.2229 | 206561.6194 | 195695.3434
Homeowner receivables incl. VAT |  | 50642.4382 | 63536.9173 | 31210.71 | 28779.27 | 31546.93 | 36199.47 | 40744.49 | 36655.89 | 41902.83 | 65284.55 | 60104.4491 | 57697.9006 | 54692.1874 | 50642.4382 | 44808.7319 | 42133.8995 | 47247.1785 | 56196.7437 | 63402.2843 | 67872.8041 | 69444.1879 | 68579.9238 | 68016.0191 | 69318.6019 | 68621.5087 | 63536.9173
SEAI grant cash received | A: bank; F: opening + claims - closing at SEAI payment days | 807859.67 | 1046336.9886 | 14200.01 | 135355.36 | 72516.9 | 75030.21 | 58661.54 | 42614.36 | 41057.29 | 91094.95 | 64273.05 | 44114 | 72258 | 96684 | 92464 | 88469.3291 | 85740.8501 | 78762.6879 | 67341.8972 | 59826.2577 | 73758.3445 | 88102.9949 | 98396.9857 | 104444.4547 | 106043.444 | 102985.7428
SEAI grant receivable |  | 180933.3291 | 205972.7586 | 240218.66 | 178192.3 | 153187.4 | 127253.19 | 121763.65 | 152013.29 | 155368 | 108387.05 | 116372 | 168942 | 189148 | 180933.3291 | 174210.1793 | 164503.538 | 146104.5851 | 127168.1549 | 133584.6022 | 161861.3395 | 186499.9806 | 202841.4403 | 210487.8986 | 209029.1868 | 202795.3064 | 205972.7586
SEAI grant days outstanding (receivable / average claims of the last three months x 30) |  | 58.6563 | 60.0001 | 95.2153 | 71.7476 | 70.1522 | 67.3943 | 73.1655 | 78.1193 | 82.0375 | 60.4426 | 65.1401 | 71.3652 | 65.1221 | 58.6563 | 58.7943 | 58.5253 | 56.7163 | 55.5776 | 59.8359 | 65.7119 | 64.4936 | 62.7464 | 61.33 | 60.0134 | 59.0974 | 60.0001
Homes completed | starts two months earlier | 22 | 44.3391 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 2 | 2 | 3 | 4 | 4 | 3.7228 | 3.608 | 3.3143 | 2.8338 | 2.5175 | 3.1038 | 3.7074 | 4.1406 | 4.395 | 4.4623 | 4.3337 | 4.2
Order book: value of started jobs not yet earned |  | 173100.5985 | 213952.3397 | 84770 | 120162 | 158545.6 | 133163.65 | 114344.1 | 157283.6 | 217284.6 | 231610.2 | 220158.5173 | 211713.1586 | 197845.6733 | 173100.5985 | 152456.4905 | 173353.8948 | 209074.5592 | 237817.2818 | 256249.1501 | 263792.9667 | 259850.6666 | 252598.0017 | 262908.4577 | 261677.464 | 244537.2522 | 213952.3397
RENOVATION AND EXTENSIONS PROGRAMME
Deseasonalised run-rate: jobs started per month | helper: single value in column C | 1.374
Average contract value, latest three actual months (value-weighted) | helper: single value in column C | 124064
Jobs started | A: job system; F: run-rate x seasonality x growth | 16.4108 | 17.215 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1.5176 | 1.4545 | 1.3214 | 1.1173 | 0.98159 | 1.1968 | 1.4137 | 1.5614 | 1.639 | 1.6457 | 1.5806 | 1.5149 | 1.5935 | 1.5273 | 1.3874 | 1.1731
Average contract value ex VAT | A: job system; F: latest average x price change | 124372.9424 | 127319.2441 | 124683 | 102963 | 123589 | 124491 | 145078 | 131987 | 123908 | 116453 | 124369.9753 | 124676.7052 | 124984.1916 | 125292.4363 | 125601.4413 | 125911.2083 | 126221.7393 | 126533.0362 | 126845.1008 | 127157.935 | 127471.5408 | 127785.92 | 128101.0746 | 128417.0064 | 128733.7173 | 129051.2094
Value of jobs started ex VAT | starts x average value | 2060951.3713 | 2192476.8356 | 124683 | 102963 | 247178 | 124491 | 290156 | 131987 | 247816 | 116453 | 188744.8965 | 181345.7472 | 165149.4855 | 139984.2421 | 123288.5506 | 150688.1761 | 178441.4708 | 197571.3754 | 207904.8985 | 209266.7674 | 201479.4024 | 193581.0368 | 204127.6056 | 196125.4255 | 178609.1686 | 151392.9579
REVENUE EARNED | A: ledger; F: value started in each of the last months x monthly share | 1982039.2699 | 2164837.1292 | 131409.36 | 114236.45 | 128758.65 | 145125.35 | 170056.66 | 189129.45 | 203261.87 | 194333.83 | 190402.7797 | 174017.342 | 175545.234 | 165762.2944 | 163015.4155 | 149877.12 | 145284.8234 | 153026.7244 | 170385.1309 | 189199.3336 | 200559.0651 | 203890.198 | 202917.2479 | 200483.1718 | 196781.4096 | 189417.4889
Cost: own labour (allocated at standard rate) | A: cost ledger; F: revenue x (1 - gross margin) x mix | 400914.0838 | 444224.5789 | 26744.36 | 21752.02 | 24812.91 | 28373.8 | 37155.85 | 39028.56 | 41499.95 | 36731.32 | 39070.6504 | 35708.3586 | 36021.882 | 34014.4228 | 33450.7633 | 30754.785 | 29812.4458 | 31401.0838 | 34963.0289 | 38823.7033 | 41154.7202 | 41838.2686 | 41638.6193 | 41139.1469 | 40379.5453 | 38868.4687
Cost: subcontractors | A: cost ledger; F: revenue x (1 - gross margin) x mix | 488705.2046 | 542941.152 | 31778.28 | 27300.04 | 31904.92 | 33620.03 | 41998.66 | 48157.15 | 49659.38 | 47290.25 | 47753.0171 | 43643.5494 | 44026.7447 | 41573.1834 | 40884.2662 | 37589.1817 | 36437.4337 | 38379.1025 | 42732.5908 | 47451.1929 | 50300.2135 | 51135.6617 | 50891.6458 | 50281.1795 | 49352.7775 | 47505.9062
Cost: materials | A: cost ledger; F: revenue x (1 - gross margin) x mix | 451286.2142 | 493582.8655 | 30318.11 | 24286.8 | 28132.24 | 30763.67 | 40621.43 | 45450.05 | 45522.69 | 45285.32 | 43411.8338 | 39675.954 | 40024.3133 | 37793.8031 | 37167.5147 | 34171.9834 | 33124.9397 | 34890.0932 | 38847.8098 | 43137.4481 | 45727.4668 | 46486.9651 | 46265.1325 | 45710.1632 | 44866.1614 | 43187.1875
Cost: plant hire | A: cost ledger; F: revenue x (1 - gross margin) x mix | 44734.0904 | 49358.2865 | 2967.98 | 2424.27 | 2823.49 | 3026.14 | 3919.63 | 4726.77 | 4464.55 | 4290.67 | 4341.1834 | 3967.5954 | 4002.4313 | 3779.3803 | 3716.7515 | 3417.1983 | 3312.494 | 3489.0093 | 3884.781 | 4313.7448 | 4572.7467 | 4648.6965 | 4626.5133 | 4571.0163 | 4486.6161 | 4318.7187
Cost: preliminaries and site services | A: cost ledger; F: revenue x (1 - gross margin) x mix | 103417.811 | 115169.3353 | 6265.74 | 5990.96 | 5981.64 | 7015.19 | 9279.62 | 10538.71 | 10927.25 | 9873.99 | 10129.4279 | 9257.7226 | 9339.0064 | 8818.5541 | 8672.4201 | 7973.4628 | 7729.1526 | 8141.0217 | 9064.489 | 10065.4045 | 10669.7423 | 10846.9585 | 10795.1976 | 10665.7047 | 10468.771 | 10077.0104
DIRECT COST | sum of cost types | 1489057.4039 | 1645276.2182 | 98074.47 | 81754.09 | 93655.2 | 102798.83 | 132975.19 | 147901.24 | 152073.82 | 143471.55 | 144706.1125 | 132253.1799 | 133414.3778 | 125979.3437 | 123891.7158 | 113906.6112 | 110416.4658 | 116300.3105 | 129492.6995 | 143791.4936 | 152424.8895 | 154956.5505 | 154217.1084 | 152367.2106 | 149553.8713 | 143957.2916
GROSS PROFIT |  | 492981.866 | 519560.911 | 33334.89 | 32482.36 | 35103.45 | 42326.52 | 37081.47 | 41228.21 | 51188.05 | 50862.28 | 45696.6671 | 41764.1621 | 42130.8561 | 39782.9506 | 39123.6997 | 35970.5088 | 34868.3576 | 36726.4139 | 40892.4314 | 45407.8401 | 48134.1756 | 48933.6475 | 48700.1395 | 48115.9612 | 47227.5383 | 45460.1973
Gross margin % |  | 24.87% | 24% | 25.37% | 28.43% | 27.26% | 29.17% | 21.81% | 21.8% | 25.18% | 26.17% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24% | 24%
Invoices incl. VAT | A: sales ledger; F: deposit + progress + snag release | 2261224.9963 | 2458493.9437 | 154404.31 | 127523.45 | 172643.28 | 158914.79 | 209857.5 | 201122.58 | 233828.21 | 202124.39 | 219046.8941 | 195946.7242 | 203978.1253 | 181834.7427 | 183071.431 | 168351.7947 | 173009.5529 | 182876.1636 | 199477.7411 | 215364.7678 | 223406.1246 | 226641.0253 | 229128.1395 | 226641.2492 | 220884.3339 | 209641.6201
Invoiced ex VAT |  | 1992268.7192 | 2166073.9592 | 136039.0396 | 112355.4626 | 152108.6167 | 140013.0308 | 184896.4758 | 177200.511 | 206016.0441 | 178083.163 | 192992.8582 | 172640.2856 | 179716.41 | 160206.8218 | 161296.415 | 148327.5724 | 152431.3241 | 161124.3732 | 175751.3138 | 189748.6941 | 196833.59 | 199683.7227 | 201875.0127 | 199683.92 | 194611.7479 | 184706.2732
Output VAT on invoices |  | 268956.2771 | 292419.9845 | 18365.2704 | 15167.9874 | 20534.6633 | 18901.7592 | 24961.0242 | 23922.069 | 27812.1659 | 24041.227 | 26054.0359 | 23306.4386 | 24261.7153 | 21627.9209 | 21775.016 | 20024.2223 | 20578.2288 | 21751.7904 | 23726.4274 | 25616.0737 | 26572.5346 | 26957.3026 | 27253.1267 | 26957.3292 | 26272.586 | 24935.3469
Programme position: earned less invoiced ex VAT | + contract asset / - contract liability | -15852.8193 | -17089.6493 | -10253.0496 | -8372.0622 | -31722.0289 | -26609.7098 | -41449.5256 | -29520.5866 | -32274.7606 | -16024.0936 | -18614.1722 | -17237.1158 | -21408.2919 | -15852.8193 | -14133.8188 | -12584.2712 | -19730.772 | -27828.4208 | -33194.6037 | -33743.9641 | -30018.489 | -25812.0137 | -24769.7785 | -23970.5268 | -21800.8651 | -17089.6493
Contract asset |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability (deposits ahead of work) |  | 15852.8193 | 17089.6493 | 10253.0496 | 8372.0622 | 31722.0289 | 26609.7098 | 41449.5256 | 29520.5866 | 32274.7606 | 16024.0936 | 18614.1722 | 17237.1158 | 21408.2919 | 15852.8193 | 14133.8188 | 12584.2712 | 19730.772 | 27828.4208 | 33194.6037 | 33743.9641 | 30018.489 | 25812.0137 | 24769.7785 | 23970.5268 | 21800.8651 | 17089.6493
Cash received from homeowners | A: bank; F: opening + invoiced - closing at payment days | 2268910.0554 | 2449224.9846 | 166567.19 | 124038.46 | 159820.04 | 151894.2 | 204243.51 | 214564.27 | 194818.62 | 235679 | 223121.1227 | 203646.7808 | 201300.9916 | 189215.8703 | 182659.2016 | 173258.3401 | 171456.9668 | 179587.2933 | 193943.8819 | 210069.0922 | 220725.6724 | 225562.7251 | 228299.1014 | 227470.2127 | 222803.3057 | 213389.1913
Homeowner receivables incl. VAT |  | 60611.5809 | 69880.54 | 56133.76 | 59618.75 | 72441.99 | 79462.58 | 85076.57 | 71634.88 | 110644.47 | 77089.86 | 73015.6314 | 65315.5747 | 67992.7084 | 60611.5809 | 61023.8103 | 56117.2649 | 57669.851 | 60958.7212 | 66492.5804 | 71788.2559 | 74468.7082 | 75547.0084 | 76376.0465 | 75547.0831 | 73628.1113 | 69880.54
Order book: value of started jobs not yet earned |  | 339137.5014 | 366777.2077 | 112214.7 | 177451.14 | 342348.24 | 340010.59 | 460109.93 | 402967.48 | 447521.61 | 369640.78 | 367982.8969 | 375311.3021 | 364915.5536 | 339137.5014 | 299410.6365 | 300221.6926 | 333378.3401 | 377922.991 | 415442.7586 | 435510.1924 | 436430.5297 | 426121.3685 | 427331.7261 | 422973.9799 | 404801.7388 | 366777.2077
RESIDENTIAL TOTALS
Revenue | retrofit + renovation | 4114858.2516 | 5069845.5494 | 270001.41 | 238680.45 | 271008.05 | 296229.3 | 307324.21 | 328577.95 | 388528.87 | 423284.23 | 429482.3442 | 403614.398 | 393066.6464 | 365060.393 | 339114.1443 | 321108.6294 | 339624.6314 | 381858.5213 | 426032.5772 | 460617.1428 | 476087.4511 | 475002.1203 | 473954.8539 | 475057.6634 | 465637.8753 | 435749.9389
Direct cost | retrofit + renovation | 3140465.6647 | 3867607.6596 | 204709.09 | 179653.17 | 209786.89 | 215772.87 | 240956.67 | 258144.23 | 297790.15 | 319895.04 | 327601.9794 | 307894.9278 | 299818.2583 | 278442.3892 | 258607.2433 | 244898.7159 | 259086.4189 | 291356.6352 | 325062.9959 | 351426.1176 | 363204.1048 | 362357.1711 | 361560.877 | 362416.6967 | 355229.0676 | 332401.6158
Own labour (allocated at standard rate) | retrofit + renovation | 923153.1768 | 1155370.6402 | 61697.3 | 52653.6 | 60617.06 | 63167.19 | 71344.9 | 73995.31 | 87831.57 | 90261.48 | 97597.3278 | 91913.7179 | 89271.1238 | 82802.5974 | 76559.7321 | 72672.2585 | 77386.8308 | 87419.1077 | 97545.5237 | 105266.7829 | 108604.0691 | 108206.4672 | 107988.6252 | 108354.9824 | 106195.6081 | 99170.6525
Subcontractors | retrofit + renovation | 985093.4768 | 1209640.5844 | 64438.48 | 57936.96 | 66782.62 | 66868.3 | 74403.82 | 80801.19 | 92024.39 | 101619.86 | 102621.7772 | 96336.0737 | 93947.9088 | 87312.0971 | 81298.9245 | 76886.8131 | 81038.4197 | 90895.9999 | 101403.6797 | 109741.5801 | 113533.9781 | 113355.8478 | 113094.7763 | 113296.0253 | 111055.3364 | 104039.2035
Materials | retrofit + renovation | 920018.4256 | 1115835.6691 | 58979.87 | 51269.33 | 62879.81 | 64331.11 | 71424.34 | 76711.97 | 87599.17 | 96243.65 | 94622.6765 | 88855.6434 | 86617.3999 | 80483.4559 | 74887.8624 | 70849.7727 | 74752.5266 | 83905.8641 | 93607.4928 | 101275.1428 | 104745.6471 | 104559.1389 | 104321.3877 | 104524.0193 | 102455.2163 | 95951.5983
Plant hire | retrofit + renovation | 95154.4766 | 116028.2298 | 6363.57 | 5591.06 | 6467.61 | 6407.18 | 7223.01 | 8214.39 | 9202.95 | 9271.98 | 9828.0594 | 9236.8478 | 8994.5477 | 8353.2717 | 7758.2173 | 7346.9615 | 7772.5926 | 8740.6991 | 9751.8899 | 10542.7835 | 10896.1231 | 10870.7151 | 10846.8263 | 10872.5009 | 10656.872 | 9972.0485
Preliminaries and site services | retrofit + renovation | 217046.1088 | 270732.5362 | 13229.87 | 12202.22 | 13039.79 | 14999.09 | 16560.6 | 18421.37 | 21132.07 | 22498.07 | 22932.1386 | 21552.6449 | 20987.2781 | 19490.9672 | 18102.507 | 17142.9101 | 18136.0493 | 20394.9645 | 22754.4097 | 24599.8282 | 25424.2873 | 25365.002 | 25309.2614 | 25369.1688 | 24866.0347 | 23268.1131
Gross profit | retrofit + renovation | 974392.5869 | 1202237.8898 | 65292.32 | 59027.28 | 61221.16 | 80456.43 | 66367.54 | 70433.72 | 90738.72 | 103389.19 | 101880.3648 | 95719.4702 | 93248.3881 | 86618.0038 | 80506.901 | 76209.9135 | 80538.2125 | 90501.8861 | 100969.5813 | 109191.0252 | 112883.3463 | 112644.9493 | 112393.9769 | 112640.9668 | 110408.8078 | 103348.3231
Contract assets | retrofit + renovation | 163623.1118 | 197342.7035 | 120956.0875 | 100405.7879 | 113372.9677 | 121215.4815 | 117492.3091 | 103230.2716 | 134114.3906 | 176176.5439 | 192726.287 | 184633.738 | 176128.2235 | 163623.1118 | 145742.0646 | 136212.0002 | 146337.3301 | 173921.1191 | 197000.1095 | 211394.6526 | 216676.7395 | 214498.5948 | 212327.8296 | 212945.0097 | 212485.0967 | 197342.7035
Contract liabilities | retrofit + renovation | 15852.8193 | 17089.6493 | 10253.0496 | 8372.0622 | 31722.0289 | 26609.7098 | 41449.5256 | 29520.5866 | 32274.7606 | 16024.0936 | 18614.1722 | 17237.1158 | 21408.2919 | 15852.8193 | 14133.8188 | 12584.2712 | 19730.772 | 27828.4208 | 33194.6037 | 33743.9641 | 30018.489 | 25812.0137 | 24769.7785 | 23970.5268 | 21800.8651 | 17089.6493
Output VAT | retrofit + renovation | 553966.5221 | 680043.9763 | 39914.9278 | 34742.2179 | 37987.763 | 38242.053 | 43994.7718 | 44672.9915 | 48653.8549 | 49271.1403 | 56095.5618 | 55394.5352 | 54775.3505 | 50221.3543 | 47962.2858 | 44427.0347 | 45447.1833 | 48920.2714 | 55123.1689 | 60314.2146 | 63055.785 | 63851.4616 | 64136.2568 | 63941.5663 | 62630.2971 | 60234.4507
Cash from homeowners | retrofit + renovation | 3836392.5029 | 4623866.9077 | 272835.2 | 217709.43 | 256275.7 | 260747.39 | 306550.96 | 320250.33 | 320384.25 | 380301.44 | 408614.5709 | 379147.031 | 368383.2669 | 345192.934 | 322919.1035 | 302334.8709 | 308085.2233 | 339227.9593 | 376945.1943 | 409216.9846 | 427486.8523 | 432166.7606 | 432911.0634 | 434123.4356 | 429364.925 | 409084.5348
Homeowner receivables | retrofit + renovation | 111254.0191 | 133417.4574 | 87344.47 | 88398.02 | 103988.92 | 115662.05 | 125821.06 | 108290.77 | 152547.3 | 142374.41 | 133120.0805 | 123013.4753 | 122684.8958 | 111254.0191 | 105832.5422 | 98251.1644 | 104917.0295 | 117155.4649 | 129894.8647 | 139661.06 | 143912.8961 | 144126.9323 | 144392.0656 | 144865.685 | 142249.62 | 133417.4574
Order book in flight | retrofit + renovation | 512238.0999 | 580729.5475 | 196984.7 | 297613.14 | 500893.84 | 473174.24 | 574454.03 | 560251.08 | 664806.21 | 601250.98 | 588141.4142 | 587024.4607 | 562761.2269 | 512238.0999 | 451867.127 | 473575.5874 | 542452.8992 | 615740.2728 | 671691.9087 | 699303.159 | 696281.1963 | 678719.3702 | 690240.1839 | 684651.4439 | 649338.991 | 580729.5475

## Pipeline
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
ORDER BOOK, PIPELINE AND COVER
Secured work = remaining revenue on contracts in progress or signed plus residential jobs started and not yet earned. Pipeline is weighted by the win probability of the selected scenario. Cover = secured work / average revenue of the latest three months.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
ORDER BOOK AND COVER
Named contracts: remaining revenue (secured) | WIP | 2347567.6284 | 0 | 515563.33 | 1396294.87 | 1189063.82 | 2360170.36 | 3140033.02 | 2866188.12 | 2798984 | 4740176.59 | 4097803.7246 | 3438248.9784 | 2828874.6355 | 2347567.6284 | 1998276.1868 | 1807407.4074 | 1699643.3471 | 1537887.5171 | 1303703.7037 | 1026063.1001 | 733936.8999 | 456296.2963 | 222112.4829 | 60356.6529 | 0 | 0
Residential jobs started, not yet earned | Residential | 512238.0999 | 580729.5475 | 196984.7 | 297613.14 | 500893.84 | 473174.24 | 574454.03 | 560251.08 | 664806.21 | 601250.98 | 588141.4142 | 587024.4607 | 562761.2269 | 512238.0999 | 451867.127 | 473575.5874 | 542452.8992 | 615740.2728 | 671691.9087 | 699303.159 | 696281.1963 | 678719.3702 | 690240.1839 | 684651.4439 | 649338.991 | 580729.5475
SECURED WORK IN HAND |  | 2859805.7283 | 580729.5475 | 712548.03 | 1693908.01 | 1689957.66 | 2833344.6 | 3714487.05 | 3426439.2 | 3463790.21 | 5341427.57 | 4685945.1388 | 4025273.4391 | 3391635.8625 | 2859805.7283 | 2450143.3138 | 2280982.9948 | 2242096.2463 | 2153627.79 | 1975395.6124 | 1725366.2592 | 1430218.0961 | 1135015.6665 | 912352.6667 | 745008.0969 | 649338.991 | 580729.5475
Pipeline, probability-weighted remaining revenue | WIP | 3106562.5 | 820550.1549 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3167500 | 3106562.5 | 2972500 | 2810615.2344 | 2676328.125 | 2543738.0642 | 2352638.8889 | 2121153.0469 | 1878922.9861 | 1658800.0175 | 1488669.8451 | 1321628.5988 | 1091496.4012 | 820550.1549
Revenue | PL | 9197434.2432 | 9703425.5229 | 664034.2 | 566098.91 | 490939.1 | 453372.76 | 476711.55 | 646422.85 | 880782.99 | 949041.64 | 1074285.2096 | 1074569.1442 | 1008230.9892 | 912944.9002 | 822468.0859 | 673862.1744 | 581675.8012 | 676204.412 | 851315.566 | 969743.5884 | 1010443.7122 | 972765.6925 | 878268.8397 | 803854.7397 | 756126.7258 | 706696.1853
Months of cover (secured / average revenue of latest three months) |  | 2.8639 | 0.76861 | 1.0731 | 2.754 | 2.9458 | 5.6276 | 7.8419 | 6.5203 | 5.1855 | 6.4712 | 4.8407 | 3.8981 | 3.2229 | 2.8639 | 2.6791 | 2.8403 | 3.2369 | 3.3446 | 2.8097 | 2.0727 | 1.5153 | 1.1531 | 0.95652 | 0.84185 | 0.79894 | 0.76861
ORDER INTAKE
Named contracts awarded (probability-weighted) | WIP | 6620000 | 2777500 | 0 | 1180000 | 0 | 1320000 | 940000 | 0 | 390000 | 2400000 | 0 | 0 | 390000 | 0 | 647500 | 0 | 390000 | 0 | 180000 | 0 | 384000 | 324000 | 852000 | 0 | 0 | 0
Residential jobs started (value) | Residential | 4233182.9014 | 5138336.997 | 245783 | 231373 | 427811 | 250213 | 408604 | 314375 | 493084 | 359729 | 416372.7784 | 402497.4445 | 368803.4126 | 314537.266 | 278743.1714 | 342817.0898 | 408501.9433 | 455145.8949 | 481984.2131 | 488228.3931 | 473065.4883 | 457440.2943 | 485475.6676 | 469468.9235 | 430325.4224 | 367140.4953
TOTAL ORDER INTAKE |  | 10853182.9014 | 7915836.997 | 245783 | 1411373 | 427811 | 1570213 | 1348604 | 314375 | 883084 | 2759729 | 416372.7784 | 402497.4445 | 758803.4126 | 314537.266 | 926243.1714 | 342817.0898 | 798501.9433 | 455145.8949 | 661984.2131 | 488228.3931 | 857065.4883 | 781440.2943 | 1337475.6676 | 469468.9235 | 430325.4224 | 367140.4953
Book-to-bill, trailing three months | intake / revenue |  |  | 0.37014 | 1.3471 | 1.2114 | 2.2573 | 2.3551 | 2.0509 | 1.2705 | 1.5981 | 1.3977 | 1.1552 | 0.49972 | 0.49264 | 0.72881 | 0.65729 | 0.99497 | 0.82644 | 0.90823 | 0.64285 | 0.70891 | 0.72021 | 1.04 | 0.97495 | 0.91757 | 0.55894
CONTRACTS NOT YET STARTED AND PIPELINE OPPORTUNITIES (selected scenario)
Contract | Client (fictional) | Status / stage | Contract value | 1: Win % Base; 2: Win % Downside; 3: Win % Upside; 4: Win % selected; 5: Weighted value; 6: Effective start; 7: Bond required; 8: Tender margin %
CF-2604 | Liffeyside Medical Partners | Contracted | 640000 | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 640000; 6: 2026-10-31; 7: 64000; 8: 14.22%
PS-2602 | Kildrum County Council | Contracted | 1760000 | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 1760000; 6: 2027-03-31; 7: 176000; 8: 12.05%
CF-P01 | Quayside Capital Partners | Tender submitted | 1850000 | 1: 35%; 2: 20%; 3: 50%; 4: 35%; 5: 647500; 6: 2027-02-28; 7: 185000; 8: 13.51%
CF-P02 | Maple & Rowe Retail Ltd | Preferred bidder | 520000 | 1: 75%; 2: 55%; 3: 85%; 4: 75%; 5: 390000; 6: 2026-12-31; 7: 52000; 8: 14.04%
CF-P03 | Tolka Hospitality Ltd | Shortlisted | 780000 | 1: 50%; 2: 30%; 3: 65%; 4: 50%; 5: 390000; 6: 2027-04-30; 7: 78000; 8: 13.59%
PS-P01 | Kildrum County Council | Framework call-off expected | 1420000 | 1: 60%; 2: 40%; 3: 75%; 4: 60%; 5: 852000; 6: 2027-10-31; 7: 142000; 8: 11.97%
CF-P04 | Brightlane Software Ltd | Tender in preparation | 720000 | 1: 25%; 2: 15%; 3: 35%; 4: 25%; 5: 180000; 6: 2027-06-30; 7: 72000; 8: 13.61%
CF-P05 | Merrion Row Holdings Ltd | Early engagement | 960000 | 1: 40%; 2: 25%; 3: 55%; 4: 40%; 5: 384000; 6: 2027-08-31; 7: 96000; 8: 13.54%
CF-P06 | Corrib Bay Hotels Ltd | Early engagement | 1080000 | 1: 30%; 2: 20%; 3: 40%; 4: 30%; 5: 324000; 6: 2027-09-30; 7: 108000; 8: 13.43%
TOTAL |  |  | 9730000 | 5: 5567500; 7: 973000

## Variations
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
VARIATIONS REGISTER (FICTIONAL)
Every variation raised on named contracts. Approved = instructed and valued by the client; Pending = submitted, undecided (expected decision date in column G); Rejected = refused. While undecided a variation counts in contract value at the policy constraint; on its decision date at the scenario agreed share.
Ref | Project | Description | Date raised | Value claimed | Status at last actual | Decision date (actual or expected) | Value approved | In contract value at last actual | Expected final value (selected scenario) | Approved as % of claimed | Days open (pending)
V-CF2501-01 | CF-2501 | Additional meeting room partitions | 2025-11-20 | 22400 | Approved | 2026-01-15 | 22400 | 22400 | 22400 | 100%
V-CF2501-02 | CF-2501 | Upgraded lighting controls | 2025-12-10 | 31800 | Approved | 2026-03-20 | 28600 | 28600 | 28600 | 89.94%
V-CF2501-03 | CF-2501 | Out-of-hours working requested by the client | 2026-01-23 | 14900 | Approved | 2026-05-22 | 12700 | 12700 | 12700 | 85.23%
V-CF2501-04 | CF-2501 | Disruption and prolongation claim | 2026-02-27 | 26500 | Rejected | 2026-05-22 | 0 | 0 | 0
V-PS2502-01 | PS-2502 | Asbestos removal, 3 homes | 2025-12-05 | 18600 | Approved | 2026-02-12 | 18600 | 18600 | 18600 | 100%
V-PS2502-02 | PS-2502 | Additional attic insulation to extension roofs | 2026-02-18 | 11200 | Approved | 2026-04-24 | 10400 | 10400 | 10400 | 92.86%
V-CF2601-01 | CF-2601 | Client change: additional comms room cooling | 2026-05-08 | 34500 | Approved | 2026-07-10 | 33000 | 33000 | 33000 | 95.65%
V-CF2601-02 | CF-2601 | Revised ceiling layout, level 2 | 2026-06-12 | 41800 | Pending | 2026-10-30 | 0 | 20900 | 27170 |  | 80
V-CF2601-03 | CF-2601 | Late design change: raised access floor extension | 2026-07-03 | 38600 | Pending | 2026-11-27 | 0 | 19300 | 25090 |  | 59
V-CF2601-04 | CF-2601 | Acceleration to meet the revised handover date | 2026-08-14 | 37600 | Pending | 2026-12-18 | 0 | 18800 | 24440 |  | 17
V-CF2601-05 | CF-2601 | Additional signage | 2026-04-17 | 6900 | Rejected | 2026-06-05 | 0 | 0 | 0
V-CF2602-01 | CF-2602 | Bathroom pod upgrades, 12 rooms | 2026-06-19 | 28800 | Approved | 2026-08-07 | 27400 | 27400 | 27400 | 95.14%
V-CF2602-02 | CF-2602 | Corridor carpet replacement | 2026-08-21 | 19500 | Pending | 2026-10-16 | 0 | 9750 | 12675 |  | 10
V-CF2603-01 | CF-2603 | Kitchen extract upgrade | 2026-08-12 | 16200 | Pending | 2026-09-25 | 0 | 8100 | 10530 |  | 19
V-PS2601-01 | PS-2601 | Structural repairs found on opening up, 4 homes | 2026-06-25 | 24300 | Approved | 2026-08-20 | 22100 | 22100 | 22100 | 90.95%
V-PS2601-02 | PS-2601 | Additional ventilation to 6 homes | 2026-08-06 | 14700 | Pending | 2026-10-23 | 0 | 7350 | 9555 |  | 25
TOTAL |  |  |  | 388300 |  |  | 175200 | 259400 | 284660
SUMMARY BY PROJECT
Project | Raised (count) | Claimed | Approved (value) | Pending: claimed | Pending: in contract value (policy) | Pending: expected final (scenario) | Rejected: claimed | Upside or (downside) of pending vs policy
CF-2501 | 4 | 95600 | 63700 | 0 | 0 | 0 | 26500 | 0
PS-2502 | 2 | 29800 | 29000 | 0 | 0 | 0 | 0 | 0
CF-2601 | 5 | 159400 | 33000 | 118000 | 59000 | 76700 | 6900 | 17700
CF-2602 | 2 | 48300 | 27400 | 19500 | 9750 | 12675 | 0 | 2925
CF-2603 | 1 | 16200 | 0 | 16200 | 8100 | 10530 | 0 | 2430
PS-2601 | 2 | 39000 | 22100 | 14700 | 7350 | 9555 | 0 | 2205
TOTAL | 16 | 388300 | 175200 | 168400 | 84200 | 109460 | 33400 | 25260

## Commitments
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
COMMITMENTS AND COST TO COMPLETE CONTROL AT THE LAST ACTUAL MONTH
Subcontract and material orders placed on named contracts. Remaining commitment = order value less invoiced to date. The project cost report cost to complete must cover every remaining commitment; the uncommitted balance is the exposure still to buy.
Order ref | Project | Supplier or subcontractor (fictional) | Package | Type | Order date | Order value | Invoiced to date | Remaining commitment | RCT rate | % invoiced
PO-CF2601-01 | CF-2601 | Leinster M&E Services Ltd | Mechanical and electrical (re-let May-26) | Subcontract | 2026-02-20 | 299100 | 210127.52 | 88972.48 | 0% | 70.25%
PO-CF2601-02 | CF-2601 | Pale Interiors Ltd | Drylining and ceilings | Subcontract | 2026-02-20 | 172500 | 121227.41 | 51272.59 | 20% | 70.28%
PO-CF2601-03 | CF-2601 | Floorline Systems Ltd | Raised access floors | Subcontract | 2026-02-20 | 103500 | 72736.45 | 30763.55 | 0% | 70.28%
PO-CF2601-04 | CF-2601 | Dublin Drylining Supplies Ltd | Plasterboard, studs and sundries | Materials | 2026-02-20 | 132200 | 101335.32 | 30864.68 |  | 76.65%
PO-CF2601-05 | CF-2601 | Fingal Builders Merchants Ltd | Doorsets and ironmongery | Materials | 2026-02-20 | 108200 | 82910.71 | 25289.29 |  | 76.63%
PO-CF2602-06 | CF-2602 | Aqua Fit Bathrooms Ltd | Bathroom refurbishment package | Subcontract | 2026-05-15 | 244000 | 59354.88 | 184645.12 | 0% | 24.33%
PO-CF2602-07 | CF-2602 | Coatline Decorators | Decoration | Subcontract | 2026-05-15 | 78700 | 19146.73 | 59553.27 | 35% | 24.33%
PO-CF2602-08 | CF-2602 | Brennan Joinery Ltd | Bedroom joinery | Subcontract | 2026-05-15 | 70800 | 17232.06 | 53567.94 | 0% | 24.34%
PO-CF2602-09 | CF-2602 | Northside Timber and Insulation Ltd | Joinery timber and boards | Materials | 2026-05-15 | 83100 | 23106.22 | 59993.78 |  | 27.81%
PO-CF2602-10 | CF-2602 | Fingal Builders Merchants Ltd | Finishes and sanitaryware | Materials | 2026-05-15 | 83100 | 23106.22 | 59993.78 |  | 27.81%
PO-CF2603-11 | CF-2603 | Leinster M&E Services Ltd | Kitchen extract and M&E | Subcontract | 2026-07-17 | 112800 | 10786.29 | 102013.71 | 0% | 9.562%
PO-CF2603-12 | CF-2603 | Brennan Joinery Ltd | Bar and joinery | Subcontract | 2026-07-17 | 48400 | 4622.7 | 43777.3 | 0% | 9.551%
PO-CF2603-13 | CF-2603 | Fingal Builders Merchants Ltd | General materials | Materials | 2026-07-17 | 67000 | 6986.74 | 60013.26 |  | 10.43%
PO-PS2601-14 | PS-2601 | Heatwise Renewables Ltd | Heat pump supply and installation | Subcontract | 2026-04-10 | 265700 | 88489.46 | 177210.54 | 0% | 33.3%
PO-PS2601-15 | PS-2601 | Thermafront EWI Ltd | External wall insulation | Subcontract | 2026-04-10 | 240400 | 80061.89 | 160338.11 | 20% | 33.3%
PO-PS2601-16 | PS-2601 | Kestrel Glazing Ltd | Windows and doors | Subcontract | 2026-04-10 | 126500 | 42137.84 | 84362.16 | 0% | 33.31%
PO-PS2601-17 | PS-2601 | Northside Timber and Insulation Ltd | Insulation and airtightness materials | Materials | 2026-04-10 | 228400 | 85185.85 | 143214.15 |  | 37.3%
PO-CF2604-18 | CF-2604 | Leinster M&E Services Ltd | Mechanical, electrical and medical gases (early order) | Subcontract | 2026-08-21 | 115300 | 0 | 115300 | 0% | 0%
TOTAL | [5 empty] | 2579700 | 1048554.29 | 1531145.71
COST TO COMPLETE CONTROL BY PROJECT (last actual month)
Project | Status | Tender budget | Cost to date | Committed, not yet invoiced | Cost to complete (cost report) | Uncommitted cost to complete | % of cost to complete committed | Forecast cost at completion | Variance vs tender budget | Check: uncommitted not negative
CF-2601 | In progress | 1018000 | 850470.94 | 227162.59 | 339529.06 | 112366.47 | 66.91% | 1190000 | 172000 | OK
CF-2602 | In progress | 812000 | 207047.04 | 417753.89 | 610952.96 | 193199.07 | 68.38% | 818000 | 6000 | OK
CF-2603 | In progress | 329000 | 32888.13 | 205804.27 | 300111.87 | 94307.6 | 68.58% | 333000 | 4000 | OK
PS-2601 | In progress | 1158000 | 399523.54 | 565124.96 | 770476.46 | 205351.5 | 73.35% | 1170000 | 12000 | OK
CF-2604 | Contracted | 549000 | 0 | 115300 | 549000 | 433700 | 21% | 549000 | 0 | OK
PS-2602 | Contracted | 1548000 | 0 | 0 | 1548000 | 1548000 | 0% | 1548000 | 0 | OK
TOTAL |  | 5414000 | 1489929.65 | 1531145.71 | 4118070.35 | 2586924.64 | 37.18% | 5608000 | 194000
ACTUAL COST TO DATE BY COST TYPE, CONTRACTS STARTED IN 2026 (from the cost ledger)
Project | Own labour (allocated at standard rate) | Subcontractors | Materials | Plant hire | Preliminaries and site services | Total | Labour share of cost
CF-2601 | 136231.64 | 423132.33 | 204717.81 | 25174.65 | 61214.51 | 850470.94 | 16.02%
CF-2602 | 34526.9 | 100244.68 | 51347.16 | 6364.38 | 14563.92 | 207047.04 | 16.68%
CF-2603 | 5535.27 | 16135.07 | 7763.05 | 1058.88 | 2395.86 | 32888.13 | 16.83%
PS-2601 | 51779.48 | 220616.95 | 94650.95 | 12152.23 | 20323.93 | 399523.54 | 12.96%

## Retentions
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
RETENTIONS: HELD BY CLIENTS, HELD FROM SUBCONTRACTORS, AND LEGACY BALANCES
Named contracts: retention % of certified value, first share released the month after practical completion, balance after the defects period. Legacy balances from contracts closed before 2026 are tracked item by item, including the disputed CF-2311 retention and its specific provision.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
NAMED CONTRACTS
Retention held by commercial clients | WIP | 106279.0694 | 91720.4924 | 33848.6205 | 40954.2335 | 48497.613 | 27766.7735 | 33235.5975 | 40210.7855 | 50668.043 | 65048.1697 | 78761.678 | 98581.2258 | 119313.7674 | 106279.0694 | 113056.0184 | 130187.5307 | 130523.2429 | 87765.4688 | 93817.194 | 101927.7083 | 111624.2227 | 121857.9479 | 131419.6519 | 117032.4452 | 118319.9763 | 91720.4924
Retention held by the council | WIP | 80472.7306 | 84447.625 | 26041.123 | 38391.1015 | 47230.5755 | 52994.407 | 27725 | 29392.3955 | 34287.7235 | 41906.3175 | 50639.5531 | 60967.4274 | 71132.1629 | 80472.7306 | 88164.9629 | 93384.6919 | 61516.375 | 64534.2076 | 44896.9991 | 56606.1898 | 70488.22 | 85094.53 | 98976.5602 | 110685.7509 | 120604.0111 | 84447.625
Retention receivable, named contracts |  | 186751.8001 | 176168.1174 | 59889.7435 | 79345.335 | 95728.1885 | 80761.1805 | 60960.5975 | 69603.181 | 84955.7665 | 106954.4872 | 129401.2311 | 159548.6532 | 190445.9303 | 186751.8001 | 201220.9813 | 223572.2227 | 192039.6179 | 152299.6764 | 138714.1932 | 158533.8981 | 182112.4426 | 206952.4779 | 230396.2121 | 227718.1961 | 238923.9874 | 176168.1174
Retention withheld / (released) in the month | WIP | 145066.0286 | -10583.6826 | 18203.972 | 19455.5915 | 16382.8535 | -14967.008 | -19800.583 | 8642.5835 | 15352.5855 | 21998.7207 | 22446.7439 | 30147.4221 | 30897.2771 | -3694.1302 | 14469.1812 | 22351.2413 | -31532.6047 | -39739.9415 | -13585.4832 | 19819.705 | 23578.5445 | 24840.0353 | 23443.7342 | -2678.016 | 11205.7913 | -62755.87
Retention held from subcontractors (payable) | WIP | 101607.3933 | 93286.5735 | 35307.1965 | 42257.5025 | 46736.3405 | 39731.0295 | 30987.578 | 38466.992 | 49491.122 | 61484.1515 | 76097.2132 | 90951.2487 | 104472.8606 | 101607.3933 | 108063.1318 | 115726.7185 | 94680.1896 | 80100.7156 | 76897.0374 | 88737.4215 | 101166.2214 | 112760.3417 | 122204.4195 | 118697.8358 | 123508.9798 | 93286.5735
LEGACY: CF-2405 OFFICE FIT-OUT (practical completion Oct-25, final half due after the defects period)
Retention balance ex VAT | released on the date on Assumptions | 0 | 0 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT |  | 21565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on the release invoice |  | 2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEGACY: CF-2311 RETAIL FIT-OUT (defects period ended Mar-25; client disputes release, counterclaims defects)
Retention balance ex VAT (gross) | settled in the scenario month | 0 | 0 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Amount recovered ex VAT | balance x scenario recovery share | 28500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash received incl. VAT |  | 32347.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32347.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output VAT on the recovered amount |  | 3847.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Amount written off | balance - recovered | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bad debt charge / (release) to the P&L | A: ledger; F: write-off less provision held | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Specific provision held | opening + charge - write-off | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 9500 | 9500 | 9500 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS
Legacy retentions, net of provision |  | 0 | 0 | 57000 | 57000 | 57000 | 57000 | 57000 | 47500 | 47500 | 47500 | 47500 | 47500 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RETENTIONS RECEIVABLE (to balance sheet) | named + legacy net | 186751.8001 | 176168.1174 | 116889.7435 | 136345.335 | 152728.1885 | 137761.1805 | 117960.5975 | 117103.181 | 132455.7665 | 154454.4872 | 176901.2311 | 207048.6532 | 209445.9303 | 186751.8001 | 201220.9813 | 223572.2227 | 192039.6179 | 152299.6764 | 138714.1932 | 158533.8981 | 182112.4426 | 206952.4779 | 230396.2121 | 227718.1961 | 238923.9874 | 176168.1174
Legacy retention cash received |  | 53912.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32347.5 | 21565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy retention output VAT |  | 6412.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847.5 | 2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention past its release date (memo): CF-2311 |  | 0 | 0 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Receivables
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
TRADE RECEIVABLES, SEAI GRANTS AND COLLECTIONS BY CUSTOMER GROUP (incl. VAT)
Rolls come from the WIP and Residential engines. Days are receivables divided by the last three months of invoicing, times 30.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
RECEIVABLES BY CUSTOMER GROUP
Retrofit homeowners | Residential | 50642.4382 | 63536.9173 | 31210.71 | 28779.27 | 31546.93 | 36199.47 | 40744.49 | 36655.89 | 41902.83 | 65284.55 | 60104.4491 | 57697.9006 | 54692.1874 | 50642.4382 | 44808.7319 | 42133.8995 | 47247.1785 | 56196.7437 | 63402.2843 | 67872.8041 | 69444.1879 | 68579.9238 | 68016.0191 | 69318.6019 | 68621.5087 | 63536.9173
Renovation homeowners | Residential | 60611.5809 | 69880.54 | 56133.76 | 59618.75 | 72441.99 | 79462.58 | 85076.57 | 71634.88 | 110644.47 | 77089.86 | 73015.6314 | 65315.5747 | 67992.7084 | 60611.5809 | 61023.8103 | 56117.2649 | 57669.851 | 60958.7212 | 66492.5804 | 71788.2559 | 74468.7082 | 75547.0084 | 76376.0465 | 75547.0831 | 73628.1113 | 69880.54
Commercial clients | WIP | 611876.1774 | 202049.3767 | 191491.35 | 138856.3144 | 175635.8433 | 154153.1595 | 123498.319 | 136879.6782 | 246035.0021 | 349602.6171 | 401951.5243 | 567911.5131 | 609143.3246 | 611876.1774 | 518955.4757 | 483056.4042 | 406336.4957 | 281751.3407 | 143621.0108 | 223594.7414 | 291487.4147 | 314999.3269 | 290670.5215 | 249183.753 | 173464.9565 | 202049.3767
Kildrum County Council | WIP | 177470.7872 | 193028.6641 | 191057.6705 | 262636.392 | 176731.618 | 107577.4865 | 69146.6935 | 32811.448 | 92468.57 | 147462.086 | 165931.4768 | 196229.6111 | 193129.9743 | 177470.7872 | 146152.413 | 99174.8517 | 70329.4783 | 57338.8203 | 181393.0384 | 222474.6228 | 263758.5734 | 277519.8903 | 263758.5734 | 222474.6228 | 188446.9447 | 193028.6641
TRADE RECEIVABLES (to balance sheet) |  | 900600.9838 | 528495.4982 | 469893.4905 | 489890.7264 | 456356.3813 | 377392.696 | 318466.0725 | 277981.8962 | 491050.8721 | 639439.1131 | 701003.0815 | 887154.5995 | 924958.1947 | 900600.9838 | 770940.4309 | 680482.4203 | 581583.0035 | 456245.626 | 454908.9139 | 585730.4241 | 699158.8842 | 736646.1494 | 698821.1604 | 616524.0607 | 504161.5211 | 528495.4982
SEAI GRANT RECEIVABLE (to balance sheet) | Residential | 180933.3291 | 205972.7586 | 240218.66 | 178192.3 | 153187.4 | 127253.19 | 121763.65 | 152013.29 | 155368 | 108387.05 | 116372 | 168942 | 189148 | 180933.3291 | 174210.1793 | 164503.538 | 146104.5851 | 127168.1549 | 133584.6022 | 161861.3395 | 186499.9806 | 202841.4403 | 210487.8986 | 209029.1868 | 202795.3064 | 205972.7586
INVOICED AND COLLECTED
Invoiced to trade customers incl. VAT |  | 9019186.1859 | 9929989.8052 | 628213.1305 | 606645.1158 | 602489.5849 | 519965.2647 | 516233.6766 | 484820.4837 | 696858.0659 | 866154.2609 | 917330.6889 | 1064909.1123 | 1082748.4737 | 1032818.3279 | 896792.0458 | 804602.9529 | 741421.3889 | 663558.5653 | 714698.6432 | 849149.933 | 947228.1487 | 973216.5278 | 935921.8055 | 866498.903 | 761774.6309 | 775126.2602
Collected from trade customers |  | 8595464.7622 | 10302095.2908 | 635199.2 | 586647.88 | 636023.93 | 598928.95 | 575160.3 | 525304.66 | 483789.09 | 717766.02 | 855766.7204 | 878757.5943 | 1044944.8785 | 1057175.5389 | 1026452.5986 | 895060.9636 | 840320.8057 | 788895.9428 | 716035.3553 | 718328.4227 | 833799.6886 | 935729.2626 | 973746.7945 | 948796.0027 | 874137.1705 | 750792.2832
Collected from SEAI |  | 807859.67 | 1046336.9886 | 14200.01 | 135355.36 | 72516.9 | 75030.21 | 58661.54 | 42614.36 | 41057.29 | 91094.95 | 64273.05 | 44114 | 72258 | 96684 | 92464 | 88469.3291 | 85740.8501 | 78762.6879 | 67341.8972 | 59826.2577 | 73758.3445 | 88102.9949 | 98396.9857 | 104444.4547 | 106043.444 | 102985.7428
Trade receivable days | receivables / last three months invoiced x 30 | 25.4849 | 19.7905 | 22.4395 | 23.8031 | 22.354 | 19.6434 | 17.4908 | 16.4484 | 26.0288 | 28.1026 | 25.4361 | 28.0312 | 27.1604 | 25.4849 | 23.0333 | 22.3989 | 21.4271 | 18.5836 | 19.3151 | 23.6669 | 25.0587 | 23.9379 | 22.0188 | 19.9908 | 17.6954 | 19.7905

## AR_Aging
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
AGED RECEIVABLES AT THE LAST ACTUAL MONTH (incl. VAT)
Open invoices, SEAI grant claims and other receivables, aged by due date. Retentions are aged separately on the Retentions sheet. Group totals must agree with the ledger.
As at | 2026-08-31
Counterparty (fictional) | Item / document | Group | Amount (EUR) | Due date | Days past due | Not yet due | 1 to 30 | 31 to 60 | 61 to 90 | Over 90 | Action / note
Harbourline Insurance DAC | CF-2601 valuation 6 (August), payment claim dated 31-Aug | Commercial | 194349.57 | 2026-09-30 | 0 | 194349.57 | 0 | 0 | 0 | 0 | Certified in full; due 30-Sep.
Harbourline Insurance DAC | CF-2601 valuation 5 (July), balance short-paid | Commercial | 39806.54 | 2026-08-30 | 1 | 0 | 39806.54 | 0 | 0 | 0 | Client QS disputes the measurement of level 2 ceilings; resolve with V-CF2601-02.
Tolka Hospitality Ltd | CF-2602 valuation 3 (August) | Commercial | 83121.49 | 2026-10-15 | 0 | 83121.49 | 0 | 0 | 0 | 0 | 45-day terms.
Tolka Hospitality Ltd | CF-2602 valuation 2 (July) | Commercial | 32325.02 | 2026-09-14 | 0 | 32325.02 | 0 | 0 | 0 | 0 | 45-day terms; due mid-September.
Kildrum County Council | PS-2601 interim certificate 4 (August) | Council | 147462.08 | 2026-09-30 | 0 | 147462.08 | 0 | 0 | 0 | 0 | Reverse charge VAT and RCT at 0%; council pays within 30 days.
Retrofit homeowners (14 open accounts) | Stage invoices issued in August | Homeowners | 56144.71 | 2026-09-10 | 0 | 56144.71 | 0 | 0 | 0 | 0 | Standard 10-day terms.
Retrofit homeowners (3 accounts) | Completion invoices, July | Homeowners | 9139.84 | 2026-08-12 | 19 | 0 | 9139.84 | 0 | 0 | 0 | Chased weekly; all three awaiting final BER certificate before paying.
Renovation clients (9 open accounts) | Deposits and progress invoices, August | Homeowners | 52820.87 | 2026-09-12 | 0 | 52820.87 | 0 | 0 | 0 | 0 | Standard 12-day terms.
Renovation clients (2 accounts) | Progress invoices, July | Homeowners | 5868.99 | 2026-08-14 | 17 | 0 | 5868.99 | 0 | 0 | 0 | Chased; payment promised in September.
Renovation client, Rathgar extension | Final invoice withheld pending snag list | Homeowners | 18400 | 2026-06-30 | 62 | 0 | 0 | 0 | 18400 | 0 | Snag list 80% closed; balance to be released on completion, target 30-Sep.
SEAI (One Stop Shop grant claims) | Grant claims lodged in August, 4 homes | SEAI grants | 67199.97 | 2026-10-30 | 0 | 67199.97 | 0 | 0 | 0 | 0 | Post-works BER published; payment expected in about 60 days.
SEAI (One Stop Shop grant claims) | Grant claims lodged in July, 3 homes | SEAI grants | 41187.08 | 2026-09-29 | 0 | 41187.08 | 0 | 0 | 0 | 0 | One claim queried by SEAI inspection (airtightness test re-run).
Various | Prepaid insurance (contractors all risks) | Other | 29000 | 2027-03-31 | 0 | 29000 | 0 | 0 | 0 | 0 | Prepayment, released monthly.
Various | Deposits and other receivables | Other | 17000 | 2027-06-30 | 0 | 17000 | 0 | 0 | 0 | 0 | Yard and office deposits.
TOTAL |  |  | 793826.16 |  |  | 720610.79 | 54815.37 | 0 | 18400 | 0
Share of total | [5 empty] | 90.78% | 6.905% | 0% | 2.318% | 0%
Commercial clients: aging vs ledger |  |  | 349602.62 | Ledger balance | 349602.6171 | Difference | 0
Council: aging vs ledger |  |  | 147462.08 | Ledger balance | 147462.086 | Difference | 0
Homeowners: aging vs ledger |  |  | 142374.41 | Ledger balance | 142374.41 | Difference | 0
SEAI grant claims: aging vs ledger |  |  | 108387.05 | Ledger balance | 108387.05 | Difference | 0
Prepayments and other receivables: aging vs ledger |  |  | 46000 | Ledger balance | 46000 | Difference | 0

## AP_Aging
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
AGED PAYABLES AT THE LAST ACTUAL MONTH
Open supplier and subcontractor balances aged by due date, with each subcontractor RCT rate. Subcontractor retentions are shown on the Retentions sheet. Group totals must agree with the Payables schedule.
As at | 2026-08-31
Counterparty (fictional) | Item / document | Group | Amount (EUR) | Due date | Days past due | Not yet due | 1 to 30 | 31 to 60 | 61 to 90 | Over 90 | Action / note
Leinster M&E Services Ltd | CF-2601, CF-2603 applications (August) | Subcontractors | 125721.07 | 2026-09-25 | 0 | 125721.07 | 0 | 0 | 0 | 0 | RCT rate 0%; reverse charge VAT.
Heatwise Renewables Ltd | PS-2601 and retrofit programme (August) | Subcontractors | 77054.85 | 2026-09-25 | 0 | 77054.85 | 0 | 0 | 0 | 0 | RCT rate 0%; reverse charge VAT.
Thermafront EWI Ltd | PS-2601 external insulation (August) | Subcontractors | 56777.26 | 2026-09-25 | 0 | 56777.26 | 0 | 0 | 0 | 0 | RCT rate 20%; reverse charge VAT.
Aqua Fit Bathrooms Ltd | CF-2602 bathrooms (August) | Subcontractors | 36499.67 | 2026-09-25 | 0 | 36499.67 | 0 | 0 | 0 | 0 | RCT rate 0%; reverse charge VAT.
Pale Interiors Ltd | CF-2601 drylining (August) | Subcontractors | 32444.15 | 2026-09-25 | 0 | 32444.15 | 0 | 0 | 0 | 0 | RCT rate 20%; reverse charge VAT.
Kestrel Glazing Ltd | Windows, retrofit and council homes | Subcontractors | 28388.63 | 2026-09-25 | 0 | 28388.63 | 0 | 0 | 0 | 0 | RCT rate 0%; reverse charge VAT.
Sparkline Electrical Ltd | Residential electrical (August) | Subcontractors | 20277.59 | 2026-09-25 | 0 | 20277.59 | 0 | 0 | 0 | 0 | RCT rate 0%; reverse charge VAT.
Liffey Plumbing and Heating | Renovation plumbing (August) | Subcontractors | 16222.07 | 2026-09-25 | 0 | 16222.07 | 0 | 0 | 0 | 0 | RCT rate 20%; reverse charge VAT.
Coatline Decorators | CF-2602 decoration: payment held, RCT at 35% applies | Subcontractors | 12166.55 | 2026-08-25 | 6 | 0 | 12166.55 | 0 | 0 | 0 | RCT rate 35%; reverse charge VAT.
Fingal Builders Merchants Ltd | July and August statement balances | Materials | 136001.98 | 2026-09-30 | 0 | 136001.98 | 0 | 0 | 0 | 0 | Monthly account, end of following month.
Northside Timber and Insulation Ltd | July and August statement balances | Materials | 108001.58 | 2026-09-30 | 0 | 108001.58 | 0 | 0 | 0 | 0 | Monthly account, end of following month.
Dublin Drylining Supplies Ltd | July and August statement balances | Materials | 88001.28 | 2026-10-15 | 0 | 88001.28 | 0 | 0 | 0 | 0 | Monthly account, end of following month.
Meridian Electrical Wholesale Ltd | July and August statement balances | Materials | 68001 | 2026-09-30 | 0 | 68001 | 0 | 0 | 0 | 0 | Monthly account, end of following month.
Blackrock Plant Hire Ltd | Access equipment and small plant, August | Plant and site services | 48253.37 | 2026-09-30 | 0 | 48253.37 | 0 | 0 | 0 | 0 | 30-day terms.
Skipway Waste Services Ltd | Skips and waste, August | Plant and site services | 32518.58 | 2026-09-30 | 0 | 32518.58 | 0 | 0 | 0 | 0 | 30-day terms.
SiteServ Welfare Units Ltd | Welfare units and site services, August | Plant and site services | 24126.69 | 2026-09-30 | 0 | 24126.69 | 0 | 0 | 0 | 0 | 30-day terms.
Anchor Fleet Services Ltd | Fuel cards and fleet maintenance, August | Overheads | 16930.06 | 2026-09-20 | 0 | 16930.06 | 0 | 0 | 0 | 0
Crossfield Recruitment (agency operatives) | Agency labour, August | Overheads | 12415.38 | 2026-09-20 | 0 | 12415.38 | 0 | 0 | 0 | 0
Harcourt Insurance Brokers | Bond commission and insurance instalments | Overheads | 10158.04 | 2026-09-20 | 0 | 10158.04 | 0 | 0 | 0 | 0
Glenview Business Parks Ltd | September rent, invoiced in advance | Overheads | 6772.02 | 2026-09-20 | 0 | 6772.02 | 0 | 0 | 0 | 0
Sundry overhead suppliers (16 invoices) | IT, marketing, professional and office costs | Overheads | 10158.03 | 2026-09-20 | 0 | 10158.03 | 0 | 0 | 0 | 0
TOTAL |  |  | 966889.85 |  |  | 954723.3 | 12166.55 | 0 | 0 | 0
Share of total | [5 empty] | 98.74% | 1.258% | 0% | 0% | 0%
Subcontractors: aging vs schedule |  |  | 405551.84 | Ledger balance | 405551.8435 | Difference | 0
Materials suppliers: aging vs schedule |  |  | 400005.84 | Ledger balance | 400005.8374 | Difference | 0
Plant hire and site services: aging vs schedule |  |  | 104898.64 | Ledger balance | 104898.6373 | Difference | 0
Overhead suppliers: aging vs schedule |  |  | 56433.53 | Ledger balance | 56433.5189 | Difference | 0

## Payables
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
TRADE PAYABLES BY SUPPLIER GROUP, SUBCONTRACTOR RETENTIONS AND RCT DEDUCTIONS
Subcontract invoices carry no VAT (reverse charge); the company deducts RCT at the rate Revenue authorises and pays it over by the 23rd of the following month. Other groups are VAT-inclusive. Actual payments per bank; forecast payments sized to the days payable.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
SUBCONTRACTORS (reverse charge, RCT)
Accrued (invoices and applications for the month) |  | 3254897.6738 | 3338852.0841 | 242236.31 | 196943.08 | 156359.38 | 134286.39 | 161564.48 | 230389.47 | 312506.99 | 341480.45 | 394883.0107 | 393416.7836 | 364380.1475 | 326451.182 | 293509.1959 | 230158.5477 | 189010.3043 | 227893.3301 | 299359.8063 | 346549.2622 | 362109.975 | 345238.2541 | 301976.3336 | 267414.3504 | 246153.2166 | 229479.5079
Less: retention withheld / add: released | WIP | 75190.0883 | -8320.8198 | 8889.8915 | 6950.306 | 4478.838 | -7005.311 | -8743.4515 | 7479.414 | 11024.13 | 11993.0295 | 14613.0617 | 14854.0355 | 13521.6119 | -2865.4673 | 6455.7384 | 7663.5867 | -21046.529 | -14579.474 | -3203.6782 | 11840.3841 | 12428.7998 | 11594.1203 | 9444.0779 | -3506.5837 | 4811.144 | -30222.4063
Amount due to subcontractors | accrued - retention movement | 3179707.5854 | 3347172.9039 | 233346.4185 | 189992.774 | 151880.542 | 141291.701 | 170307.9315 | 222910.056 | 301482.86 | 329487.4205 | 380269.949 | 378562.7481 | 350858.5355 | 329316.6493 | 287053.4574 | 222494.961 | 210056.8333 | 242472.8041 | 302563.4845 | 334708.8781 | 349681.1752 | 333644.1338 | 292532.2557 | 270920.9341 | 241342.0726 | 259701.9142
Opening balance |  |  |  | 182000 | 252395.4585 | 218548.6225 | 180318.2245 | 158742.0755 | 174451.557 | 229204.573 | 336942.863 | 405551.8435 | 424201.605 | 429265.408 | 401333.5686 | 376097.7874 | 330962.344 | 260768.7553 | 239722.8281 | 270480.3819 | 334893.1917 | 375050.676 | 394309.0256 | 380268.2905 | 337018.1402 | 309925.2349 | 277464.8638
Paid (gross, before RCT) | A: bank; F: opening + due - closing at days payable | 2985609.7981 | 3431389.8341 | 162950.96 | 223839.61 | 190110.94 | 162867.85 | 154598.45 | 168157.04 | 193744.57 | 260878.44 | 361620.1874 | 373498.9452 | 378790.3749 | 354552.4305 | 332188.9008 | 292688.5497 | 231102.7605 | 211715.2503 | 238150.6747 | 294551.3938 | 330422.8256 | 347684.8689 | 335782.406 | 298013.8395 | 273802.4437 | 245285.9208
CLOSING BALANCE |  | 376097.7874 | 291880.8572 | 252395.4585 | 218548.6225 | 180318.2245 | 158742.0755 | 174451.557 | 229204.573 | 336942.863 | 405551.8435 | 424201.605 | 429265.408 | 401333.5686 | 376097.7874 | 330962.344 | 260768.7553 | 239722.8281 | 270480.3819 | 334893.1917 | 375050.676 | 394309.0256 | 380268.2905 | 337018.1402 | 309925.2349 | 277464.8638 | 291880.8572
RCT deducted from payments | gross paid x blended RCT rate | 110467.5625 | 126961.4239 | 6029.1855 | 8282.0656 | 7034.1048 | 6026.1105 | 5720.1426 | 6221.8105 | 7168.5491 | 9652.5023 | 13379.9469 | 13819.461 | 14015.2439 | 13118.4399 | 12290.9893 | 10829.4763 | 8550.8021 | 7833.4643 | 8811.575 | 10898.4016 | 12225.6445 | 12864.3401 | 12423.949 | 11026.5121 | 10130.6904 | 9075.5791
Cash paid to subcontractors (net of RCT) |  | 2875142.2355 | 3304428.4102 | 156921.7745 | 215557.5444 | 183076.8352 | 156841.7395 | 148878.3073 | 161935.2295 | 186576.0209 | 251225.9377 | 348240.2405 | 359679.4842 | 364775.131 | 341433.9906 | 319897.9115 | 281859.0733 | 222551.9584 | 203881.786 | 229339.0997 | 283652.9922 | 318197.181 | 334820.5288 | 323358.457 | 286987.3274 | 263671.7532 | 236210.3417
MATERIALS SUPPLIERS (incl. 23% VAT)
Accrued (invoices and applications for the month) |  | 2411992.2607 | 2538461.0683 | 169389.4869 | 135899.7972 | 126625.548 | 117808.5513 | 137779.2126 | 187654.4457 | 237662.2113 | 250031.0544 | 280538.788 | 276290.7561 | 258485.3892 | 233827.02 | 213088.4585 | 176048.0159 | 153158.7121 | 177297.6665 | 222180.5477 | 252725.5982 | 263334.2925 | 253857.0306 | 230001.0127 | 211228.2523 | 199193.5325 | 186347.9489
Opening balance |  |  |  | 148000 | 218555.8369 | 214146.3441 | 210234.8021 | 179830.1234 | 189119.496 | 261846.9917 | 362464.743 | 400005.8374 | 413888.6837 | 425911.443 | 405840.4591 | 371685.8943 | 337796.2026 | 289695.1938 | 247050.9873 | 258982.313 | 316739.3031 | 371221.8903 | 398121.2782 | 394301.9865 | 365391.4289 | 333895.459 | 311848.6004
Paid | A: bank; F: opening + due - closing at days payable | 2188306.3664 | 2617562.463 | 98833.65 | 140309.29 | 130537.09 | 148213.23 | 128489.84 | 114926.95 | 137044.46 | 212489.96 | 266655.9417 | 264267.9967 | 278556.3731 | 267981.5849 | 246978.1502 | 224149.0247 | 195802.9186 | 165366.3408 | 164423.5575 | 198243.011 | 236434.9046 | 257676.3222 | 258911.5702 | 242724.2222 | 221240.3911 | 205612.0497
CLOSING BALANCE |  | 371685.8943 | 292584.4996 | 218555.8369 | 214146.3441 | 210234.8021 | 179830.1234 | 189119.496 | 261846.9917 | 362464.743 | 400005.8374 | 413888.6837 | 425911.443 | 405840.4591 | 371685.8943 | 337796.2026 | 289695.1938 | 247050.9873 | 258982.313 | 316739.3031 | 371221.8903 | 398121.2782 | 394301.9865 | 365391.4289 | 333895.459 | 311848.6004 | 292584.4996
PLANT HIRE AND SITE SERVICES (incl. 23% VAT)
Accrued (invoices and applications for the month) |  | 887522.1051 | 924365.0502 | 60485.9019 | 49657.3878 | 42652.2918 | 41443.5708 | 50586.948 | 67480.7766 | 87855.5052 | 93193.7052 | 105265.0089 | 104026.6327 | 97039.2702 | 87835.106 | 80455.6701 | 66517.0081 | 56339.2317 | 63938.399 | 80572.7675 | 91868.4874 | 95710.7098 | 92001.3892 | 82829.6628 | 75622.1138 | 71493.7099 | 67015.9011
Opening balance |  |  |  | 41000 | 61614.4819 | 48915.2997 | 42861.8215 | 39095.4823 | 51569.1803 | 73416.6069 | 76893.3621 | 104898.6373 | 105265.0089 | 104026.6327 | 97039.2702 | 87835.106 | 80455.6701 | 66517.0081 | 56339.2317 | 63938.399 | 80572.7675 | 91868.4874 | 95710.7098 | 92001.3892 | 82829.6628 | 75622.1138 | 71493.7099
Paid | A: bank; F: opening + due - closing at days payable | 840686.9991 | 945184.255 | 39871.42 | 62356.57 | 48705.77 | 45209.91 | 38113.25 | 45633.35 | 84378.75 | 65188.43 | 104898.6373 | 105265.0089 | 104026.6327 | 97039.2702 | 87835.106 | 80455.6701 | 66517.0081 | 56339.2317 | 63938.399 | 80572.7675 | 91868.4874 | 95710.7098 | 92001.3892 | 82829.6628 | 75622.1138 | 71493.7099
CLOSING BALANCE |  | 87835.106 | 67015.9011 | 61614.4819 | 48915.2997 | 42861.8215 | 39095.4823 | 51569.1803 | 73416.6069 | 76893.3621 | 104898.6373 | 105265.0089 | 104026.6327 | 97039.2702 | 87835.106 | 80455.6701 | 66517.0081 | 56339.2317 | 63938.399 | 80572.7675 | 91868.4874 | 95710.7098 | 92001.3892 | 82829.6628 | 75622.1138 | 71493.7099 | 67015.9011
OVERHEAD, FLEET AND AGENCY SUPPLIERS
Accrued (invoices and applications for the month) |  | 854081.4594 | 774750.4455 | 57361.4113 | 57190.4182 | 61684.2088 | 63844.0733 | 62972.0493 | 63686.4479 | 69181.3851 | 65328.5651 | 111259.1801 | 105198.0908 | 73742.7403 | 62632.8893 | 64833.9871 | 64833.9871 | 64584.6538 | 64447.3205 | 64471.3205 | 64471.3205 | 64522.5205 | 64565.7205 | 64679.3205 | 64540.9871 | 64516.9871 | 64282.3205
Opening balance |  |  |  | 38000 | 51160.6213 | 43646.2395 | 51745.4983 | 52506.7116 | 52841.7109 | 46566.5087 | 57268.9238 | 56433.5189 | 89007.3441 | 84158.4726 | 58994.1922 | 50106.3115 | 51867.1897 | 51867.1897 | 51667.723 | 51557.8564 | 51577.0564 | 51577.0564 | 51618.0164 | 51652.5764 | 51743.4564 | 51632.7897 | 51613.5897
Paid | A: bank; F: opening + due - closing at days payable | 841975.1479 | 773430.9006 | 44200.79 | 64704.8 | 53584.95 | 63082.86 | 62637.05 | 69961.65 | 58478.97 | 66163.97 | 78685.3549 | 110046.9622 | 98907.0207 | 71520.7701 | 63073.1089 | 64833.9871 | 64784.1205 | 64557.1871 | 64452.1205 | 64471.3205 | 64481.5605 | 64531.1605 | 64588.4405 | 64651.6538 | 64536.1871 | 64470.0538
CLOSING BALANCE |  | 50106.3115 | 51425.8564 | 51160.6213 | 43646.2395 | 51745.4983 | 52506.7116 | 52841.7109 | 46566.5087 | 57268.9238 | 56433.5189 | 89007.3441 | 84158.4726 | 58994.1922 | 50106.3115 | 51867.1897 | 51867.1897 | 51667.723 | 51557.8564 | 51577.0564 | 51577.0564 | 51618.0164 | 51652.5764 | 51743.4564 | 51632.7897 | 51613.5897 | 51425.8564
TOTALS
TRADE PAYABLES (to balance sheet, excl. subcontractor retentions) |  | 885725.0991 | 702907.1143 | 583726.3986 | 525256.5058 | 485160.3464 | 430174.3928 | 467981.9442 | 611034.6803 | 833569.8919 | 966889.8371 | 1032362.6417 | 1043361.9564 | 963207.4901 | 885725.0991 | 801081.4063 | 668848.1469 | 594780.77 | 644958.9502 | 783782.3187 | 889718.1101 | 939759.0299 | 918224.2426 | 836982.6883 | 771075.5974 | 712420.7637 | 702907.1143
Subcontractor days payable (memo) |  |  |  | 32.449 | 34.509 | 35.6171 | 33.7052 | 30.7299 | 30.8471 | 33.5286 | 36.9257 | 33.4658 | 34.018 | 34.3158 | 34.2617 | 34.5889 | 35.1606 | 34.2369 | 33.4652 | 33.2056 | 33.6158 | 33.8287 | 34.1923 | 34.5622 | 34.3191 | 34.4902 | 33.7172

## VAT_RCT
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
VAT (BI-MONTHLY RETURNS) AND RCT (MONTHLY)
Output VAT at 13.5% on construction services to homeowners and commercial clients; council contracts are reverse charged (the council accounts for the VAT). Subcontractor services to the company are reverse charged: output and input VAT net to zero. VAT is paid by the 23rd of the month after each two-month period; RCT by the 23rd of the following month (ROS).
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
OUTPUT VAT
Retrofit invoices and SEAI claims | Residential | 285010.245 | 387623.9919 | 21549.6575 | 19574.2304 | 17453.0997 | 19340.2939 | 19033.7475 | 20750.9226 | 20841.6889 | 25229.9133 | 30041.5259 | 32088.0967 | 30513.6351 | 28593.4334 | 26187.2698 | 24402.8125 | 24868.9546 | 27168.4811 | 31396.7415 | 34698.1409 | 36483.2504 | 36894.1591 | 36883.1301 | 36984.2371 | 36357.7111 | 35299.1038
Renovation invoices | Residential | 268956.2771 | 292419.9845 | 18365.2704 | 15167.9874 | 20534.6633 | 18901.7592 | 24961.0242 | 23922.069 | 27812.1659 | 24041.227 | 26054.0359 | 23306.4386 | 24261.7153 | 21627.9209 | 21775.016 | 20024.2223 | 20578.2288 | 21751.7904 | 23726.4274 | 25616.0737 | 26572.5346 | 26957.3026 | 27253.1267 | 26957.3292 | 26272.586 | 24935.3469
Commercial fit-out invoices | WIP | 404821.368 | 368497.5422 | 22443.6025 | 18225.8973 | 19348.7684 | 16417.8967 | 14884.7836 | 17891.3572 | 28451.8214 | 41781.3016 | 41872.4767 | 59428.4363 | 62036.2243 | 62038.802 | 51519.0932 | 48846.7596 | 42384.1507 | 30301.0593 | 17082.6753 | 24703.4692 | 29941.5592 | 31319.5053 | 28425.7707 | 24909.8462 | 17434.4859 | 21629.1676
Council invoices (reverse charge: accounted by the council) | WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy retention release invoices | Retentions | 6412.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847.5 | 2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reverse charge on subcontractor services (T1) | subcontract cost x 13.5% | 439411.186 | 450745.0314 | 32701.9018 | 26587.3158 | 21108.5163 | 18128.6626 | 21811.2048 | 31102.5785 | 42188.4437 | 46099.8607 | 53309.2064 | 53111.2658 | 49191.3199 | 44070.9096 | 39623.7414 | 31071.4039 | 25516.3911 | 30765.5996 | 40413.5738 | 46784.1504 | 48884.8466 | 46607.1643 | 40766.805 | 36100.9373 | 33230.6842 | 30979.7336
Total output VAT |  | 1404611.5761 | 1499286.5499 | 95060.4322 | 79555.431 | 78445.0477 | 72788.6124 | 80690.7601 | 93666.9272 | 119294.1199 | 137152.3027 | 151277.2449 | 167934.2373 | 169850.3947 | 158896.0659 | 139105.1205 | 124345.1982 | 113347.725 | 109986.9303 | 112619.418 | 131801.8343 | 141882.1909 | 141778.1312 | 133328.8326 | 124952.3497 | 113295.4673 | 112843.3519
INPUT VAT (recoverable)
Reverse charge on subcontractor services (T2) |  | 439411.186 | 450745.0314 | 32701.9018 | 26587.3158 | 21108.5163 | 18128.6626 | 21811.2048 | 31102.5785 | 42188.4437 | 46099.8607 | 53309.2064 | 53111.2658 | 49191.3199 | 44070.9096 | 39623.7414 | 31071.4039 | 25516.3911 | 30765.5996 | 40413.5738 | 46784.1504 | 48884.8466 | 46607.1643 | 40766.805 | 36100.9373 | 33230.6842 | 30979.7336
Materials | cost x 23% | 451022.9431 | 474671.5819 | 31674.4569 | 25412.1572 | 23677.948 | 22029.2413 | 25763.5926 | 35089.8557 | 44440.9013 | 46753.7744 | 52458.4725 | 51664.1251 | 48334.6663 | 43723.7517 | 39845.8093 | 32919.5477 | 28639.434 | 33153.2222 | 41545.9561 | 47257.6322 | 49241.3718 | 47469.2008 | 43008.3194 | 39497.9659 | 37247.5711 | 34845.5514
Plant hire and site services |  | 165959.418 | 172848.7492 | 11310.3719 | 9285.5278 | 7975.6318 | 7749.6108 | 9459.348 | 12618.3566 | 16428.2652 | 17426.4652 | 19683.7008 | 19452.1346 | 18145.5546 | 16424.4507 | 15044.5562 | 12438.1397 | 10534.9783 | 11955.9608 | 15066.4525 | 17178.6603 | 17897.1246 | 17203.5118 | 15488.4735 | 14140.7205 | 13368.7425 | 12531.4287
Overheads |  | 66511.0642 | 70241.5087 | 5189.3566 | 5136.0242 | 5695.1588 | 5910.77 | 5915.1906 | 5406.2512 | 5566.2484 | 5070.0004 | 5655.516 | 5655.516 | 5655.516 | 5655.516 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591 | 5853.4591
Fleet and agency |  | 45982.7584 | 24989.5368 | 1880.388 | 1892.394 | 1894.05 | 1940.97 | 1833.192 | 2624.53 | 3355.47 | 3452.898 | 11085.0646 | 9951.6901 | 4060.0717 | 2012.04 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614 | 2082.4614
Capex |  | 13524 | 24127.92 | 414 | 0 | 1518 | 9062 | 0 | 713 | 276 | 437 | 276 | 276 | 276 | 276 | 3045.66 | 285.66 | 18225.66 | 285.66 | 285.66 | 285.66 | 285.66 | 285.66 | 285.66 | 285.66 | 285.66 | 285.66
Total input VAT |  | 1182411.3697 | 1217624.328 | 83170.4753 | 68313.419 | 61869.3049 | 64821.2548 | 64782.528 | 87554.5719 | 112255.3286 | 119239.9987 | 142467.9604 | 140110.7316 | 125663.1285 | 112162.668 | 105495.6874 | 84650.6718 | 90852.3838 | 84096.363 | 105247.5628 | 119442.0233 | 124244.9234 | 119501.4574 | 107485.1785 | 97961.2041 | 92068.5783 | 86578.2941
VAT PAYABLE
Net VAT for the month (output - input) |  | 222200.2064 | 281662.2219 | 11889.957 | 11242.012 | 16575.7428 | 7967.3576 | 15908.2321 | 6112.3553 | 7038.7914 | 17912.304 | 8809.2845 | 27823.5057 | 44187.2662 | 46733.3979 | 33609.433 | 39694.5264 | 22495.3413 | 25890.5673 | 7371.8552 | 12359.811 | 17637.2674 | 22276.6738 | 25843.6541 | 26991.1456 | 21226.889 | 26265.0578
Opening VAT payable / (repayable) |  |  |  | 46300 | 11889.957 | 23131.969 | 16575.7428 | 24543.1004 | 15908.2321 | 22020.5874 | 7038.7914 | 24951.0953 | 8809.2845 | 36632.7902 | 44187.2662 | 90920.6641 | 33609.433 | 73303.9595 | 22495.3413 | 48385.9085 | 7371.8552 | 19731.6662 | 17637.2674 | 39913.9413 | 25843.6541 | 52834.7997 | 21226.889
VAT paid / (repaid): prior two months, by the 23rd | Timeline flag | -177579.5423 | -325090.9393 | -46300 | 0 | -23131.969 | 0 | -24543.1004 | 0 | -22020.5874 | 0 | -24951.0953 | 0 | -36632.7902 | 0 | -90920.6641 | 0 | -73303.9595 | 0 | -48385.9085 | 0 | -19731.6662 | 0 | -39913.9413 | 0 | -52834.7997 | 0
CLOSING VAT PAYABLE / (REPAYABLE) |  | 90920.6641 | 47491.9467 | 11889.957 | 23131.969 | 16575.7428 | 24543.1004 | 15908.2321 | 22020.5874 | 7038.7914 | 24951.0953 | 8809.2845 | 36632.7902 | 44187.2662 | 90920.6641 | 33609.433 | 73303.9595 | 22495.3413 | 48385.9085 | 7371.8552 | 19731.6662 | 17637.2674 | 39913.9413 | 25843.6541 | 52834.7997 | 21226.889 | 47491.9467
RCT (RELEVANT CONTRACTS TAX) PAYABLE
Opening balance |  |  |  | 5200 | 6029.1855 | 8282.0656 | 7034.1048 | 6026.1105 | 5720.1426 | 6221.8105 | 7168.5491 | 9652.5023 | 13379.9469 | 13819.461 | 14015.2439 | 13118.4399 | 12290.9893 | 10829.4763 | 8550.8021 | 7833.4643 | 8811.575 | 10898.4016 | 12225.6445 | 12864.3401 | 12423.949 | 11026.5121 | 10130.6904
Deducted from subcontractor payments | Payables | 110467.5625 | 126961.4239 | 6029.1855 | 8282.0656 | 7034.1048 | 6026.1105 | 5720.1426 | 6221.8105 | 7168.5491 | 9652.5023 | 13379.9469 | 13819.461 | 14015.2439 | 13118.4399 | 12290.9893 | 10829.4763 | 8550.8021 | 7833.4643 | 8811.575 | 10898.4016 | 12225.6445 | 12864.3401 | 12423.949 | 11026.5121 | 10130.6904 | 9075.5791
Paid to Revenue (prior month, by the 23rd) |  | -102549.1226 | -131004.2847 | -5200 | -6029.1855 | -8282.0656 | -7034.1048 | -6026.1105 | -5720.1426 | -6221.8105 | -7168.5491 | -9652.5023 | -13379.9469 | -13819.461 | -14015.2439 | -13118.4399 | -12290.9893 | -10829.4763 | -8550.8021 | -7833.4643 | -8811.575 | -10898.4016 | -12225.6445 | -12864.3401 | -12423.949 | -11026.5121 | -10130.6904
CLOSING RCT PAYABLE |  | 13118.4399 | 9075.5791 | 6029.1855 | 8282.0656 | 7034.1048 | 6026.1105 | 5720.1426 | 6221.8105 | 7168.5491 | 9652.5023 | 13379.9469 | 13819.461 | 14015.2439 | 13118.4399 | 12290.9893 | 10829.4763 | 8550.8021 | 7833.4643 | 8811.575 | 10898.4016 | 12225.6445 | 12864.3401 | 12423.949 | 11026.5121 | 10130.6904 | 9075.5791

## Resources
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
SITE RESOURCES: HEADCOUNT, LABOUR UTILISATION AND RECOVERY, AGENCY AND FLEET
Own labour is charged to jobs at the standard hourly rate. Hours required above the productive hours available are bought from an agency. Recovery variance = labour charged to jobs less site payroll and agency cost (negative = under-recovery, charged to the P&L below gross profit).
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
SITE HEADCOUNT PLAN AND PAY RATES
Monthly gross pay per head: site supervisors and foremen (column C, FY2026 rate) | input | 5300
Monthly gross pay per head: craft operatives (carpentry, drylining, finishing) (column C, FY2026 rate) | input | 4050
Monthly gross pay per head: retrofit installers (insulation, airtightness) (column C, FY2026 rate) | input | 3700
Monthly gross pay per head: general operatives (column C, FY2026 rate) | input | 3250
Planned change in headcount: site supervisors and foremen | input, forecast months | 0 | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned change in headcount: craft operatives (carpentry, drylining, finishing) | input, forecast months | 0 | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned change in headcount: retrofit installers (insulation, airtightness) | input, forecast months | 2 | 0 | [8 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned change in headcount: general operatives | input, forecast months | 0 | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Headcount: site supervisors and foremen | A: payroll; F: prior month + planned change x hiring flag | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Headcount: craft operatives (carpentry, drylining, finishing) | A: payroll; F: prior month + planned change x hiring flag | 11 | 12 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Headcount: retrofit installers (insulation, airtightness) | A: payroll; F: prior month + planned change x hiring flag | 10 | 10 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Headcount: general operatives | A: payroll; F: prior month + planned change x hiring flag | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SITE HEADCOUNT |  | 29 | 32 | 25 | 25 | 25 | 24 | 24 | 26 | 27 | 27 | 27 | 27 | 29 | 29 | 29 | 30 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
SITE PAYROLL COST
Site gross pay | A: payroll; F: headcount x pay rate x inflation | 1273971 | 1566731.25 | 100577 | 100073 | 103197 | 98593 | 98614 | 103650 | 112754 | 108313 | 108350 | 108350 | 115750 | 115750 | 119801.25 | 123993 | 127356.75 | 132842.25 | 132842.25 | 132842.25 | 132842.25 | 132842.25 | 132842.25 | 132842.25 | 132842.25 | 132842.25
Employer PRSI | gross x rate in force | 143831.5125 | 178607.3625 | 11314.9125 | 11258.2125 | 11609.6625 | 11091.7125 | 11094.075 | 11660.625 | 12684.825 | 12185.2125 | 12189.375 | 12351.9 | 13195.5 | 13195.5 | 13657.3425 | 14135.202 | 14518.6695 | 15144.0165 | 15144.0165 | 15144.0165 | 15144.0165 | 15144.0165 | 15144.0165 | 15144.0165 | 15144.0165 | 15144.0165
Employer pension and other employment costs |  | 63698.55 | 78336.5625 | 5028.85 | 5003.65 | 5159.85 | 4929.65 | 4930.7 | 5182.5 | 5637.7 | 5415.65 | 5417.5 | 5417.5 | 5787.5 | 5787.5 | 5990.0625 | 6199.65 | 6367.8375 | 6642.1125 | 6642.1125 | 6642.1125 | 6642.1125 | 6642.1125 | 6642.1125 | 6642.1125 | 6642.1125 | 6642.1125
SITE PAYROLL COST |  | 1481501.0625 | 1823675.175 | 116920.7625 | 116334.8625 | 119966.5125 | 114614.3625 | 114638.775 | 120493.125 | 131076.525 | 125913.8625 | 125956.875 | 126119.4 | 134733 | 134733 | 139448.655 | 144327.852 | 148243.257 | 154628.379 | 154628.379 | 154628.379 | 154628.379 | 154628.379 | 154628.379 | 154628.379 | 154628.379 | 154628.379
UTILISATION AND RECOVERY
Productive hours available | headcount x productive hours | 44100 | 52920 | 3500 | 3500 | 3500 | 3360 | 3360 | 3640 | 3780 | 3780 | 3780 | 3780 | 4060 | 4060 | 4060 | 4200 | 4340 | 4480 | 4480 | 4480 | 4480 | 4480 | 4480 | 4480 | 4480 | 4480
Own labour charged to jobs at standard rate | WIP + Residential labour lines | 1579361.4108 | 1742797.419 | 107708.23 | 89643.43 | 84766.52 | 82567.4 | 98827.85 | 117650.17 | 151488.72 | 165295.61 | 182463.05 | 178321.6725 | 167853.5573 | 152775.201 | 140021.0844 | 120081.2377 | 109325.982 | 124258.4904 | 150757.499 | 169030.7227 | 175507.0251 | 170394.3187 | 158296.7383 | 149087.5366 | 142634.9997 | 133401.7843
Standard hourly rate in force | FY2026 rate x inflation | 39.5 | 40.8825 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825 | 40.8825
Hours charged to jobs | labour charged / standard rate | 39983.8332 | 42629.4238 | 2726.7906 | 2269.4539 | 2145.9878 | 2090.3139 | 2501.9709 | 2978.4853 | 3835.1575 | 4184.699 | 4619.3177 | 4514.4727 | 4249.4571 | 3867.7266 | 3424.9638 | 2937.2283 | 2674.1511 | 3039.4054 | 3687.5802 | 4134.5496 | 4292.9622 | 4167.9036 | 3871.9926 | 3646.7324 | 3488.9011 | 3263.0535
Hours worked by own operatives | min(required, available) | 37760.7291 | 42629.4238 | 2726.7906 | 2269.4539 | 2145.9878 | 2090.3139 | 2501.9709 | 2978.4853 | 3780 | 3780 | 3780 | 3780 | 4060 | 3867.7266 | 3424.9638 | 2937.2283 | 2674.1511 | 3039.4054 | 3687.5802 | 4134.5496 | 4292.9622 | 4167.9036 | 3871.9926 | 3646.7324 | 3488.9011 | 3263.0535
Utilisation of productive hours |  | 85.63% | 80.55% | 77.91% | 64.84% | 61.31% | 62.21% | 74.46% | 81.83% | 100% | 100% | 100% | 100% | 100% | 95.26% | 84.36% | 69.93% | 61.62% | 67.84% | 82.31% | 92.29% | 95.83% | 93.03% | 86.43% | 81.4% | 77.88% | 72.84%
Agency hours (required above available) |  | 2223.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.1575 | 404.699 | 839.3177 | 734.4727 | 189.4571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agency operatives cost | A: invoices; F: agency hours x rate | 97772.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 5400 | 6900 | 39447.9329 | 34520.218 | 8904.4859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LABOUR RECOVERY VARIANCE (+ over / - under-recovery) | charged to jobs - payroll - agency | 87.7116 | -80877.756 | -9212.5325 | -26691.4325 | -35199.9925 | -32046.9625 | -15810.925 | -5442.955 | 15012.195 | 32481.7475 | 17058.2421 | 17682.0546 | 24216.0714 | 18042.201 | 572.4294 | -24246.6143 | -38917.275 | -30369.8886 | -3870.88 | 14402.3437 | 20878.6461 | 15765.9397 | 3668.3593 | -5540.8424 | -11993.3793 | -21226.5947
Recovery % (charged to jobs / payroll and agency) |  | 100% | 95.57% | 92.12% | 77.06% | 70.66% | 72.04% | 86.21% | 95.58% | 111% | 124.5% | 110.3% | 111% | 116.9% | 113.4% | 100.4% | 83.2% | 73.75% | 80.36% | 97.5% | 109.3% | 113.5% | 110.2% | 102.4% | 96.42% | 92.24% | 86.27%
FLEET AND SMALL TOOLS
Vans | A: fleet register; F: last actual (replacements like for like) | 13 | 13 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Fleet running costs and small tools | A: ledger; F: vans x cost per van + tools, inflated | 170254 | 181083.6 | 13626 | 13713 | 13725 | 14065 | 13284 | 14685 | 15315 | 13521 | 14580 | 14580 | 14580 | 14580 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3 | 15090.3
Fleet cost per own labour hour (memo) |  |  |  | 4.9971 | 6.0424 | 6.3957 | 6.7287 | 5.3094 | 4.9304 | 4.0516 | 3.577 | 3.8571 | 3.8571 | 3.5911 | 3.7697 | 4.406 | 5.1376 | 5.643 | 4.9649 | 4.0922 | 3.6498 | 3.5151 | 3.6206 | 3.8973 | 4.138 | 4.3252 | 4.6246

## Overheads
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
OFFICE PAYROLL, OVERHEADS AND PAYROLL TAXES (EUR, ex VAT)
Office payroll from the staff table (planned hires switched by the scenario). Overhead lines: actual months from the ledger; forecast from the monthly base in column C with inflation from FY2027 and the discretionary factor on marketing, training and motor.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
OFFICE STAFF (C = monthly gross pay, D = start month; planned hires only if the scenario allows)
Managing Director (founder) | gross x inflation x active flag | 8500 | 2019-03-31 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5 | 8797.5
Finance Manager | gross x inflation x active flag | 5800 | 2021-09-30 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003 | 6003
Commercial Manager (quantity surveyor) | gross x inflation x active flag | 6500 | 2020-05-31 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5 | 6727.5
Quantity Surveyor | gross x inflation x active flag | 4600 | 2023-02-28 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761 | 4761
Estimator | gross x inflation x active flag | 4800 | 2022-06-30 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968 | 4968
Retrofit Coordinator (One Stop Shop) | gross x inflation x active flag | 4100 | 2022-01-31 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5 | 4243.5
Customer Care Coordinator 1 | gross x inflation x active flag | 3000 | 2023-08-31 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105
Customer Care Coordinator 2 | gross x inflation x active flag | 3000 | 2024-04-30 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105 | 3105
Health, Safety and Office Administrator | gross x inflation x active flag | 3400 | 2021-01-31 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519 | 3519
Planned hire: second Retrofit Coordinator | gross x inflation x active flag | 4200 | 2026-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347
Planned hire: Contracts Manager (commercial) | gross x inflation x active flag | 6200 | 2027-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417 | 6417
Office gross pay per staff table | sum of roles | 532800 | 671922 | 43700 | 43700 | 43700 | 43700 | 43700 | 43700 | 43700 | 43700 | 43700 | 43700 | 47900 | 47900 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5
Office gross pay | A: payroll; F: staff table | 518648 | 671922 | 43634 | 43301 | 39568 | 39249 | 39045 | 43840 | 43272 | 43539 | 43700 | 43700 | 47900 | 47900 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5 | 55993.5
Employer PRSI |  | 58557.15 | 76599.108 | 4908.825 | 4871.3625 | 4451.4 | 4415.5125 | 4392.5625 | 4932 | 4868.1 | 4898.1375 | 4916.25 | 4981.8 | 5460.6 | 5460.6 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259 | 6383.259
Employer pension and other employment costs |  | 25932.4 | 33596.1 | 2181.7 | 2165.05 | 1978.4 | 1962.45 | 1952.25 | 2192 | 2163.6 | 2176.95 | 2185 | 2185 | 2395 | 2395 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675 | 2799.675
OFFICE PAYROLL COST |  | 603137.55 | 782117.208 | 50724.525 | 50337.4125 | 45997.8 | 45626.9625 | 45389.8125 | 50964 | 50303.7 | 50614.0875 | 50801.25 | 50866.8 | 55755.6 | 55755.6 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434 | 65176.434
FORECAST MONTHLY BASE (column C, EUR at FY2026 prices)
Rent: office and yard | monthly base | 7400
Insurance (public, employer and contractors all risks) | monthly base | 9700
IT, software and estimating tools | monthly base | 3900
Marketing and lead generation (residential) (discretionary) | monthly base | 6800
Professional fees (audit, legal, tax) | monthly base | 4200
Training, health and safety, PPE (discretionary) | monthly base | 2800
Office and administration | monthly base | 2250
Motor (non-site vehicles) (discretionary) | monthly base | 1750
Subscriptions and memberships | monthly base | 860
OVERHEAD LINES
Rent: office and yard | A: ledger; F: base x inflation | 86912 | 91908 | 6023 | 5858 | 8709 | 7347 | 7358 | 7044 | 8501 | 6472 | 7400 | 7400 | 7400 | 7400 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659
Insurance (public, employer and contractors all risks) | A: ledger; F: base x inflation | 113931 | 120474 | 10070 | 8856 | 8959 | 9674 | 9909 | 9772 | 9369 | 8522 | 9700 | 9700 | 9700 | 9700 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5 | 10039.5
IT, software and estimating tools | A: ledger; F: base x inflation | 46834 | 48438 | 3706 | 4237 | 4035 | 4028 | 3676 | 4033 | 3989 | 3530 | 3900 | 3900 | 3900 | 3900 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5 | 4036.5
Marketing and lead generation (residential) | A: ledger; F: base x inflation x discretionary factor | 79676 | 84456 | 3684 | 5487 | 7730 | 8125 | 8707 | 6050 | 6484 | 6209 | 6800 | 6800 | 6800 | 6800 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038 | 7038
Professional fees (audit, legal, tax) | A: ledger; F: base x inflation | 49640 | 52164 | 5000 | 4331 | 3264 | 4655 | 4063 | 3755 | 3675 | 4097 | 4200 | 4200 | 4200 | 4200 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347 | 4347
Training, health and safety, PPE | A: ledger; F: base x inflation x discretionary factor | 31928 | 34776 | 3015 | 2508 | 2777 | 2372 | 3007 | 2630 | 1867 | 2552 | 2800 | 2800 | 2800 | 2800 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898 | 2898
Office and administration | A: ledger; F: base x inflation | 26868 | 27945 | 2372 | 2245 | 1938 | 2556 | 2479 | 2112 | 2318 | 1848 | 2250 | 2250 | 2250 | 2250 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75 | 2328.75
Motor (non-site vehicles) | A: ledger; F: base x inflation x discretionary factor | 20345 | 21735 | 1687 | 1848 | 1800 | 1716 | 1422 | 1619 | 1791 | 1462 | 1750 | 1750 | 1750 | 1750 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25 | 1811.25
Subscriptions and memberships | A: ledger; F: base x inflation | 10283 | 10681.2 | 834 | 647 | 726 | 977 | 860 | 897 | 1040 | 862 | 860 | 860 | 860 | 860 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1 | 890.1
Overhead lines subject to VAT and trade payables | sum of the lines above | 466417 | 492577.2 | 36391 | 36017 | 39938 | 41450 | 41481 | 37912 | 39034 | 35554 | 39660 | 39660 | 39660 | 39660 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1 | 41048.1
Bond commission | bonds outstanding x annual rate / 12 | 7144 | 5858.6 | 274.6667 | 432 | 432 | 477.3333 | 458.6667 | 458.6667 | 510.6667 | 830.6667 | 830.6667 | 830.6667 | 882.6667 | 725.3333 | 759.6667 | 759.6667 | 510.3333 | 373 | 397 | 397 | 448.2 | 491.4 | 605 | 466.6667 | 442.6667 | 208
Bad debts and specific provisions | Retentions (legacy dispute) | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OVERHEADS | office payroll + lines + bond commission + bad debts | 1086198.55 | 1280553.008 | 87390.1917 | 86786.4125 | 86367.8 | 87554.2958 | 87329.4792 | 98834.6667 | 89848.3667 | 86998.7542 | 91291.9167 | 91357.4667 | 96298.2667 | 96140.9333 | 106984.2007 | 106984.2007 | 106734.8673 | 106597.534 | 106621.534 | 106621.534 | 106672.734 | 106715.934 | 106829.534 | 106691.2007 | 106667.2007 | 106432.534
PAYE, USC, PRSI AND PENSION PAYABLE (site and office)
Gross pay, site and office |  | 1792619 | 2238653.25 | 144211 | 143374 | 142765 | 137842 | 137659 | 147490 | 156026 | 151852 | 152050 | 152050 | 163650 | 163650 | 175794.75 | 179986.5 | 183350.25 | 188835.75 | 188835.75 | 188835.75 | 188835.75 | 188835.75 | 188835.75 | 188835.75 | 188835.75 | 188835.75
Opening balance |  |  |  | 61800 | 58044.9275 | 57708.035 | 57462.9125 | 55481.405 | 55407.7475 | 59364.725 | 62800.465 | 61120.43 | 61200.125 | 61428.2 | 66114.6 | 66114.6 | 71021.079 | 72714.546 | 74073.501 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643
Accrued: employee deductions + employer PRSI + employer pension |  | 722248.1725 | 904415.913 | 58044.9275 | 57708.035 | 57462.9125 | 55481.405 | 55407.7475 | 59364.725 | 62800.465 | 61120.43 | 61200.125 | 61428.2 | 66114.6 | 66114.6 | 71021.079 | 72714.546 | 74073.501 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643
Paid (prior month liability, by the 23rd) |  | -717933.5725 | -894240.87 | -61800 | -58044.9275 | -57708.035 | -57462.9125 | -55481.405 | -55407.7475 | -59364.725 | -62800.465 | -61120.43 | -61200.125 | -61428.2 | -66114.6 | -66114.6 | -71021.079 | -72714.546 | -74073.501 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643 | -76289.643
CLOSING BALANCE (to balance sheet) |  | 66114.6 | 76289.643 | 58044.9275 | 57708.035 | 57462.9125 | 55481.405 | 55407.7475 | 59364.725 | 62800.465 | 61120.43 | 61200.125 | 61428.2 | 66114.6 | 66114.6 | 71021.079 | 72714.546 | 74073.501 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643 | 76289.643
Net wages paid to site workforce (weekly) | gross less employee deductions | 968217.96 | 1190715.75 | 76438.52 | 76055.48 | 78429.72 | 74930.68 | 74946.64 | 78774 | 85693.04 | 82317.88 | 82346 | 82346 | 87970 | 87970 | 91048.95 | 94234.68 | 96791.13 | 100960.11 | 100960.11 | 100960.11 | 100960.11 | 100960.11 | 100960.11 | 100960.11 | 100960.11 | 100960.11
Net salaries paid to office staff (25th) |  | 394172.48 | 510660.72 | 33161.84 | 32908.76 | 30071.68 | 29829.24 | 29674.2 | 33318.4 | 32886.72 | 33089.64 | 33212 | 33212 | 36404 | 36404 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06 | 42555.06

## Fixed_Assets
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
FIXED ASSETS AND DEPRECIATION
Three classes, straight line over the lives on Assumptions. Actual capex from the asset register; forecast per the capex plan.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
VANS
Cost: opening |  |  |  | 395000 | 395000 | 395000 | 395000 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500
Additions | A: asset register; F: capex plan | 38500 | 78000 | 0 | 0 | 0 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: closing |  | 433500 | 511500 | 395000 | 395000 | 395000 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 433500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500 | 511500
Accumulated depreciation: opening |  |  |  | 178000 | 184583.3333 | 191166.6667 | 197750 | 204975 | 212200 | 219425 | 226650 | 233875 | 241100 | 248325 | 255550 | 262775 | 270000 | 277225 | 285750 | 294275 | 302800 | 311325 | 319850 | 328375 | 336900 | 345425 | 353950
Depreciation charge | min(NBV, cost / life) | 84775 | 99700 | 6583.3333 | 6583.3333 | 6583.3333 | 7225 | 7225 | 7225 | 7225 | 7225 | 7225 | 7225 | 7225 | 7225 | 7225 | 7225 | 8525 | 8525 | 8525 | 8525 | 8525 | 8525 | 8525 | 8525 | 8525 | 8525
Accumulated depreciation: closing |  | 262775 | 362475 | 184583.3333 | 191166.6667 | 197750 | 204975 | 212200 | 219425 | 226650 | 233875 | 241100 | 248325 | 255550 | 262775 | 270000 | 277225 | 285750 | 294275 | 302800 | 311325 | 319850 | 328375 | 336900 | 345425 | 353950 | 362475
Net book value |  | 170725 | 149025 | 210416.6667 | 203833.3333 | 197250 | 228525 | 221300 | 214075 | 206850 | 199625 | 192400 | 185175 | 177950 | 170725 | 163500 | 156275 | 225750 | 217225 | 208700 | 200175 | 191650 | 183125 | 174600 | 166075 | 157550 | 149025
PLANT AND TOOLS
Cost: opening |  |  |  | 118000 | 119800 | 119800 | 122200 | 123100 | 123100 | 126200 | 127400 | 127400 | 128600 | 129800 | 131000 | 132200 | 133442 | 134684 | 135926 | 137168 | 138410 | 139652 | 140894 | 142136 | 143378 | 144620 | 145862
Additions | A: asset register; F: capex plan | 14200 | 14904 | 1800 | 0 | 2400 | 900 | 0 | 3100 | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242
Cost: closing |  | 132200 | 147104 | 119800 | 119800 | 122200 | 123100 | 123100 | 126200 | 127400 | 127400 | 128600 | 129800 | 131000 | 132200 | 133442 | 134684 | 135926 | 137168 | 138410 | 139652 | 140894 | 142136 | 143378 | 144620 | 145862 | 147104
Accumulated depreciation: opening |  |  |  | 61000 | 63495.8333 | 65991.6667 | 68537.5 | 71102.0833 | 73666.6667 | 76295.8333 | 78950 | 81604.1667 | 84283.3333 | 86987.5 | 89716.6667 | 92470.8333 | 95250.875 | 98056.7917 | 100888.5833 | 103746.25 | 106629.7917 | 109539.2083 | 112474.5 | 115435.6667 | 118422.7083 | 121435.625 | 124474.4167
Depreciation charge | min(NBV, cost / life) | 31470.8333 | 35068.25 | 2495.8333 | 2495.8333 | 2545.8333 | 2564.5833 | 2564.5833 | 2629.1667 | 2654.1667 | 2654.1667 | 2679.1667 | 2704.1667 | 2729.1667 | 2754.1667 | 2780.0417 | 2805.9167 | 2831.7917 | 2857.6667 | 2883.5417 | 2909.4167 | 2935.2917 | 2961.1667 | 2987.0417 | 3012.9167 | 3038.7917 | 3064.6667
Accumulated depreciation: closing |  | 92470.8333 | 127539.0833 | 63495.8333 | 65991.6667 | 68537.5 | 71102.0833 | 73666.6667 | 76295.8333 | 78950 | 81604.1667 | 84283.3333 | 86987.5 | 89716.6667 | 92470.8333 | 95250.875 | 98056.7917 | 100888.5833 | 103746.25 | 106629.7917 | 109539.2083 | 112474.5 | 115435.6667 | 118422.7083 | 121435.625 | 124474.4167 | 127539.0833
Net book value |  | 39729.1667 | 19564.9167 | 56304.1667 | 53808.3333 | 53662.5 | 51997.9167 | 49433.3333 | 49904.1667 | 48450 | 45795.8333 | 44316.6667 | 42812.5 | 41283.3333 | 39729.1667 | 38191.125 | 36627.2083 | 35037.4167 | 33421.75 | 31780.2083 | 30112.7917 | 28419.5 | 26700.3333 | 24955.2917 | 23184.375 | 21387.5833 | 19564.9167
IT AND OFFICE
Cost: opening |  |  |  | 64000 | 64000 | 64000 | 68200 | 68200 | 68200 | 68200 | 68200 | 70100 | 70100 | 70100 | 70100 | 70100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100
Additions | A: asset register; F: capex plan | 6100 | 12000 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost: closing |  | 70100 | 82100 | 64000 | 64000 | 68200 | 68200 | 68200 | 68200 | 68200 | 70100 | 70100 | 70100 | 70100 | 70100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100 | 82100
Accumulated depreciation: opening |  |  |  | 41000 | 42777.7778 | 44555.5556 | 46450 | 48344.4444 | 50238.8889 | 52133.3333 | 54027.7778 | 55975 | 57922.2222 | 59869.4444 | 61816.6667 | 63763.8889 | 66044.4444 | 68325 | 70605.5556 | 72886.1111 | 75166.6667 | 77447.2222 | 79727.7778 | 82008.3333 | 82100 | 82100 | 82100
Depreciation charge | min(NBV, cost / life) | 22763.8889 | 18336.1111 | 1777.7778 | 1777.7778 | 1894.4444 | 1894.4444 | 1894.4444 | 1894.4444 | 1894.4444 | 1947.2222 | 1947.2222 | 1947.2222 | 1947.2222 | 1947.2222 | 2280.5556 | 2280.5556 | 2280.5556 | 2280.5556 | 2280.5556 | 2280.5556 | 2280.5556 | 2280.5556 | 91.6667 | 0 | 0 | 0
Accumulated depreciation: closing |  | 63763.8889 | 82100 | 42777.7778 | 44555.5556 | 46450 | 48344.4444 | 50238.8889 | 52133.3333 | 54027.7778 | 55975 | 57922.2222 | 59869.4444 | 61816.6667 | 63763.8889 | 66044.4444 | 68325 | 70605.5556 | 72886.1111 | 75166.6667 | 77447.2222 | 79727.7778 | 82008.3333 | 82100 | 82100 | 82100 | 82100
Net book value |  | 6336.1111 | 0 | 21222.2222 | 19444.4444 | 21750 | 19855.5556 | 17961.1111 | 16066.6667 | 14172.2222 | 14125 | 12177.7778 | 10230.5556 | 8283.3333 | 6336.1111 | 16055.5556 | 13775 | 11494.4444 | 9213.8889 | 6933.3333 | 4652.7778 | 2372.2222 | 91.6667 | 0 | 0 | 0 | 0
TOTAL
Capex |  | 58800 | 104904 | 1800 | 0 | 6600 | 39400 | 0 | 3100 | 1200 | 1900 | 1200 | 1200 | 1200 | 1200 | 13242 | 1242 | 79242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242 | 1242
Depreciation |  | 139009.7222 | 153104.3611 | 10856.9444 | 10856.9444 | 11023.6111 | 11684.0278 | 11684.0278 | 11748.6111 | 11773.6111 | 11826.3889 | 11851.3889 | 11876.3889 | 11901.3889 | 11926.3889 | 12285.5972 | 12311.4722 | 13637.3472 | 13663.2222 | 13689.0972 | 13714.9722 | 13740.8472 | 13766.7222 | 11603.7083 | 11537.9167 | 11563.7917 | 11589.6667
NET BOOK VALUE (to balance sheet) |  | 216790.2778 | 168589.9167 | 287943.0556 | 277086.1111 | 272662.5 | 300378.4722 | 288694.4444 | 280045.8333 | 269472.2222 | 259545.8333 | 248894.4444 | 238218.0556 | 227516.6667 | 216790.2778 | 217746.6806 | 206677.2083 | 272281.8611 | 259860.6389 | 247413.5417 | 234940.5694 | 222441.7222 | 209917 | 199555.2917 | 189259.375 | 178937.5833 | 168589.9167

## Debt
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
HIRE PURCHASE, OVERDRAFT FACILITY AND PERFORMANCE BONDS
Existing hire purchase repays at a fixed monthly principal; new agreements repay straight line over the term on Assumptions. Interest on opening balances. Bonds are contingent liabilities shown as a memo against the surety facility.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
HIRE PURCHASE: EXISTING AGREEMENTS
Opening balance |  |  |  | 140000 | 136100 | 132200 | 128300 | 124400 | 120500 | 116600 | 112700 | 108800 | 104900 | 101000 | 97100 | 93200 | 89300 | 85400 | 81500 | 77600 | 73700 | 69800 | 65900 | 62000 | 58100 | 54200 | 50300
Principal repaid | fixed monthly principal, capped at the balance | -46800 | -46800 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900 | -3900
Closing balance |  | 93200 | 46400 | 136100 | 132200 | 128300 | 124400 | 120500 | 116600 | 112700 | 108800 | 104900 | 101000 | 97100 | 93200 | 89300 | 85400 | 81500 | 77600 | 73700 | 69800 | 65900 | 62000 | 58100 | 54200 | 50300 | 46400
HIRE PURCHASE: NEW AGREEMENTS
Opening balance |  |  |  | 0 | 0 | 0 | 0 | 34650 | 33928.125 | 33206.25 | 32484.375 | 31762.5 | 31040.625 | 30318.75 | 29596.875 | 28875 | 28153.125 | 27431.25 | 96909.375 | 94725 | 92540.625 | 90356.25 | 88171.875 | 85987.5 | 83803.125 | 81618.75 | 79434.375
Drawn | A: agreements; F: van capex x HP share | 34650 | 70200 | 0 | 0 | 0 | 34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Principal repaid | draws of the prior term months / term | -5775 | -21825 | 0 | 0 | 0 | 0 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -721.875 | -2184.375 | -2184.375 | -2184.375 | -2184.375 | -2184.375 | -2184.375 | -2184.375 | -2184.375 | -2184.375
Closing balance |  | 28875 | 77250 | 0 | 0 | 0 | 34650 | 33928.125 | 33206.25 | 32484.375 | 31762.5 | 31040.625 | 30318.75 | 29596.875 | 28875 | 28153.125 | 27431.25 | 96909.375 | 94725 | 92540.625 | 90356.25 | 88171.875 | 85987.5 | 83803.125 | 81618.75 | 79434.375 | 77250
HIRE PURCHASE: TOTAL
HIRE PURCHASE CREDITOR |  | 122075 | 123650 | 136100 | 132200 | 128300 | 159050 | 154428.125 | 149806.25 | 145184.375 | 140562.5 | 135940.625 | 131318.75 | 126696.875 | 122075 | 117453.125 | 112831.25 | 178409.375 | 172325 | 166240.625 | 160156.25 | 154071.875 | 147987.5 | 141903.125 | 135818.75 | 129734.375 | 123650
Interest | opening balances x rate / 12 | 9657.6281 | 9999.2859 | 805 | 782.575 | 760.15 | 737.725 | 914.5375 | 887.9617 | 861.3859 | 834.8102 | 808.2344 | 781.6586 | 755.0828 | 728.507 | 701.9312 | 675.3555 | 648.7797 | 1025.8539 | 990.8687 | 955.8836 | 920.8984 | 885.9133 | 850.9281 | 815.943 | 780.9578 | 745.9727
Principal repaid |  | -52575 | -68625 | -3900 | -3900 | -3900 | -3900 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -4621.875 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375 | -6084.375
Current portion (next 12 months at the current repayment rate) |  | 55462.5 | 73012.5 | 46800 | 46800 | 46800 | 46800 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 55462.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5 | 73012.5
Non-current portion |  | 66612.5 | 50637.5 | 89300 | 85400 | 81500 | 112250 | 98965.625 | 94343.75 | 89721.875 | 85100 | 80478.125 | 75856.25 | 71234.375 | 66612.5 | 61990.625 | 57368.75 | 122946.875 | 99312.5 | 93228.125 | 87143.75 | 81059.375 | 74975 | 68890.625 | 62806.25 | 56721.875 | 50637.5
FACILITIES AND BONDS (memo)
Overdraft facility, undrawn | Assumptions | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
Performance bonds outstanding | WIP | 544000 | 156000 | 206000 | 324000 | 324000 | 358000 | 344000 | 344000 | 383000 | 623000 | 623000 | 623000 | 662000 | 544000 | 569750 | 569750 | 382750 | 279750 | 297750 | 297750 | 336150 | 368550 | 453750 | 350000 | 332000 | 156000
Bond facility limit | Assumptions | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000
Bond headroom (negative = new bonds cannot be issued) |  | 206000 | 594000 | 544000 | 426000 | 426000 | 392000 | 406000 | 406000 | 367000 | 127000 | 127000 | 127000 | 88000 | 206000 | 180250 | 180250 | 367250 | 470250 | 452250 | 452250 | 413850 | 381450 | 296250 | 400000 | 418000 | 594000
Bond facility utilisation |  | 72.53% | 20.8% | 27.47% | 43.2% | 43.2% | 47.73% | 45.87% | 45.87% | 51.07% | 83.07% | 83.07% | 83.07% | 88.27% | 72.53% | 75.97% | 75.97% | 51.03% | 37.3% | 39.7% | 39.7% | 44.82% | 49.14% | 60.5% | 46.67% | 44.27% | 20.8%

## Project_Register
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
PROJECT REGISTER: COMMERCIAL FIT-OUT AND PUBLIC SECTOR RETROFIT CONTRACTS
One row per contract. Blue = input (contract terms, cost plan, FY2025 closing positions). Black = derived. Pipeline contracts are weighted by the win probability of the selected scenario; delays and overruns come from the scenario drivers.
Code | Project | Client (fictional) | Segment | Status at last actual | Stage | Contract award (month) | Win % Base | Win % Downside | Win % Upside | Win % selected | Planned start (month) | Planned practical completion | Original contract value | Tender budget cost | Tender margin % | Retention % | Share of retention released at PC | Defects period (months) | Client payment days | Subcontractor retention % | Performance bond % | VAT rate on invoices | Labour share | Subcontract share | Materials share | Plant share | Preliminaries share | Opening cost to date | Opening revenue to date | Opening certified to date | Opening receivable incl. VAT | Opening subcontract cost to date | Start delay (months, scenario) | Completion delay (months, scenario) | Start month no. (effective) | Practical completion month no. (effective) | Award month no. (effective) | Final account month no. | Final retention release month no. | Contract value, probability-weighted | Tender budget, probability-weighted | Cost to date at last actual | Cost to complete at last actual | Overrun applied to cost to complete | Forecast cost at completion | Programme position at last actual | S-curve cost share at last actual | Opening retention held | Opening subcontractor retention held | Payment days incl. scenario slip | Forecast final margin % (selected scenario)
CF-2501 | Office fit-out, 1,850 m2, Dublin 2 | Northwall Analytics Ltd | CF | Completed | Contract | 2025-07-31 | 100% | 100% | 100% | 100% | 2025-08-31 | 2026-03-31 | 980000 | 842000 | 14.08% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 568646.02 | 680146.56 | 501973.56 | 220396.74 | 275606.07 | 0 | 0 | -4 | 3 | -5 | 6 | 16 | 980000 | 842000 | 851000 | 0 | 0% | 851000 | 1 | 1 | 25098.678 | 13780.3035 | 30
PS-2502 | Deep retrofit of 24 council homes, Phase 1 | Kildrum County Council | PS | Completed | Contract | 2025-08-31 | 100% | 100% | 100% | 100% | 2025-09-30 | 2026-04-30 | 1080000 | 948000 | 12.22% | 5% | 50% | 12 | 30 | 5% | 10% | 0% | 13% | 56% | 23% | 3% | 5% | 457166.38 | 525307.32 | 331741.87 | 156197.21 | 252740.03 | 0 | 0 | -3 | 4 | -4 | 7 | 17 | 1080000 | 948000 | 941000.01 | 0 | 0% | 941000.01 | 1 | 1 | 16587.0935 | 12637.0015 | 30
CF-2601 | Office fit-out, 2,300 m2, Dublin 4 | Harbourline Insurance DAC | CF | In progress | Contract | 2026-02-28 | 100% | 100% | 100% | 100% | 2026-03-31 | 2026-11-30 | 1180000 | 1018000 | 13.73% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11 | 2 | 14 | 24 | 1180000 | 1018000 | 850470.94 | 339529.06 | 0% | 1190000 | 0.66667 | 0.74074 | 0 | 0 | 30
CF-2602 | Hotel bedroom refurbishment, 64 rooms | Tolka Hospitality Ltd | CF | In progress | Contract | 2026-05-31 | 100% | 100% | 100% | 100% | 2026-06-30 | 2027-02-28 | 940000 | 812000 | 13.62% | 3% | 50% | 12 | 45 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 14 | 5 | 17 | 27 | 940000 | 812000 | 207047.04 | 610952.96 | 0% | 818000 | 0.33333 | 0.25926 | 0 | 0 | 45
CF-2603 | Restaurant fit-out, Dublin 7 | Ember & Oak Restaurants Ltd | CF | In progress | Contract | 2026-07-31 | 100% | 100% | 100% | 100% | 2026-08-31 | 2026-12-31 | 390000 | 329000 | 15.64% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 7 | 15 | 25 | 390000 | 329000 | 32888.13 | 300111.87 | 0% | 333000 | 0.2 | 0.104 | 0 | 0 | 30
PS-2601 | Deep retrofit of 30 council homes, Phase 2 | Kildrum County Council | PS | In progress | Contract | 2026-04-30 | 100% | 100% | 100% | 100% | 2026-05-31 | 2027-02-28 | 1320000 | 1158000 | 12.27% | 5% | 50% | 12 | 30 | 5% | 10% | 0% | 13% | 56% | 23% | 3% | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 14 | 4 | 17 | 27 | 1320000 | 1158000 | 399523.54 | 770476.46 | 0% | 1170000 | 0.4 | 0.352 | 0 | 0 | 30
CF-2604 | Medical clinic fit-out, Dublin 15 | Liffeyside Medical Partners | CF | Contracted | Contract | 2026-08-31 | 100% | 100% | 100% | 100% | 2026-10-31 | 2027-03-31 | 640000 | 549000 | 14.22% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 8 | 18 | 28 | 640000 | 549000 | 0 | 549000 | 0% | 549000 | 0 | 0 | 0 | 0 | 30
PS-2602 | Deep retrofit of 40 council homes, Phase 3 | Kildrum County Council | PS | Contracted | Contract | 2026-08-31 | 100% | 100% | 100% | 100% | 2027-03-31 | 2027-11-30 | 1760000 | 1548000 | 12.05% | 5% | 50% | 12 | 30 | 5% | 10% | 0% | 13% | 56% | 23% | 3% | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 23 | 8 | 26 | 36 | 1760000 | 1548000 | 0 | 1548000 | 0% | 1548000 | 0 | 0 | 0 | 0 | 30
CF-P01 | Office fit-out, 3,100 m2, Dublin 2 | Quayside Capital Partners | CF | Pipeline | Tender submitted | 2027-01-31 | 35% | 20% | 50% | 35% | 2027-02-28 | 2027-09-30 | 1850000 | 1600000 | 13.51% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 21 | 13 | 24 | 34 | 647500 | 560000 | 0 | 560000 | 0% | 560000 | 0 | 0 | 0 | 0 | 30
CF-P02 | Retail flagship fit-out, city centre | Maple & Rowe Retail Ltd | CF | Pipeline | Preferred bidder | 2026-11-30 | 75% | 55% | 85% | 75% | 2026-12-31 | 2027-03-31 | 520000 | 447000 | 14.04% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 11 | 18 | 28 | 390000 | 335250 | 0 | 335250 | 0% | 335250 | 0 | 0 | 0 | 0 | 30
CF-P03 | Hotel public areas refurbishment (phase 2) | Tolka Hospitality Ltd | CF | Pipeline | Shortlisted | 2027-03-31 | 50% | 30% | 65% | 50% | 2027-04-30 | 2027-09-30 | 780000 | 674000 | 13.59% | 3% | 50% | 12 | 45 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 21 | 15 | 24 | 34 | 390000 | 337000 | 0 | 337000 | 0% | 337000 | 0 | 0 | 0 | 0 | 45
PS-P01 | Deep retrofit of 32 council homes, Phase 4 | Kildrum County Council | PS | Pipeline | Framework call-off expected | 2027-09-30 | 60% | 40% | 75% | 60% | 2027-10-31 | 2028-05-31 | 1420000 | 1250000 | 11.97% | 5% | 50% | 12 | 30 | 5% | 10% | 0% | 13% | 56% | 23% | 3% | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 29 | 21 | 32 | 42 | 852000 | 750000 | 0 | 750000 | 0% | 750000 | 0 | 0 | 0 | 0 | 30
CF-P04 | Office fit-out, 1,200 m2, Sandyford | Brightlane Software Ltd | CF | Pipeline | Tender in preparation | 2027-05-31 | 25% | 15% | 35% | 25% | 2027-06-30 | 2027-10-31 | 720000 | 622000 | 13.61% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 22 | 17 | 25 | 35 | 180000 | 155500 | 0 | 155500 | 0% | 155500 | 0 | 0 | 0 | 0 | 30
CF-P05 | Office refurbishment and M&E upgrade, Dublin 2 | Merrion Row Holdings Ltd | CF | Pipeline | Early engagement | 2027-07-31 | 40% | 25% | 55% | 40% | 2027-08-31 | 2028-02-29 | 960000 | 830000 | 13.54% | 5% | 50% | 12 | 30 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26 | 19 | 29 | 39 | 384000 | 332000 | 0 | 332000 | 0% | 332000 | 0 | 0 | 0 | 0 | 30
CF-P06 | Hotel refurbishment, 48 rooms, Galway | Corrib Bay Hotels Ltd | CF | Pipeline | Early engagement | 2027-08-31 | 30% | 20% | 40% | 30% | 2027-09-30 | 2028-04-30 | 1080000 | 935000 | 13.43% | 3% | 50% | 12 | 45 | 5% | 10% | 13.5% | 16% | 50% | 24% | 3% | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 28 | 20 | 31 | 41 | 324000 | 280500 | 0 | 280500 | 0% | 280500 | 0 | 0 | 0 | 0 | 45
TOTAL | [12 empty] | 15620000 | 13562000 | [13 empty] | 1025812.4 | 1205453.88 | 833715.43 | 376593.95 | 528346.1 | [7 empty] | 11457500 | 9954250 | 3281929.66 | 6868320.35 |  | 10150250.01 |  |  | 41685.7715 | 26417.305
Month numbers count from the model start (Jan-26 = 1); negative numbers are months before the model starts. Retention: first share released the month after practical completion, the balance the month after the defects period ends. Final account agreed the months after completion set on Assumptions.

## Assumptions
TARNLEA BUILD & RETROFIT LTD (FICTIONAL DEMONSTRATION COMPANY)
ASSUMPTIONS, TIMELINE AND SCENARIO DRIVERS
Every input lives here, on Inputs_Actuals, Project_Register, Variations, Commitments, Budget_FY26 or the headcount tables. Blue on yellow = input. Black = formula. Green = link to another sheet.
GENERAL
Company name |  | Tarnlea Build & Retrofit Ltd (fictional demonstration company) | All figures fictional. Irish private company limited by shares, financial year = calendar year, reporting currency EUR.
Reporting currency |  | EUR
Model start month (month end) | date | 2026-01-31 | 24 monthly columns from this month
Last actual month (month end) | date | 2026-08-31 | Months up to and including this date are actual (fictional ledger); later months are forecast
Last actual month number | calc | 8
Scenario selector (1 = Base, 2 = Downside, 3 = Upside) | input | 1 | Change this cell and every forecast month moves. Base = management case; Downside = worst case; Upside = best case.
Scenario name | calc | Base
Minimum cash buffer (board policy) | EUR | 200000 | Used by the 13-week cash forecast and the CFO report
Undrawn overdraft facility available | EUR | 250000 | Committed, undrawn; first lever if the buffer is breached
Performance bond facility limit (surety) | EUR | 750000 | Bonds outstanding are a contingent liability; the limit caps how much commercial and public work can be taken on
Bond commission, annual rate on bonds outstanding | rate | 1.6% | VAT exempt; charged monthly to overheads
Aged receivables and payables: as-at date | calc | 2026-08-31
TAX (IRELAND)
Corporation tax rate on trading income | rate | 12.5% | Assumes capital allowances equal depreciation and no disallowable items (information needed: FY2026 tax computation)
FY2025 corporation tax liability (per the FY2025 return) | EUR | 32000 | Basis for FY2026 preliminary tax at 100% of the prior year
Small company threshold for preliminary tax (prior-year liability) | EUR | 200000 | One payment by the 23rd of month 11 (100% prior year or 90% current); balance by the 23rd of month 9 after year end (Revenue TDM 41A-07-02)
VAT: reduced rate on construction services | rate | 13.5% | Renovation, retrofit and fit-out services (Revenue). Reverse charge applies where the customer is a principal contractor, e.g. a county council
VAT: standard rate | rate | 23% | Materials, plant hire, agency labour and most overheads
Share of overheads bearing recoverable VAT | share | 62% | Insurance, bond commission and some rent are exempt
Share of fleet running costs bearing recoverable VAT | share | 60% | Diesel and maintenance recoverable; vehicle insurance exempt
Share of capex bearing recoverable VAT | share | 100% | Commercial vans, tools and IT
RCT: blended deduction rate on subcontractor payments | rate | 3.7% | Revenue determines each subcontractor rate (0%, 20% or 35%); blend reflects the current mix. Remitted by the 23rd of the following month
Employer PRSI, Class A (weekly pay above EUR 552), to 30-Sep-26 | rate | 11.25% | gov.ie PRSI Class A rates
Employer PRSI, Class A, from 1-Oct-26 | rate | 11.4% | gov.ie; later increases not modelled until confirmed
Employer pension and other employment costs, share of gross pay | share | 5% | Company assumption
Employee deductions (PAYE, USC, PRSI, pension), share of gross pay | share | 24% | Company average; remitted with employer PRSI by the 23rd of the following month
SITE LABOUR, FLEET AND OVERHEAD RATES
Productive hours per site FTE per month | hours | 140 | After annual leave, public holidays, sick leave and training (company assumption)
Standard labour cost rate charged to projects, FY2026 | EUR/hour | 39.5 | Set so that 85% utilisation recovers the site payroll
Target utilisation of productive hours | share | 85%
Agency operatives, cost per hour ex VAT | EUR/hour | 47
Fleet running cost per van per month (fuel, maintenance, insurance, tracking) | EUR | 960
Small tools and consumables per month | EUR | 2100
Pay and overhead inflation applied from FY2027 | rate | 3.5%
RESIDENTIAL PROGRAMMES
Retrofit run-rate basis: latest actual months averaged | months | 3 | Latest quarter only: starts were depressed Mar to May by the coordinator vacancy
Renovation run-rate basis: latest actual months averaged | months | 6
Retrofit revenue earned in month 1 of the job (share of contract value) | share | 30% | Three-month job; shares must sum to 100%
Retrofit revenue earned in month 2 of the job (share of contract value) | share | 45%
Retrofit revenue earned in month 3 of the job (share of contract value) | share | 25%
Renovation revenue earned in month 1 of the job (share of contract value) | share | 10% | Five-month job; shares must sum to 100%
Renovation revenue earned in month 2 of the job (share of contract value) | share | 22%
Renovation revenue earned in month 3 of the job (share of contract value) | share | 28%
Renovation revenue earned in month 4 of the job (share of contract value) | share | 25%
Renovation revenue earned in month 5 of the job (share of contract value) | share | 15%
Retrofit homeowner stage invoice 1 (share of homeowner portion) | share | 20% | Deposit at start
Retrofit homeowner stage invoice 2 (share of homeowner portion) | share | 50% | Month 2 stage
Retrofit homeowner stage invoice 3 (share of homeowner portion) | share | 30% | Completion
SEAI grant claim: months after completion (post-works BER) | months | 1 | Grant is deducted from the homeowner price and paid to the One Stop Shop (SEAI homeowner guide)
Renovation deposit at contract start | share | 15%
Renovation progress billing as share of revenue earned | share | 80%
Renovation snag retention held by the homeowner | share | 5%
Snag retention released: months after completion | months | 2
Retrofit forecast cost mix: own labour (allocated at standard rate) | share | 32%
Retrofit forecast cost mix: subcontractors | share | 30%
Retrofit forecast cost mix: materials | share | 28%
Retrofit forecast cost mix: plant hire | share | 3%
Retrofit forecast cost mix: preliminaries and site services | share | 7%
Renovation forecast cost mix: own labour (allocated at standard rate) | share | 27%
Renovation forecast cost mix: subcontractors | share | 33%
Renovation forecast cost mix: materials | share | 30%
Renovation forecast cost mix: plant hire | share | 3%
Renovation forecast cost mix: preliminaries and site services | share | 7%
NAMED PROJECTS, PAYABLES, DEBT AND CAPEX
Pending variations recognised in contract value while undecided | share | 50% | Revenue constraint (IFRS 15.56): only the amount highly probable not to reverse
Final account agreed: months after practical completion | months | 3
Subcontractors: days payable | days | 34 | Monthly payment run on the 25th after the payment notice
Materials suppliers: days payable | days | 46
Plant hire and site services: days payable | days | 30
Overhead, fleet and agency suppliers: days payable | days | 24
Hire purchase: annual interest rate | rate | 6.9%
Hire purchase: term of new agreements | months | 48
Hire purchase: existing agreements, monthly principal | EUR | 3900
Share of van purchases financed by hire purchase | share | 90%
Van replacements (two vans) | EUR | 78000
Van replacements: month | month | 2027-03-31
Plant and tools capex per month | EUR | 1200
IT and estimating software refresh | EUR | 12000
IT refresh: month | month | 2027-01-31
Depreciation: vans, useful life | years | 5
Depreciation: plant and tools, useful life | years | 4
Depreciation: IT and office, useful life | years | 3
Legacy retention CF-2405: final release received | month | 2026-12-31 | Defects period ends Oct-26; release certified Nov-26, paid Dec-26
TIMELINE (24 months)
Month end date |  |  |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Actual (A) or Forecast (F) | bar: 2026-01-31 to 2027-12-31
Financial year |  |  |  | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027
Calendar month |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Days in month |  |  |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
Months after the last actual month (growth compounding base) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Residential starts seasonality (12-month profile, FY27 repeats FY26) |  |  |  | 0.7 | 0.85 | 1 | 1.1 | 1.15 | 1.15 | 1.1 | 1.05 | 1.1 | 1.05 | 0.95 | 0.8 | 0.7 | 0.85 | 1 | 1.1 | 1.15 | 1.15 | 1.1 | 1.05 | 1.1 | 1.05 | 0.95 | 0.8
Employer PRSI rate in force |  |  |  | 11.25% | 11.25% | 11.25% | 11.25% | 11.25% | 11.25% | 11.25% | 11.25% | 11.25% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4% | 11.4%
Pay and overhead inflation factor |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035 | 1.035
VAT payment month (bi-monthly return for the prior two months, 23rd) |  |  |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
Corporation tax balance of the prior year paid (23 September) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Corporation tax preliminary payment (23 November) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
SCENARIO DRIVERS (C = Base, D = Downside, E = Upside, F = selected, G = YTD actual reference) | bar: 1 to 4
Driver | Unit | Base | Downside | 1: Upside; 2: Selected; 3: YTD actual; 4: Note
Retrofit homes started: growth vs deseasonalised run-rate (annualised) |  | 20% | -10% | 1: 35%; 2: 20%; 4: Base assumes the second retrofit coordinator (Nov-26) clears the survey backlog
Renovation jobs started: growth vs run-rate (annualised) |  | 5% | -15% | 1: 12%; 2: 5%
Retrofit average contract value change (annualised) |  | 3% | 0% | bar: 1 to 2
Renovation average contract value change (annualised) |  | 3% | 0% | bar: 1 to 2
Retrofit gross margin on new and in-flight work |  | 23.5% | 20.5% | 1: 24.5%; 2: 23.5%; 3: 21.91%
Renovation gross margin on new and in-flight work |  | 24% | 21% | 1: 25.5%; 2: 24%; 3: 25.35%
Start delay: contracted and pipeline projects | months | 0 | 2 | 1: 0; 2: 0
Completion delay: projects in progress | months | 0 | 1 | 1: 0; 2: 0
Cost overrun on cost to complete, projects in progress |  | 0% | 5% | 1: -1%; 2: 0%; 4: Applied to the project managers cost to complete at the last actual month
Cost overrun on tender budgets, projects not yet started |  | 0% | 4% | 1: -1%; 2: 0%
Pending variations: final agreed value as share of claimed |  | 65% | 35% | 1: 85%; 2: 65%; 4: Applied on the expected decision date; the policy constraint applies until then
Commercial and council clients: extra payment days | days | 0 | 15 | 1: 0; 2: 0
SEAI grant claims: days to payment | days | 60 | 90 | 1: 45; 2: 60; 3: 60.4426
Homeowners: days to payment | days | 10 | 20 | 1: 7; 2: 10; 3: 11.5399
Site hiring plan (1 = as planned, 0 = freeze) | flag | 1 | 0 | bar: 1 to 2
Office hiring plan (1 = as planned, 0 = freeze) | flag | 1 | 0 | bar: 1 to 2
Discretionary overheads factor (marketing, training, motor) | x | 1 | 0.9 | bar: 1 to 2
Disputed retention CF-2311: share recovered |  | 75% | 50% | 1: 90%; 2: 75%
Disputed retention CF-2311: month of settlement | month | 2026-11-30 | 2027-02-28 | 1: 2026-10-31; 2: 2026-11-30

## Inputs_Actuals
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
INPUTS: ACTUAL MONTHS (FICTIONAL LEDGER, VALUATIONS, JOB SYSTEM AND BANK)
Jan-26 to Aug-26 are fictional actuals entered as inputs. Forecast months are blank by design and are driven from Assumptions and the registers.
Line | Basis | FY2026 | FY2027 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
Actual (A) or Forecast (F) |  | A + F | F | A | A | A | A | A | A | A | A | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Month number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
NAMED PROJECTS: COST BY TYPE, COST TO COMPLETE, REVENUE, VALUATIONS AND CASH
CF-2501: own labour (allocated at standard rate) | cost ledger | 46241.49 |  | 1: 20871.48; 2: 17684.27; 3: 7685.74; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2501: subcontractors | cost ledger | 139442.55 |  | 1: 61951.26; 2: 52022.57; 3: 25468.72; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2501: materials | cost ledger | 68644.3 |  | 1: 31369.52; 2: 25055.71; 3: 12219.07; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2501: plant hire | cost ledger | 8504.12 |  | 1: 3705.32; 2: 3404.59; 3: 1394.21; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2501: preliminaries and site services | cost ledger | 19521.52 |  | 1: 8828.56; 2: 7071.15; 3: 3621.81; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2501: cost to complete at month end (project cost report) | cost report |  |  | 1: 155627.84; 2: 50389.55; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2501: revenue recognised in the month | ledger (percentage of completion) | 363553.44 |  | 1: 158017.94; 2: 139314.06; 3: 74221.44; 4: 0; 5: -8000; 6: 0; 7: 0; 8: 0
CF-2501: gross value certified in the month (before retention) | payment certificates | 541726.44 |  | 1: 174998.85; 2: 142112.26; 3: 150867.59; 4: 61047.74; 5: 12700; 6: 0; 7: 0; 8: 0
CF-2501: cash received incl. VAT | bank | 834128.26 |  | 1: 217597.9; 2: 205867.58; 3: 125893.45; 4: 155017.36; 5: 115232.36; 6: 14519.61; 7: 0; 8: 0
PS-2502: own labour (allocated at standard rate) | cost ledger | 62064.74 |  | 1: 25139.45; 2: 19305.56; 3: 11616.66; 4: 6003.07; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: subcontractors | cost ledger | 271319.35 |  | 1: 115846.57; 2: 86983.55; 3: 45995.01; 4: 22494.22; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: materials | cost ledger | 111445.86 |  | 1: 47365.64; 2: 34162.6; 3: 19879.12; 4: 10038.5; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: plant hire | cost ledger | 14462.99 |  | 1: 5935.65; 2: 4596.24; 3: 2738.29; 4: 1192.81; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: preliminaries and site services | cost ledger | 24540.69 |  | 1: 11112.56; 2: 7506.6; 3: 3978.11; 4: 1943.42; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: cost to complete at month end (project cost report) | cost report |  |  | 1: 285433.75; 2: 132879.2; 3: 41672.01; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: revenue recognised in the month | ledger (percentage of completion) | 583692.68 |  | 1: 236014.85; 2: 188104.4; 3: 105874.14; 4: 53699.29; 5: 0; 6: 0; 7: 0; 8: 0
PS-2502: gross value certified in the month (before retention) | payment certificates | 777258.13 |  | 1: 189080.59; 2: 246999.57; 3: 176789.48; 4: 115276.63; 5: 49111.86; 6: 0; 7: 0; 8: 0
PS-2502: cash received incl. VAT | bank | 922317.43 |  | 1: 144766.1; 2: 163070.87; 3: 253854.78; 4: 178666.93; 5: 112812.06; 6: 69146.69; 7: 0; 8: 0
CF-2601: own labour (allocated at standard rate) | cost ledger | 136231.64 |  | 1: 0; 2: 0; 3: 4847.06; 4: 13397.14; 5: 23717.38; 6: 29166.41; 7: 35066.67; 8: 30036.98
CF-2601: subcontractors | cost ledger | 423132.33 |  | 1: 0; 2: 0; 3: 18113.03; 4: 44923.87; 5: 70640.96; 6: 89625.98; 7: 109569.75; 8: 90258.74
CF-2601: materials | cost ledger | 204717.81 |  | 1: 0; 2: 0; 3: 7969.6; 4: 21409.7; 5: 34121.09; 6: 47617.47; 7: 55295.75; 8: 38304.2
CF-2601: plant hire | cost ledger | 25174.65 |  | 1: 0; 2: 0; 3: 989.86; 4: 2574.07; 5: 4285.88; 6: 5906.54; 7: 6585.68; 8: 4832.62
CF-2601: preliminaries and site services | cost ledger | 61214.51 |  | 1: 0; 2: 0; 3: 2446.98; 4: 6577.39; 5: 10558.36; 6: 13057.1; 7: 16107.85; 8: 12466.83
CF-2601: cost to complete at month end (project cost report) | cost report |  |  | 3: 983633.47; 4: 894751.3; 5: 847427.63; 6: 706054.13; 7: 483428.43; 8: 339529.06
CF-2601: revenue recognised in the month | ledger (percentage of completion) | 909074.82 |  | 1: 0; 2: 0; 3: 39835.47; 4: 103444.17; 5: 144039.43; 6: 188102.23; 7: 254607.28; 8: 179046.24
CF-2601: gross value certified in the month (before retention) | payment certificates | 706610.81 |  | 1: 0; 2: 0; 3: 0; 4: 39835.47; 5: 103026.48; 6: 139503.76; 7: 191045.64; 8: 233199.46
CF-2601: cash received incl. VAT | bank | 527747 |  | 1: 0; 2: 0; 3: 0; 4: 4497.27; 5: 40564.92; 6: 122518.96; 7: 136091.39; 8: 224074.46
CF-2602: own labour (allocated at standard rate) | cost ledger | 34526.9 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 3938.24; 7: 12971.66; 8: 17617
CF-2602: subcontractors | cost ledger | 100244.68 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 13677.06; 7: 35197.37; 8: 51370.25
CF-2602: materials | cost ledger | 51347.16 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 5956.3; 7: 20397.19; 8: 24993.67
CF-2602: plant hire | cost ledger | 6364.38 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 766.17; 7: 2359.28; 8: 3238.93
CF-2602: preliminaries and site services | cost ledger | 14563.92 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 1720.39; 7: 5192.47; 8: 7651.06
CF-2602: cost to complete at month end (project cost report) | cost report |  |  | 6: 785941.84; 7: 715823.87; 8: 610952.96
CF-2602: revenue recognised in the month | ledger (percentage of completion) | 247330.09 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 30627.97; 7: 88585.84; 8: 128116.28
CF-2602: gross value certified in the month (before retention) | payment certificates | 120837.64 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 30165.85; 8: 90671.79
CF-2602: cash received incl. VAT | bank | 17589.69 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: -6040.66; 8: 23630.35
CF-2603: own labour (allocated at standard rate) | cost ledger | 5535.27 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 5535.27
CF-2603: subcontractors | cost ledger | 16135.07 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 16135.07
CF-2603: materials | cost ledger | 7763.05 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 7763.05
CF-2603: plant hire | cost ledger | 1058.88 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 1058.88
CF-2603: preliminaries and site services | cost ledger | 2395.86 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 2395.86
CF-2603: cost to complete at month end (project cost report) | cost report |  |  | 8: 300111.87
CF-2603: revenue recognised in the month | ledger (percentage of completion) | 39317.61 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 39317.61
CF-2603: gross value certified in the month (before retention) | payment certificates | 0 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
CF-2603: cash received incl. VAT | bank | 0 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0
PS-2601: own labour (allocated at standard rate) | cost ledger | 51779.48 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 3765.57; 6: 10550.21; 7: 15618.82; 8: 21844.88
PS-2601: subcontractors | cost ledger | 220616.95 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 16519.7; 6: 46285.24; 7: 75715.48; 8: 82096.53
PS-2601: materials | cost ledger | 94650.95 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 6470.19; 6: 22278.85; 7: 29929.2; 8: 35972.71
PS-2601: plant hire | cost ledger | 12152.23 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 914.62; 6: 2460.24; 7: 4183.21; 8: 4594.16
PS-2601: preliminaries and site services | cost ledger | 20323.93 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 1585.13; 6: 4316.22; 7: 6663.73; 8: 7758.85
PS-2601: cost to complete at month end (project cost report) | cost report |  |  | 5: 1128744.79; 6: 1042854.03; 7: 922743.59; 8: 770476.46
PS-2601: revenue recognised in the month | ledger (percentage of completion) | 460800.89 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 33347.91; 6: 99114.7; 7: 149061; 8: 179277.28
PS-2601: gross value certified in the month (before retention) | payment certificates | 283626.35 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 33347.91; 7: 97906.56; 8: 152371.88
PS-2601: cash received incl. VAT | bank | 121982.95 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: -1130.93; 7: 33354.11; 8: 89759.77
RESIDENTIAL RETROFIT PROGRAMME (SEAI ONE STOP SHOP)
Retrofit: homes started | job system | 22 |  | 1: 2; 2: 2; 3: 3; 4: 2; 5: 2; 6: 3; 7: 4; 8: 4
Retrofit: average contract value ex VAT (EUR per home) | job system | 61247.875 |  | 1: 60550; 2: 64205; 3: 60211; 4: 62861; 5: 59224; 6: 60796; 7: 61317; 8: 60819
Retrofit: average SEAI grant per home (EUR) | grant applications | 23882.25 |  | 1: 24548; 2: 26586; 3: 24288; 4: 22206; 5: 22057; 6: 24086; 7: 24171; 8: 23116
Retrofit: revenue earned | ledger | 1247322.85 |  | 1: 138592.05; 2: 124444; 3: 142249.4; 4: 151103.95; 5: 137267.55; 6: 139448.5; 7: 185267; 8: 228950.4
Retrofit: own labour (allocated at standard rate) | cost ledger | 305469.64 |  | 1: 34952.94; 2: 30901.58; 3: 35804.15; 4: 34793.39; 5: 34189.05; 6: 34966.75; 7: 46331.62; 8: 53530.16
Retrofit: subcontractors | cost ledger | 293166.91 |  | 1: 32660.2; 2: 30636.92; 3: 34877.7; 4: 33248.27; 5: 32405.16; 6: 32644.04; 7: 42365.01; 8: 54329.61
Retrofit: materials | cost ledger | 279058.94 |  | 1: 28661.76; 2: 26982.53; 3: 34747.57; 4: 33567.44; 5: 30802.91; 6: 31261.92; 7: 42076.48; 8: 50958.33
Retrofit: plant hire | cost ledger | 30098.25 |  | 1: 3395.59; 2: 3166.79; 3: 3644.12; 4: 3381.04; 5: 3303.38; 6: 3487.62; 7: 4738.4; 8: 4981.31
Retrofit: preliminaries and site services | cost ledger | 66209.98 |  | 1: 6964.13; 2: 6211.26; 3: 7058.15; 4: 7983.9; 5: 7280.98; 6: 7882.66; 7: 10204.82; 8: 12624.08
Retrofit: homeowner invoices incl. VAT | sales ledger | 916724.99 |  | 1: 105489.75; 2: 91239.53; 3: 99223.32; 4: 113505.73; 5: 106852.47; 6: 101597.46; 7: 130812.57; 8: 168004.16
Retrofit: SEAI grant claims lodged incl. VAT | SEAI claims | 460186 |  | 1: 75687; 2: 73329; 3: 47512; 4: 49096; 5: 53172; 6: 72864; 7: 44412; 8: 44114
Retrofit: cash received from homeowners | bank | 883429.41 |  | 1: 106268.01; 2: 93670.97; 3: 96455.66; 4: 108853.19; 5: 102307.45; 6: 105686.06; 7: 125565.63; 8: 144622.44
Retrofit: SEAI grant cash received | bank | 530530.62 |  | 1: 14200.01; 2: 135355.36; 3: 72516.9; 4: 75030.21; 5: 58661.54; 6: 42614.36; 7: 41057.29; 8: 91094.95
RESIDENTIAL RENOVATION AND EXTENSIONS PROGRAMME
Renovation: jobs started | job system | 11 |  | 1: 1; 2: 1; 3: 2; 4: 1; 5: 2; 6: 1; 7: 2; 8: 1
Renovation: average contract value ex VAT (EUR per job) | job system | 124144 |  | 1: 124683; 2: 102963; 3: 123589; 4: 124491; 5: 145078; 6: 131987; 7: 123908; 8: 116453
Renovation: revenue earned | ledger | 1276311.62 |  | 1: 131409.36; 2: 114236.45; 3: 128758.65; 4: 145125.35; 5: 170056.66; 6: 189129.45; 7: 203261.87; 8: 194333.83
Renovation: own labour (allocated at standard rate) | cost ledger | 256098.77 |  | 1: 26744.36; 2: 21752.02; 3: 24812.91; 4: 28373.8; 5: 37155.85; 6: 39028.56; 7: 41499.95; 8: 36731.32
Renovation: subcontractors | cost ledger | 311708.71 |  | 1: 31778.28; 2: 27300.04; 3: 31904.92; 4: 33620.03; 5: 41998.66; 6: 48157.15; 7: 49659.38; 8: 47290.25
Renovation: materials | cost ledger | 290380.31 |  | 1: 30318.11; 2: 24286.8; 3: 28132.24; 4: 30763.67; 5: 40621.43; 6: 45450.05; 7: 45522.69; 8: 45285.32
Renovation: plant hire | cost ledger | 28643.5 |  | 1: 2967.98; 2: 2424.27; 3: 2823.49; 4: 3026.14; 5: 3919.63; 6: 4726.77; 7: 4464.55; 8: 4290.67
Renovation: preliminaries and site services | cost ledger | 65873.1 |  | 1: 6265.74; 2: 5990.96; 3: 5981.64; 4: 7015.19; 5: 9279.62; 6: 10538.71; 7: 10927.25; 8: 9873.99
Renovation: invoices incl. VAT | sales ledger | 1460418.51 |  | 1: 154404.31; 2: 127523.45; 3: 172643.28; 4: 158914.79; 5: 209857.5; 6: 201122.58; 7: 233828.21; 8: 202124.39
Renovation: cash received | bank | 1451625.29 |  | 1: 166567.19; 2: 124038.46; 3: 159820.04; 4: 151894.2; 5: 204243.51; 6: 214564.27; 7: 194818.62; 8: 235679
SITE WORKFORCE, AGENCY AND FLEET
Headcount: site supervisors and foremen | payroll | 4 |  | 1: 4; 2: 4; 3: 4; 4: 4; 5: 4; 6: 4; 7: 4; 8: 4
Headcount: craft operatives (carpentry, drylining, finishing) | payroll | 10.375 |  | 1: 10; 2: 10; 3: 10; 4: 10; 5: 10; 6: 11; 7: 11; 8: 11
Headcount: retrofit installers (insulation, airtightness) | payroll | 7.75 |  | 1: 8; 2: 8; 3: 8; 4: 7; 5: 7; 6: 8; 7: 8; 8: 8
Headcount: general operatives | payroll | 3.25 |  | 1: 3; 2: 3; 3: 3; 4: 3; 5: 3; 6: 3; 7: 4; 8: 4
Site workforce gross pay | payroll | 825771 |  | 1: 100577; 2: 100073; 3: 103197; 4: 98593; 5: 98614; 6: 103650; 7: 112754; 8: 108313
Agency operatives (ex VAT) | supplier invoices | 14900 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 2600; 7: 5400; 8: 6900
Vans in the fleet | fleet register | 12.625 |  | 1: 12; 2: 12; 3: 12; 4: 13; 5: 13; 6: 13; 7: 13; 8: 13
Fleet running costs and small tools (ex VAT) | ledger | 111934 |  | 1: 13626; 2: 13713; 3: 13725; 4: 14065; 5: 13284; 6: 14685; 7: 15315; 8: 13521
OFFICE PAYROLL AND OVERHEADS (ex VAT)
Office staff gross pay | payroll | 335448 |  | 1: 43634; 2: 43301; 3: 39568; 4: 39249; 5: 39045; 6: 43840; 7: 43272; 8: 43539
Rent: office and yard | ledger | 57312 |  | 1: 6023; 2: 5858; 3: 8709; 4: 7347; 5: 7358; 6: 7044; 7: 8501; 8: 6472
Insurance (public, employer and contractors all risks) | ledger | 75131 |  | 1: 10070; 2: 8856; 3: 8959; 4: 9674; 5: 9909; 6: 9772; 7: 9369; 8: 8522
IT, software and estimating tools | ledger | 31234 |  | 1: 3706; 2: 4237; 3: 4035; 4: 4028; 5: 3676; 6: 4033; 7: 3989; 8: 3530
Marketing and lead generation (residential) | ledger | 52476 |  | 1: 3684; 2: 5487; 3: 7730; 4: 8125; 5: 8707; 6: 6050; 7: 6484; 8: 6209
Professional fees (audit, legal, tax) | ledger | 32840 |  | 1: 5000; 2: 4331; 3: 3264; 4: 4655; 5: 4063; 6: 3755; 7: 3675; 8: 4097
Training, health and safety, PPE | ledger | 20728 |  | 1: 3015; 2: 2508; 3: 2777; 4: 2372; 5: 3007; 6: 2630; 7: 1867; 8: 2552
Office and administration | ledger | 17868 |  | 1: 2372; 2: 2245; 3: 1938; 4: 2556; 5: 2479; 6: 2112; 7: 2318; 8: 1848
Motor (non-site vehicles) | ledger | 13345 |  | 1: 1687; 2: 1848; 3: 1800; 4: 1716; 5: 1422; 6: 1619; 7: 1791; 8: 1462
Subscriptions and memberships | ledger | 6843 |  | 1: 834; 2: 647; 3: 726; 4: 977; 5: 860; 6: 897; 7: 1040; 8: 862
Bad debt charge (specific provisions) | ledger | 9500 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 9500; 7: 0; 8: 0
CAPEX AND FINANCING
Capex: vans | asset register | 38500 |  | 1: 0; 2: 0; 3: 0; 4: 38500; 5: 0; 6: 0; 7: 0; 8: 0
Capex: plant and tools | asset register | 9400 |  | 1: 1800; 2: 0; 3: 2400; 4: 900; 5: 0; 6: 3100; 7: 1200; 8: 0
Capex: IT and office | asset register | 6100 |  | 1: 0; 2: 0; 3: 4200; 4: 0; 5: 0; 6: 0; 7: 0; 8: 1900
Hire purchase drawn | HP agreements | 34650 |  | 1: 0; 2: 0; 3: 0; 4: 34650; 5: 0; 6: 0; 7: 0; 8: 0
SUPPLIER PAYMENTS (per bank)
Subcontractors: gross payments before RCT deducted | bank + RCT deduction summaries | 1517147.86 |  | 1: 162950.96; 2: 223839.61; 3: 190110.94; 4: 162867.85; 5: 154598.45; 6: 168157.04; 7: 193744.57; 8: 260878.44
Materials suppliers: payments | bank | 1110844.47 |  | 1: 98833.65; 2: 140309.29; 3: 130537.09; 4: 148213.23; 5: 128489.84; 6: 114926.95; 7: 137044.46; 8: 212489.96
Plant hire and site services: payments | bank | 429457.45 |  | 1: 39871.42; 2: 62356.57; 3: 48705.77; 4: 45209.91; 5: 38113.25; 6: 45633.35; 7: 84378.75; 8: 65188.43
Overhead, fleet and agency suppliers: payments | bank | 482815.04 |  | 1: 44200.79; 2: 64704.8; 3: 53584.95; 4: 63082.86; 5: 62637.05; 6: 69961.65; 7: 58478.97; 8: 66163.97
OPENING BALANCE SHEET AT 31-DEC-25 (FY2025 accounts, fictional) - values in column C; named project openings are on Project_Register
Cash at bank | FY25 accounts | 420000
Retrofit homeowner receivables | FY25 accounts | 31988.97
SEAI grant claims receivable | FY25 accounts | 178731.67
Renovation homeowner receivables | FY25 accounts | 68296.64
Retrofit programme: revenue earned less billed (ex VAT; + asset, - liability) | FY25 accounts | 141991.13
Renovation programme: revenue earned less billed (ex VAT) | FY25 accounts | -5623.37
Legacy retention CF-2405 (final half, ex VAT) | FY25 accounts | 19000
Legacy retention CF-2311 (overdue, ex VAT) | FY25 accounts | 38000
Prepayments and other receivables | FY25 accounts | 46000
Vans: cost | FY25 accounts | 395000
Vans: accumulated depreciation | FY25 accounts | 178000
Plant and tools: cost | FY25 accounts | 118000
Plant and tools: accumulated depreciation | FY25 accounts | 61000
IT and office: cost | FY25 accounts | 64000
IT and office: accumulated depreciation | FY25 accounts | 41000
Trade payables: subcontractors | FY25 accounts | 182000
Trade payables: materials suppliers | FY25 accounts | 148000
Trade payables: plant hire and site services | FY25 accounts | 41000
Trade payables: overhead suppliers | FY25 accounts | 38000
RCT deducted, payable to Revenue | FY25 accounts | 5200
PAYE, USC, PRSI and pension payable | FY25 accounts | 61800
VAT payable (Nov-Dec 25 return) | FY25 accounts | 46300
Corporation tax payable (FY2025 balance) | FY25 accounts | 6000
Hire purchase creditor | FY25 accounts | 140000
Share capital | FY25 accounts | 100000
Retained earnings | FY25 accounts | 1230685.9

## Budget_FY26
Tarnlea Build & Retrofit Ltd (fictional demonstration company)
ORIGINAL FY2026 BUDGET (APPROVED DEC-25, FICTIONAL)
Twelve budget months. Volumes, revenue by segment, gross margin rates, site costs and overhead lines are inputs as approved; everything else is calculated. Never overwritten.
Line | Basis | FY2026 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31
Actual (A) or Forecast (F) |  | A + F | bar: 2026-01-31 to 2026-12-31
Month number |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
VOLUMES
Retrofit homes started | budget input | 42 | 2.45 | 2.98 | 3.5 | 3.85 | 4.02 | 4.02 | 3.85 | 3.68 | 3.85 | 3.68 | 3.32 | 2.8
Renovation jobs started | budget input | 17.99 | 1.05 | 1.27 | 1.5 | 1.65 | 1.72 | 1.72 | 1.65 | 1.58 | 1.65 | 1.58 | 1.42 | 1.2
REVENUE
Residential deep retrofit (SEAI One Stop Shop) | budget input | 2525498 | 147097 | 153212 | 183214 | 211975 | 232624 | 242627 | 242109 | 234332 | 230184 | 229146 | 220484 | 198494
Residential renovation and extensions | budget input | 2007754 | 131121 | 118038 | 130392 | 147416 | 165880 | 183036 | 192850 | 194892 | 192862 | 189532 | 184916 | 176819
Commercial fit-out | budget input | 3649153 | 156953 | 111016 | 82576 | 140686 | 243402 | 351781 | 470863 | 502607 | 509422 | 462604 | 360933 | 256310
Public sector retrofit (council) | budget input | 1860000 | 198281 | 172969 | 159304 | 146726 | 147840 | 179520 | 195360 | 195360 | 179520 | 147840 | 100320 | 36960
NET REVENUE |  | 10042405 | 633452 | 555235 | 555486 | 646803 | 789746 | 956964 | 1101182 | 1127191 | 1111988 | 1029122 | 866653 | 668583
GROSS PROFIT
Gross margin rate: residential deep retrofit (seai one stop shop) | budget input | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5% | 24.5%
Gross margin rate: residential renovation and extensions | budget input | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5% | 25.5%
Gross margin rate: commercial fit-out | budget input | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8% | 14.8%
Gross margin rate: public sector retrofit (council) | budget input | 13% | 13% | 13% | 13% | 13% | 13% | 13% | 13% | 13% | 13% | 13% | 13% | 13%
Residential deep retrofit (SEAI One Stop Shop) | revenue x margin rate | 618747.01 | 36038.765 | 37536.94 | 44887.43 | 51933.875 | 56992.88 | 59443.615 | 59316.705 | 57411.34 | 56395.08 | 56140.77 | 54018.58 | 48631.03
Residential renovation and extensions | revenue x margin rate | 511977.27 | 33435.855 | 30099.69 | 33249.96 | 37591.08 | 42299.4 | 46674.18 | 49176.75 | 49697.46 | 49179.81 | 48330.66 | 47153.58 | 45088.845
Commercial fit-out | revenue x margin rate | 540074.644 | 23229.044 | 16430.368 | 12221.248 | 20821.528 | 36023.496 | 52063.588 | 69687.724 | 74385.836 | 75394.456 | 68465.392 | 53418.084 | 37933.88
Public sector retrofit (council) | revenue x margin rate | 241800 | 25776.53 | 22485.97 | 20709.52 | 19074.38 | 19219.2 | 23337.6 | 25396.8 | 25396.8 | 23337.6 | 19219.2 | 13041.6 | 4804.8
GROSS PROFIT |  | 1912598.924 | 118480.194 | 106552.968 | 111068.158 | 129420.863 | 154534.976 | 181518.983 | 203577.979 | 206891.436 | 204306.946 | 192156.022 | 167631.844 | 136458.555
SITE RESOURCES AND OVERHEADS
Labour recovery variance | budget input | -36000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000 | -3000
Fleet running costs and small tools | budget input | -156000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000 | -13000
CONTRIBUTION AFTER SITE RESOURCES |  | 1720598.924 | 102480.194 | 90552.968 | 95068.158 | 113420.863 | 138534.976 | 165518.983 | 187577.979 | 190891.436 | 188306.946 | 176156.022 | 151631.844 | 120458.555
Office payroll (incl. employer PRSI and pension) | budget input | -658440 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870 | -54870
Rent: office and yard | budget input | -88800 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400
Insurance (public, employer and contractors all risks) | budget input | -115200 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600 | -9600
IT, software and estimating tools | budget input | -44400 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700 | -3700
Marketing and lead generation (residential) | budget input | -78000 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500 | -6500
Professional fees (audit, legal, tax) | budget input | -48000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000 | -4000
Training, health and safety, PPE | budget input | -31200 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600 | -2600
Office and administration | budget input | -25200 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100
Motor (non-site vehicles) | budget input | -20400 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700 | -1700
Subscriptions and memberships | budget input | -10200 | -850 | -850 | -850 | -850 | -850 | -850 | -850 | -850 | -850 | -850 | -850 | -850
Bond commission | budget input | -6240 | -520 | -520 | -520 | -520 | -520 | -520 | -520 | -520 | -520 | -520 | -520 | -520
Bad debts and specific provisions | budget input | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OVERHEADS |  | -1126080 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840 | -93840
EBITDA |  | 594518.924 | 8640.194 | -3287.032 | 1228.158 | 19580.863 | 44694.976 | 71678.983 | 93737.979 | 97051.436 | 94466.946 | 82316.022 | 57791.844 | 26618.555
Depreciation | budget input | -88800 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400 | -7400
Hire purchase interest | budget input | -8330 | -780 | -770 | -750 | -740 | -720 | -700 | -690 | -670 | -650 | -640 | -620 | -600
PROFIT BEFORE TAX |  | 497388.924 | 460.194 | -11457.032 | -6921.842 | 11440.863 | 36574.976 | 63578.983 | 85647.979 | 88981.436 | 86416.946 | 74276.022 | 49771.844 | 18618.555
Corporation tax (budget: 12.5% of positive monthly profit) |  | -64470.9748 | -57.5242 | 0 | 0 | -1430.1079 | -4571.872 | -7947.3729 | -10705.9974 | -11122.6795 | -10802.1182 | -9284.5027 | -6221.4805 | -2327.3194
NET PROFIT |  | 432917.9493 | 402.6697 | -11457.032 | -6921.842 | 10010.7551 | 32003.104 | 55631.6101 | 74941.9816 | 77858.7565 | 75614.8277 | 64991.5192 | 43550.3635 | 16291.2356
BUDGETED MONTH-END BALANCES
Cash at bank | budget balance | 610000 | 452000 | 470000 | 488000 | 500000 | 515000 | 530000 | 545000 | 560000 | 575000 | 590000 | 600000 | 610000
Trade receivables and SEAI grants | budget balance | 720000 | 690000 | 660000 | 640000 | 650000 | 680000 | 700000 | 720000 | 740000 | 760000 | 770000 | 760000 | 720000
Contract assets less contract liabilities | budget balance | 450000 | 480000 | 450000 | 420000 | 430000 | 450000 | 470000 | 480000 | 490000 | 500000 | 500000 | 480000 | 450000
Retentions receivable | budget balance | 195000 | 170000 | 165000 | 160000 | 165000 | 170000 | 175000 | 180000 | 185000 | 190000 | 195000 | 200000 | 195000